## PSPM Planner Report
PSPM Planner Report - | [5 empty] | Report Run: 1/9/2026 6:35:58 PM (UTC Time Zone)
Project Name: | MK-0001_NJIT Non Rolling Submission_OMA RP US |  |  | Planner Name: |  | NJIT
Initiative MK/V Number: | MK-0001 |  |  | App Type: |  | Marketing Application
[5 empty] | Component ID |  | Task Name | Document ID Regional | Dojument ID jentraP | SRC Link | Task Duration | Planned Start | Actual Start | Planned Finish | Actual Finish | Filing Status | Filing Notes | ORION Event Id | Additional ORION Event | Responsible | LCM | File Type | File Name | Planner Comments | Component Source | Task Index
Central Components - NJIT Non Rolling Submission_OMA_CentralPlan - REFERENCE ONLY | [10 empty] | 6 days | 2024-01-22 | 2024-01-25 | 2024-01-28 | 2024-02-01 | Completed | QC completed | 700007 |  | Alex Kim | N. Ortiz |  |  |  | Central | 1
|  | TEMPLATE: WMA Accelerated Central Plan - Original |  |  | 5 | [5 empty] | 222 days | 2024-01-17 | 2024-01-21 | 2024-08-26 | 2024-08-24 | Completed | QC completed | 700008 | Submission build | Jamie Carter | A. Shah |  |  |  | Central | 2
|  |  | Phase 3 - Submission Components for an Original Marketing Application |  | 1.8 |  | Phase 3 - Submission Components for an Original Marketing Application | 1 |  |  | 10 days | 2024-01-23 | 2024-01-22 | 2024-02-02 | 2024-02-03 | Completed | Completed as planned | 700009 | Publishing QC | Casey Rivera | R. Gupta | PDF | Phase_3_Submission_Components_for_an_Original_Marketing_Appl_0009.pdf | Timing estimate is illustrative | Central | 3
[5 empty] | 1 |  | Module 1 Administrative Information - GLOBAL | 2 |  |  | 215 days | 2024-01-18 | 2024-01-16 | 2024-08-20 | 2024-08-18 | Completed |  | 700010 |  | Sam Brooks | L. Bennett | DOCX | Module_1_Administrative_Information_GLOBAL_0010.docx | Sample entry for dashboard validation | Central | 4
[5 empty] | 1.4 |  | 1.4 Information about the Expert | 3 |  |  | 94 days | 2024-01-24 | 2024-01-29 | 2024-04-27 | 2024-04-26 | Completed | QC completed | 700011 | Publishing QC | Morgan Lee | M. Sullivan | PDF | Information_about_the_Expert_0011.pdf | Dummy data added for planning demo | Central | 5
[5 empty] | 1.4.1 |  | 1.4.1 Information about the Expert - Quality CV | 4 |  |  | 60 days | 2024-01-17 | 2024-01-17 | 2024-03-17 | 2024-03-24 | Completed | QC completed | 700012 | Archive release | Jordan Patel | A. Shah | DOCX | Information_about_the_Expert_Quality_CV_0012.docx | Placeholder timeline for reporting test | Central | 6
[5 empty] | 1.4.1 |  | 1.4.1 Information about the Expert - Quality Declaration | 5 |  |  | 24 days | 2024-01-20 | 2024-01-22 | 2024-02-13 |  | In Progress | Metadata check in progress | 700013 | Regional alignment | Sam Brooks | M. Sullivan | DOCX | Information_about_the_Expert_Quality_Declaration_0013.docx | Sample entry for dashboard validation | Central | 7
[5 empty] | 1.4.2 |  | 1.4.2 Information about the Expert - Nonclinical CV | 6 |  |  | 41 days | 2024-01-21 |  | 2024-03-02 |  | Not Started | Scheduled after current milestone | 700014 |  | Morgan Lee | N. Ortiz | PDF | Information_about_the_Expert_Nonclinical_CV_0014.pdf | Sample entry for dashboard validation | Central | 8
[5 empty] | 1.4.2 |  | 1.4.2 Information about the Expert - Nonclinical Declaration | 7 |  |  | 34 days | 2024-01-19 | 2024-01-18 | 2024-02-22 | 2024-02-21 | Completed | Completed as planned | 700015 |  | Taylor Chen | N. Ortiz | PDF | Information_about_the_Expert_Nonclinical_Declaration_0015.pdf | Placeholder timeline for reporting test | Central | 9
[5 empty] | 1.4.3 |  | 1.4.3 Information about the Expert - Clinical CV | 8 |  |  | 44 days | 2024-01-20 | 2024-01-22 | 2024-03-04 |  | In Progress | Pending cross-functional signoff | 700016 |  | Alex Kim | M. Sullivan | PDF | Information_about_the_Expert_Clinical_CV_0016.pdf | Dummy data added for planning demo | Central | 10
[5 empty] | 1.4.3 |  | 1.4.3 Information about the Expert - Clinical Declaration | 9 |  |  | 23 days | 2024-01-20 | 2024-01-23 | 2024-02-12 | 2024-02-15 | Completed | Released to archive | 700017 | Publishing QC | Taylor Chen | R. Gupta | DOCX | Information_about_the_Expert_Clinical_Declaration_0017.docx | Timing estimate is illustrative | Central | 11
[5 empty] | 1.8 |  | 1.8 RMP | 10 |  |  | 133 days | 2024-01-24 | 2024-01-21 | 2024-06-05 | 2024-06-05 | Completed | Released to archive | 700018 | Publishing QC | Sam Brooks | M. Sullivan | DOCX | RMP_0018.docx | Timing estimate is illustrative | Central | 12
[5 empty] | 1.8.2 |  | 1.8.2 HA approved EU RMP | 11 |  |  | 73 days | 2024-01-28 | 2024-02-03 | 2024-04-10 |  | In Progress | Regional review underway | 700019 |  | Alex Kim | R. Gupta | PDF | HA_approved_EU_RMP_0019.pdf | Dummy data added for planning demo | Central | 13
[5 empty] | 1.8.2 |  | 1.8.2 non-HA approved EU RMP | 12 |  |  | 32 days | 2024-01-29 | 2024-01-30 | 2024-03-01 | 2024-03-05 | Completed | Filed in baseline wave | 700020 | Archive release | Sam Brooks | L. Bennett | DOCX | non_HA_approved_EU_RMP_0020.docx | Timing estimate is illustrative | Central | 14
[5 empty] | 1.8.2 |  | 1.8.2 Core RMP | 13 |  |  | 55 days | 2024-01-23 | 2024-01-23 | 2024-03-18 | 2024-03-25 | Completed | Released to archive | 700021 | Archive release | Jordan Patel | A. Shah | PDF | Core_RMP_0021.pdf | Dummy data added for planning demo | Central | 15
[5 empty] | 2 |  | Module 2 Summaries | 14 |  |  | 236 days | 2024-01-24 | 2024-01-23 | 2024-09-16 | 2024-09-13 | Completed |  | 700022 | Publishing QC | Sam Brooks | A. Shah | DOCX | Module_2_Summaries_0022.docx | Timing estimate is illustrative | Central | 16
[5 empty] | 2.2 |  | 2.2 Introduction [hypercholest] | 15 |  |  | 82 days | 2024-01-31 | 2024-01-28 | 2024-04-22 | 2024-04-19 | Completed | Filed in baseline wave | 700023 | Publishing QC | Jamie Carter | R. Gupta | DOCX | Introduction_hypercholest_0023.docx | Placeholder timeline for reporting test | Central | 17
[5 empty] | 2.4 |  | 2.4 Nonclinical overview | 16 |  |  | 139 days | 2024-01-30 | 2024-01-27 | 2024-06-17 | 2024-06-13 | Completed | Filed in baseline wave | 700024 | Submission build | Morgan Lee | R. Gupta | DOCX | Nonclinical_overview_0024.docx | Placeholder timeline for reporting test | Central | 18
[5 empty] | 2.5 |  | 2.5 Clinical overview [hypercholest] | 17 |  |  | 92 days | 2024-01-26 | 2024-01-26 | 2024-04-27 |  | In Progress | Draft in QC review | 700025 | Regional alignment | Casey Rivera | L. Bennett | DOCX | Clinical_overview_hypercholest_0025.docx | Sample entry for dashboard validation | Central | 19
[5 empty] | 2.6 |  | 2.6 Nonclinical written and tabulated summaries | 18 |  |  | 98 days | 2024-02-02 | 2024-02-01 | 2024-05-10 | 2024-05-07 | Completed | Filed in baseline wave | 700026 | Publishing QC | Jamie Carter | N. Ortiz | PDF | Nonclinical_written_and_tabulated_summaries_0026.pdf | Sample entry for dashboard validation | Central | 20
[5 empty] | 2.6.1 |  | 2.6.1 Introduction | 19 |  |  | 71 days | 2024-02-02 | 2024-02-06 | 2024-04-13 | 2024-04-11 | Completed |  | 700027 |  | Jamie Carter | R. Gupta | XLSX | Introduction_0027.xlsx | Dummy data added for planning demo | Central | 21
[5 empty] | 2.6.2 |  | 2.6.2 Pharmacology written summary | 20 |  |  | 50 days | 2024-01-29 | 2024-01-28 | 2024-03-19 |  | In Progress | Publishing build in progress | 700028 | Regional alignment | Alex Kim | A. Shah | DOCX | Pharmacology_written_summary_0028.docx | Placeholder timeline for reporting test | Central | 22
[5 empty] | 2.6.3 |  | 2.6.3 Pharmacology tabulated summary | 21 |  |  | 65 days | 2024-01-27 | 2024-02-02 | 2024-04-01 |  | In Progress | Regional review underway | 700029 |  | Sam Brooks | M. Sullivan | PDF | Pharmacology_tabulated_summary_0029.pdf | Placeholder timeline for reporting test | Central | 23
[5 empty] | 2.6.4 |  | 2.6.4 Pharmacokinetic written summary | 22 |  |  | 53 days | 2024-02-05 | 2024-02-03 | 2024-03-29 | 2024-03-31 | Completed | Filed in baseline wave | 700030 |  | Morgan Lee | L. Bennett | PDF | Pharmacokinetic_written_summary_0030.pdf | Dummy data added for planning demo | Central | 24
[5 empty] | 2.6.5 |  | 2.6.5 Pharmacokinetic tabulated summary | 23 |  |  | 61 days | 2024-01-29 | 2024-02-04 | 2024-03-30 |  | In Progress | Publishing build in progress | 700031 | Regional alignment | Jamie Carter | N. Ortiz | PDF | Pharmacokinetic_tabulated_summary_0031.pdf | Sample entry for dashboard validation | Central | 25
[5 empty] | 2.6.6 |  | 2.6.6 Toxicology written summary | 24 |  |  | 35 days | 2024-02-03 | 2024-02-04 | 2024-03-09 | 2024-03-05 | Completed |  | 700032 | Submission build | Taylor Chen | L. Bennett | DOCX | Toxicology_written_summary_0032.docx | Timing estimate is illustrative | Central | 26
[5 empty] | 2.6.7 |  | 2.6.7 Toxicology tabulated summary | 25 |  |  | 49 days | 2024-01-31 | 2024-02-04 | 2024-03-20 | 2024-03-17 | Completed | Released to archive | 700033 |  | Morgan Lee | A. Shah | DOCX | Toxicology_tabulated_summary_0033.docx | Dummy data added for planning demo | Central | 27
[5 empty] | 2.7 |  | 2.7 Clinical summary | 26 |  |  | 96 days | 2024-01-31 | 2024-02-05 | 2024-05-06 | 2024-05-10 | Completed | Completed as planned | 700034 | Publishing QC | Jamie Carter | M. Sullivan | DOCX | Clinical_summary_0034.docx | Timing estimate is illustrative | Central | 28
[5 empty] | 2.7.1 |  | 2.7.1 Summary of Biopharmaceutic Studies and Associated Analytical Methods | 27 |  |  | 41 days | 2024-02-07 | 2024-02-04 | 2024-03-19 | 2024-03-18 | Completed | Released to archive | 700035 | Archive release | Taylor Chen | M. Sullivan | DOCX | Summary_of_Biopharmaceutic_Studies_and_Associated_Analytical_0035.docx | Placeholder timeline for reporting test | Central | 29
[5 empty] | 2.7.2 |  | 2.7.2 Summary of Clinical Pharmacology studies [Indication Suffix] | 28 |  |  | 27 days | 2024-02-07 | 2024-02-07 | 2024-03-05 | 2024-03-01 | Completed | QC completed | 700036 | Archive release | Jamie Carter | R. Gupta | DOCX | Summary_of_Clinical_Pharmacology_studies_Indication_Suffix_0036.docx | Dummy data added for planning demo | Central | 30
[5 empty] | 2.7.3 |  | 2.7.3 Summary of Clinical Efficacy [Indication Suffix] | 29 |  |  | 30 days | 2024-02-01 | 2024-02-04 | 2024-03-02 | 2024-02-28 | Completed | QC completed | 700037 |  | Jordan Patel | N. Ortiz | PDF | Summary_of_Clinical_Efficacy_Indication_Suffix_0037.pdf | Sample entry for dashboard validation | Central | 31
[5 empty] | 2.7.4 |  | 2.7.4 Summary of Clinical Safety [Indication Suffix] | 30 |  |  | 49 days | 2024-02-05 | 2024-02-06 | 2024-03-25 |  | In Progress | Regional review underway | 700038 | Publishing prep | Alex Kim | L. Bennett | PDF | Summary_of_Clinical_Safety_Indication_Suffix_0038.pdf | Dummy data added for planning demo | Central | 32
[5 empty] | 2.7.5 |  | 2.7.5 References | 31 |  |  | 49 days | 2024-02-09 | 2024-02-14 | 2024-03-29 | 2024-03-27 | Completed | Released to archive | 700039 | Publishing QC | Taylor Chen | A. Shah | XLSX | References_0039.xlsx | Sample entry for dashboard validation | Central | 33
[5 empty] | 2.7.6 |  | 2.7.6 Synopses of individual studies | 32 |  |  | 52 days | 2024-02-10 | 2024-02-09 | 2024-04-02 | 2024-04-09 | Completed |  | 700040 | Submission build | Sam Brooks | N. Ortiz | PDF | Synopses_of_individual_studies_0040.pdf | Sample entry for dashboard validation | Central | 34
[5 empty] | 4 |  | Module 4 Nonclinical Study Reports | 33 |  |  | 219 days | 2024-02-08 | 2024-02-12 | 2024-09-14 |  | In Progress | Pending cross-functional signoff | 700041 | QC review | Morgan Lee | L. Bennett | DOCX | Module_4_Nonclinical_Study_Reports_0041.docx | Placeholder timeline for reporting test | Central | 35
[5 empty] | 4.2 |  | 4.2 Study reports | 34 |  |  | 62 days | 2024-02-11 | 2024-02-16 | 2024-04-13 | 2024-04-13 | Completed |  | 700042 | Archive release | Sam Brooks | M. Sullivan | XLSX | Study_reports_0042.xlsx | Timing estimate is illustrative | Central | 36
[5 empty] | 4.2.1 |  | 4.2.1 Pharmacology | 35 |  |  | 33 days | 2024-02-08 | 2024-02-09 | 2024-03-12 | 2024-03-18 | Completed | QC completed | 700043 | Submission build | Sam Brooks | N. Ortiz | XLSX | Pharmacology_0043.xlsx | Placeholder timeline for reporting test | Central | 37
[5 empty] | 4.2.1.1 |  | 4.2.1.1 Primary pharmacodynamics | 36 |  |  | 31 days | 2024-02-06 | 2024-02-10 | 2024-03-08 | 2024-03-13 | Completed |  | 700044 |  | Sam Brooks | M. Sullivan | DOCX | Primary_pharmacodynamics_0044.docx | Sample entry for dashboard validation | Central | 38
[5 empty] | 4.2.1.1 |  | Study report [pd001mk0001] and related information | 37 |  |  | 23 days | 2024-02-06 | 2024-02-09 | 2024-02-29 | 2024-02-27 | Completed | Completed as planned | 700045 | Publishing QC | Jordan Patel | R. Gupta | PDF | Study_report_pd001mk0001_and_related_information_0045.pdf | Placeholder timeline for reporting test | Central | 39
[5 empty] | 4.2.1.1 |  | Study report [pd002mk0001] and related information | 38 |  |  | 11 days | 2024-02-10 | 2024-02-12 | 2024-02-21 |  | In Progress | Awaiting final source document | 700046 |  | Alex Kim | R. Gupta | DOCX | Study_report_pd002mk0001_and_related_information_0046.docx | Dummy data added for planning demo | Central | 40
[5 empty] | 4.2.1.1 |  | Study report [pd004mk0001] and related information | 39 |  |  | 34 days | 2024-02-15 | 2024-02-20 | 2024-03-20 | 2024-03-22 | Completed | Filed in baseline wave | 700047 |  | Jamie Carter | R. Gupta | PDF | Study_report_pd004mk0001_and_related_information_0047.pdf | Sample entry for dashboard validation | Central | 41
[5 empty] | 4.2.1.1 |  | Study report [pd005mk0001] and related information | 40 |  |  | 20 days | 2024-02-13 | 2024-02-16 | 2024-03-04 |  | In Progress | Pending cross-functional signoff | 700048 | Authoring | Alex Kim | R. Gupta | PDF | Study_report_pd005mk0001_and_related_information_0048.pdf | Sample entry for dashboard validation | Central | 42
[5 empty] | 4.2.1.2 |  | 4.2.1.2 Secondary pharmacodynamics | 41 |  |  | 27 days | 2024-02-11 | 2024-02-13 | 2024-03-09 | 2024-03-14 | Completed |  | 700049 |  | Jordan Patel | N. Ortiz | DOCX | Secondary_pharmacodynamics_0049.docx | Sample entry for dashboard validation | Central | 43
[5 empty] | 4.2.1.2 |  | Study report [pd003mk0001] and related information | 42 |  |  | 28 days | 2024-02-11 | 2024-02-10 | 2024-03-10 | 2024-03-17 | Completed |  | 700050 | Publishing QC | Casey Rivera | A. Shah | DOCX | Study_report_pd003mk0001_and_related_information_0050.docx | Placeholder timeline for reporting test | Central | 44
[5 empty] | 4.2.1.2 |  | Study report [tt175072fin] and related information | 43 |  |  | 15 days | 2024-02-17 | 2024-02-18 | 2024-03-03 | 2024-02-28 | Completed | QC completed | 700051 |  | Sam Brooks | N. Ortiz | PDF | Study_report_tt175072fin_and_related_information_0051.pdf | Timing estimate is illustrative | Central | 45
[5 empty] | 4.2.1.3 |  | 4.2.1.3 Safety pharmacology | 44 |  |  | 26 days | 2024-02-15 | 2024-02-16 | 2024-03-12 | 2024-03-15 | Completed |  | 700052 |  | Morgan Lee | A. Shah | XLSX | Safety_pharmacology_0052.xlsx | Placeholder timeline for reporting test | Central | 46
[5 empty] | 4.2.1.3 |  | Study report [tt172962fin] and related information | 45 |  |  | 14 days | 2024-02-18 | 2024-02-24 | 2024-03-03 |  | In Progress | Draft in QC review | 700053 |  | Jordan Patel | L. Bennett | DOCX | Study_report_tt172962fin_and_related_information_0053.docx | Dummy data added for planning demo | Central | 47
[5 empty] | 4.2.1.3 |  | Study report [tt184703fin] and related information | 46 |  |  | 14 days | 2024-02-16 | 2024-02-19 | 2024-03-01 |  | In Progress | Metadata check in progress | 700054 | Publishing prep | Morgan Lee | N. Ortiz | DOCX | Study_report_tt184703fin_and_related_information_0054.docx | Dummy data added for planning demo | Central | 48
[5 empty] | 4.2.1.3 |  | Study report [tt185801fin] and related information | 47 |  |  | 28 days | 2024-02-13 | 2024-02-13 | 2024-03-12 | 2024-03-18 | Completed |  | 700055 |  | Jordan Patel | A. Shah | DOCX | Study_report_tt185801fin_and_related_information_0055.docx | Sample entry for dashboard validation | Central | 49
[5 empty] | 4.2.1.3 |  | Study report [tt185803fin] and related information | 48 |  |  | 19 days | 2024-02-13 | 2024-02-14 | 2024-03-03 | 2024-02-28 | Completed |  | 700056 | Archive release | Taylor Chen | M. Sullivan | DOCX | Study_report_tt185803fin_and_related_information_0056.docx | Sample entry for dashboard validation | Central | 50
[5 empty] | 4.2.1.3 |  | Study report [tt185900fin] and related information | 49 |  |  | 16 days | 2024-02-13 | 2024-02-14 | 2024-02-29 |  | In Progress | Metadata check in progress | 700057 |  | Alex Kim | A. Shah | PDF | Study_report_tt185900fin_and_related_information_0057.pdf | Dummy data added for planning demo | Central | 51
[5 empty] | 4.2.1.3 |  | Study report [tt195900fin] and related information | 50 |  |  | 13 days | 2024-02-14 | 2024-02-14 | 2024-02-27 | 2024-03-04 | Completed | Released to archive | 700058 | Publishing QC | Jordan Patel | M. Sullivan | DOCX | Study_report_tt195900fin_and_related_information_0058.docx | Dummy data added for planning demo | Central | 52
[5 empty] | 4.2.2 |  | 4.2.2 Pharmacokinetics | 51 |  |  | 21 days | 2024-02-16 | 2024-02-18 | 2024-03-08 | 2024-03-04 | Completed | Completed as planned | 700059 | Publishing QC | Alex Kim | N. Ortiz | DOCX | Pharmacokinetics_0059.docx | Dummy data added for planning demo | Central | 53
[5 empty] | 4.2.2.1 |  | 4.2.2.1 Analytical methods and validation reports | 52 |  |  | 15 days | 2024-02-17 | 2024-02-21 | 2024-03-03 | 2024-03-09 | Completed | Released to archive | 700060 |  | Morgan Lee | A. Shah | DOCX | Analytical_methods_and_validation_reports_0060.docx | Dummy data added for planning demo | Central | 54
[5 empty] | 4.2.2.1 |  | Study report [055DG9] and related information | 53 |  |  | 7 days | 2024-02-23 | 2024-02-21 | 2024-03-01 | 2024-03-08 | Completed |  | 700061 | Publishing QC | Sam Brooks | A. Shah | DOCX | Study_report_055DG9_and_related_information_0061.docx | Dummy data added for planning demo | Central | 55
[5 empty] | 4.2.2.1 |  | Study report [05FRC2] and related information | 54 |  |  | 32 days | 2024-02-20 | 2024-02-18 | 2024-03-23 | 2024-03-23 | Completed | Released to archive | 700062 |  | Casey Rivera | A. Shah | DOCX | Study_report_05FRC2_and_related_information_0062.docx | Timing estimate is illustrative | Central | 56
[5 empty] | 4.2.2.1 |  | Study report [07XM2X] and related information | 55 |  |  | 14 days | 2024-02-24 | 2024-02-27 | 2024-03-09 | 2024-03-13 | Completed | QC completed | 700063 | Submission build | Morgan Lee | R. Gupta | PDF | Study_report_07XM2X_and_related_information_0063.pdf | Timing estimate is illustrative | Central | 57
[5 empty] | 4.2.2.1 |  | Study report [08WH66] and related information | 56 |  |  | 8 days | 2024-02-18 | 2024-02-21 | 2024-02-26 | 2024-03-01 | Completed |  | 700064 | Publishing QC | Morgan Lee | N. Ortiz | DOCX | Study_report_08WH66_and_related_information_0064.docx | Timing estimate is illustrative | Central | 58
[5 empty] | 4.2.2.1 |  | Study report [08WQR8] and related information | 57 |  |  | 35 days | 2024-02-23 | 2024-02-28 | 2024-03-29 | 2024-03-27 | Completed | Filed in baseline wave | 700065 | Submission build | Jordan Patel | M. Sullivan | DOCX | Study_report_08WQR8_and_related_information_0065.docx | Timing estimate is illustrative | Central | 59
[5 empty] | 4.2.2.1 |  | Study report [08WQRR] and related information | 58 |  |  | 12 days | 2024-02-19 | 2024-02-16 | 2024-03-02 | 2024-03-06 | Completed | Released to archive | 700066 |  | Alex Kim | R. Gupta | PDF | Study_report_08WQRR_and_related_information_0066.pdf | Placeholder timeline for reporting test | Central | 60
[5 empty] | 4.2.2.1 |  | Study report [08WQSF] and related information | 59 |  |  | 13 days | 2024-02-20 | 2024-02-24 | 2024-03-04 | 2024-03-05 | Completed | QC completed | 700067 | Submission build | Sam Brooks | N. Ortiz | PDF | Study_report_08WQSF_and_related_information_0067.pdf | Placeholder timeline for reporting test | Central | 61
[5 empty] | 4.2.2.2 |  | 4.2.2.2 Absorption | 60 |  |  | 35 days | 2024-02-20 | 2024-02-24 | 2024-03-26 | 2024-03-29 | Completed | QC completed | 700068 |  | Sam Brooks | R. Gupta | XLSX | Absorption_0068.xlsx | Timing estimate is illustrative | Central | 62
[5 empty] | 4.2.2.2 |  | Study report [pk001mk0001] and related information | 61 |  |  | 32 days | 2024-02-25 | 2024-02-28 | 2024-03-28 | 2024-03-26 | Completed | Completed as planned | 700069 | Archive release | Jordan Patel | N. Ortiz | DOCX | Study_report_pk001mk0001_and_related_information_0069.docx | Placeholder timeline for reporting test | Central | 63
[5 empty] | 4.2.2.3 |  | 4.2.2.3 Distribution | 62 |  |  | 11 days | 2024-02-25 | 2024-02-27 | 2024-03-07 | 2024-03-10 | Completed | Released to archive | 700070 |  | Morgan Lee | R. Gupta | DOCX | Distribution_0070.docx | Dummy data added for planning demo | Central | 64
[5 empty] | 4.2.2.3 |  | Study report [PK002mk0001] and related information | 63 |  |  | 27 days | 2024-02-23 | 2024-02-24 | 2024-03-21 | 2024-03-19 | Completed |  | 700071 | Submission build | Morgan Lee | A. Shah | PDF | Study_report_PK002mk0001_and_related_information_0071.pdf | Dummy data added for planning demo | Central | 65
[5 empty] | 4.2.2.3 |  | Study report [pk014mk0001] and related information | 64 |  |  | 27 days | 2024-02-29 | 2024-03-03 | 2024-03-27 | 2024-04-01 | Completed | Filed in baseline wave | 700072 | Publishing QC | Taylor Chen | R. Gupta | DOCX | Study_report_pk014mk0001_and_related_information_0072.docx | Timing estimate is illustrative | Central | 66
[5 empty] | 4.2.2.3 |  | Study report [pk015mk0001] and related information | 65 |  |  | 19 days | 2024-02-27 | 2024-02-28 | 2024-03-17 | 2024-03-15 | Completed | Released to archive | 700073 |  | Taylor Chen | A. Shah | DOCX | Study_report_pk015mk0001_and_related_information_0073.docx | Placeholder timeline for reporting test | Central | 67
[5 empty] | 4.2.2.3 |  | Study report [tt247090] and related information | 66 |  |  | 7 days | 2024-03-02 | 2024-03-01 | 2024-03-09 | 2024-03-13 | Completed | Filed in baseline wave | 700074 |  | Jordan Patel | N. Ortiz | PDF | Study_report_tt247090_and_related_information_0074.pdf | Sample entry for dashboard validation | Central | 68
[5 empty] | 4.2.2.4 |  | 4.2.2.4 Metabolism | 67 |  |  | 8 days | 2024-02-28 | 2024-03-03 | 2024-03-07 | 2024-03-06 | Completed | Completed as planned | 700075 | Archive release | Morgan Lee | N. Ortiz | PDF | Metabolism_0075.pdf | Timing estimate is illustrative | Central | 69
[5 empty] | 4.2.2.4 |  | Study report [PK018mk0001] and related information | 68 |  |  | 32 days | 2024-03-03 | 2024-03-07 | 2024-04-04 | 2024-04-07 | Completed | Completed as planned | 700076 | Publishing QC | Sam Brooks | R. Gupta | PDF | Study_report_PK018mk0001_and_related_information_0076.pdf | Placeholder timeline for reporting test | Central | 70
[5 empty] | 4.2.2.5 |  | 4.2.2.5 Excretion | 69 |  |  | 25 days | 2024-02-28 | 2024-02-27 | 2024-03-24 | 2024-03-26 | Completed | Released to archive | 700077 | Archive release | Taylor Chen | A. Shah | XLSX | Excretion_0077.xlsx | Placeholder timeline for reporting test | Central | 71
[5 empty] | 4.2.2.5 |  | Study report [pk003mk0001] and related information | 70 |  |  | 14 days | 2024-03-02 | 2024-03-04 | 2024-03-16 | 2024-03-17 | Completed | Released to archive | 700078 |  | Taylor Chen | A. Shah | PDF | Study_report_pk003mk0001_and_related_information_0078.pdf | Sample entry for dashboard validation | Central | 72
[5 empty] | 4.2.2.5 |  | Study report [pk009mk0001] and related information | 71 |  |  | 14 days | 2024-02-28 | 2024-02-29 | 2024-03-13 | 2024-03-12 | Completed | Filed in baseline wave | 700079 | Submission build | Jordan Patel | R. Gupta | PDF | Study_report_pk009mk0001_and_related_information_0079.pdf | Timing estimate is illustrative | Central | 73
[5 empty] | 4.2.2.5 |  | Study report [pk010mk0001] and related information | 72 |  |  | 32 days | 2024-03-03 | 2024-03-01 | 2024-04-04 | 2024-04-07 | Completed | Released to archive | 700080 |  | Jordan Patel | M. Sullivan | PDF | Study_report_pk010mk0001_and_related_information_0080.pdf | Sample entry for dashboard validation | Central | 74
[5 empty] | 4.2.2.5 |  | Study report [pk013mk0001] and related information | 73 |  |  | 14 days | 2024-02-27 | 2024-02-26 | 2024-03-12 | 2024-03-10 | Completed |  | 700081 | Publishing QC | Taylor Chen | N. Ortiz | PDF | Study_report_pk013mk0001_and_related_information_0081.pdf | Timing estimate is illustrative | Central | 75
[5 empty] | 4.2.2.6 |  | 4.2.2.6 Pharmacokinetic drug interactions | 74 |  |  | 12 days | 2024-03-02 | 2024-03-05 | 2024-03-14 | 2024-03-19 | Completed |  | 700082 | Publishing QC | Sam Brooks | R. Gupta | PDF | Pharmacokinetic_drug_interactions_0082.pdf | Timing estimate is illustrative | Central | 76
[5 empty] | 4.2.2.6 |  | Study report [pk004mk0001] and related information | 75 |  |  | 26 days | 2024-03-06 |  | 2024-04-01 |  | Not Started | Scheduled after current milestone | 700083 |  | Jordan Patel | N. Ortiz | DOCX | Study_report_pk004mk0001_and_related_information_0083.docx | Timing estimate is illustrative | Central | 77
[5 empty] | 4.2.2.6 |  | Study report [pk005mk0001] and related information | 76 |  |  | 26 days | 2024-03-01 | 2024-03-02 | 2024-03-27 | 2024-03-25 | Completed | QC completed | 700084 |  | Taylor Chen | M. Sullivan | PDF | Study_report_pk005mk0001_and_related_information_0084.pdf | Timing estimate is illustrative | Central | 78
[5 empty] | 4.2.2.6 |  | Study report [pk006mk0001] and related information | 77 |  |  | 19 days | 2024-03-06 | 2024-03-03 | 2024-03-25 | 2024-03-24 | Completed |  | 700085 |  | Sam Brooks | L. Bennett | PDF | Study_report_pk006mk0001_and_related_information_0085.pdf | Dummy data added for planning demo | Central | 79
[5 empty] | 4.2.2.6 |  | Study report [pk007mk0001] and related information | 78 |  |  | 22 days | 2024-03-03 | 2024-03-01 | 2024-03-25 |  | In Progress | Pending cross-functional signoff | 700086 |  | Jamie Carter | A. Shah | PDF | Study_report_pk007mk0001_and_related_information_0086.pdf | Sample entry for dashboard validation | Central | 80
[5 empty] | 4.2.2.6 |  | Study report [pk008mk0001] and related information | 79 |  |  | 35 days | 2024-03-03 | 2024-02-29 | 2024-04-07 | 2024-04-13 | Completed | Released to archive | 700087 |  | Casey Rivera | R. Gupta | PDF | Study_report_pk008mk0001_and_related_information_0087.pdf | Sample entry for dashboard validation | Central | 81
[5 empty] | 4.2.2.6 |  | Study report [pk016mk0001] and related information | 80 |  |  | 32 days | 2024-03-05 | 2024-03-08 | 2024-04-06 | 2024-04-07 | Completed |  | 700088 |  | Alex Kim | L. Bennett | PDF | Study_report_pk016mk0001_and_related_information_0088.pdf | Placeholder timeline for reporting test | Central | 82
[5 empty] | 4.2.2.6 |  | Study report [pk017mk0001] and related information | 81 |  |  | 31 days | 2024-03-09 | 2024-03-07 | 2024-04-09 | 2024-04-09 | Completed |  | 700089 |  | Casey Rivera | R. Gupta | PDF | Study_report_pk017mk0001_and_related_information_0089.pdf | Dummy data added for planning demo | Central | 83
[5 empty] | 4.2.2.6 |  | Study report [PK020mk0001] and related information | 82 |  |  | 25 days | 2024-03-03 | 2024-03-08 | 2024-03-28 | 2024-03-24 | Completed | Released to archive | 700090 | Submission build | Sam Brooks | R. Gupta | DOCX | Study_report_PK020mk0001_and_related_information_0090.docx | Placeholder timeline for reporting test | Central | 84
[5 empty] | 4.2.2.7 |  | 4.2.2.7 Other pharmacokinetic studies | 83 |  |  | 11 days | 2024-03-05 | 2024-03-06 | 2024-03-16 | 2024-03-16 | Completed |  | 700091 |  | Taylor Chen | R. Gupta | XLSX | Other_pharmacokinetic_studies_0091.xlsx | Placeholder timeline for reporting test | Central | 85
[5 empty] | 4.2.2.7 |  | Study report [PK012mk0001] and related information | 84 |  |  | 31 days | 2024-03-10 | 2024-03-15 | 2024-04-10 | 2024-04-14 | Completed | Released to archive | 700092 | Submission build | Morgan Lee | M. Sullivan | DOCX | Study_report_PK012mk0001_and_related_information_0092.docx | Placeholder timeline for reporting test | Central | 86
[5 empty] | 4.2.3 |  | 4.2.3 Toxicology | 85 |  |  | 56 days | 2024-03-09 | 2024-03-12 | 2024-05-04 | 2024-05-11 | Completed | Filed in baseline wave | 700093 | Publishing QC | Sam Brooks | N. Ortiz | DOCX | Toxicology_0093.docx | Timing estimate is illustrative | Central | 87
[5 empty] | 4.2.3.2 |  | 4.2.3.2 Repeat dose toxicity [Species, route, duration] | 86 |  |  | 13 days | 2024-03-06 | 2024-03-08 | 2024-03-19 | 2024-03-23 | Completed |  | 700094 | Publishing QC | Jordan Patel | L. Bennett | XLSX | Repeat_dose_toxicity_Species_route_duration_0094.xlsx | Dummy data added for planning demo | Central | 88
[5 empty] | 4.2.3.2 |  | Study report [tt181034fin] and related information | 87 |  |  | 33 days | 2024-03-07 | 2024-03-10 | 2024-04-09 | 2024-04-06 | Completed | Completed as planned | 700095 | Archive release | Jordan Patel | R. Gupta | PDF | Study_report_tt181034fin_and_related_information_0095.pdf | Dummy data added for planning demo | Central | 89
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt181034 | 88 |  |  | 19 days | 2024-03-12 | 2024-03-17 | 2024-03-31 | 2024-03-31 | Completed |  | 700096 | Publishing QC | Jamie Carter | N. Ortiz | ZIP | NonClinical_SEND_Datasets_tt181034_0096.zip | Sample entry for dashboard validation | Central | 90
[5 empty] | 4.2.3.2 |  | Study report [tt181035fin] and related information | 89 |  |  | 7 days | 2024-03-14 | 2024-03-19 | 2024-03-21 | 2024-03-21 | Completed | Filed in baseline wave | 700097 | Publishing QC | Jamie Carter | M. Sullivan | PDF | Study_report_tt181035fin_and_related_information_0097.pdf | Timing estimate is illustrative | Central | 91
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt181035 | 90 |  |  | 18 days | 2024-03-08 | 2024-03-05 | 2024-03-26 | 2024-03-24 | Completed | Completed as planned | 700098 | Archive release | Jamie Carter | L. Bennett | CSV | NonClinical_SEND_Datasets_tt181035_0098.csv | Sample entry for dashboard validation | Central | 92
[5 empty] | 4.2.3.2 |  | Study report [tt182515fin] and related information | 91 |  |  | 25 days | 2024-03-14 | 2024-03-11 | 2024-04-08 | 2024-04-15 | Completed | Completed as planned | 700099 | Publishing QC | Taylor Chen | R. Gupta | DOCX | Study_report_tt182515fin_and_related_information_0099.docx | Placeholder timeline for reporting test | Central | 93
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt182515 | 92 |  |  | 14 days | 2024-03-13 | 2024-03-13 | 2024-03-27 | 2024-03-30 | Completed | Released to archive | 700100 |  | Alex Kim | R. Gupta | XLSX | NonClinical_SEND_Datasets_tt182515_0100.xlsx | Sample entry for dashboard validation | Central | 94
[5 empty] | 4.2.3.2 |  | Study report [tt182516fin] and related information | 93 |  |  | 10 days | 2024-03-17 | 2024-03-22 | 2024-03-27 | 2024-03-27 | Completed | QC completed | 700101 | Publishing QC | Jamie Carter | M. Sullivan | DOCX | Study_report_tt182516fin_and_related_information_0101.docx | Placeholder timeline for reporting test | Central | 95
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt182516 | 94 |  |  | 19 days | 2024-03-17 | 2024-03-17 | 2024-04-05 | 2024-04-06 | Completed | Released to archive | 700102 |  | Taylor Chen | A. Shah | CSV | NonClinical_SEND_Datasets_tt182516_0102.csv | Dummy data added for planning demo | Central | 96
[5 empty] | 4.2.3.2 |  | Study report [tt201020fin] and related information | 95 |  |  | 9 days | 2024-03-15 | 2024-03-15 | 2024-03-24 | 2024-03-30 | Completed | Filed in baseline wave | 700103 | Archive release | Casey Rivera | R. Gupta | PDF | Study_report_tt201020fin_and_related_information_0103.pdf | Placeholder timeline for reporting test | Central | 97
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt201020 | 96 |  |  | 16 days | 2024-03-14 | 2024-03-16 | 2024-03-30 | 2024-03-27 | Completed |  | 700104 | Submission build | Casey Rivera | R. Gupta | CSV | NonClinical_SEND_Datasets_tt201020_0104.csv | Timing estimate is illustrative | Central | 98
[5 empty] | 4.2.3.2 |  | Study report [tt201021fin] and related information | 97 |  |  | 12 days | 2024-03-16 | 2024-03-17 | 2024-03-28 |  | In Progress | Publishing build in progress | 700105 | QC review | Jordan Patel | N. Ortiz | DOCX | Study_report_tt201021fin_and_related_information_0105.docx | Timing estimate is illustrative | Central | 99
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt201021 | 98 |  |  | 13 days | 2024-03-15 | 2024-03-18 | 2024-03-28 |  | In Progress | Awaiting final source document | 700106 | Authoring | Alex Kim | A. Shah | ZIP | NonClinical_SEND_Datasets_tt201021_0106.zip | Sample entry for dashboard validation | Central | 100
[5 empty] | 4.2.3.2 |  | Study report [tt221002fin] and related information | 99 |  |  | 31 days | 2024-03-13 | 2024-03-11 | 2024-04-13 |  | In Progress | Publishing build in progress | 700107 | Publishing prep | Taylor Chen | R. Gupta | DOCX | Study_report_tt221002fin_and_related_information_0107.docx | Placeholder timeline for reporting test | Central | 101
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt221002 | 100 |  |  | 12 days | 2024-03-20 |  | 2024-04-01 |  | Not Started | Resource assignment not yet confirmed | 700108 |  | Morgan Lee | L. Bennett | XLSX | NonClinical_SEND_Datasets_tt221002_0108.xlsx | Timing estimate is illustrative | Central | 102
[5 empty] | 4.2.3.2 |  | Study report [tt229000fin] and related information | 101 |  |  | 23 days | 2024-03-14 | 2024-03-18 | 2024-04-06 | 2024-04-10 | Completed | Completed as planned | 700109 |  | Morgan Lee | L. Bennett | PDF | Study_report_tt229000fin_and_related_information_0109.pdf | Sample entry for dashboard validation | Central | 103
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt229000 | 102 |  |  | 29 days | 2024-03-16 | 2024-03-18 | 2024-04-14 | 2024-04-21 | Completed | Completed as planned | 700110 | Publishing QC | Sam Brooks | N. Ortiz | CSV | NonClinical_SEND_Datasets_tt229000_0110.csv | Dummy data added for planning demo | Central | 104
[5 empty] | 4.2.3.2 |  | Study report [tt176024fin] and related information | 103 |  |  | 18 days | 2024-03-20 | 2024-03-21 | 2024-04-07 | 2024-04-05 | Completed |  | 700111 | Archive release | Jordan Patel | R. Gupta | DOCX | Study_report_tt176024fin_and_related_information_0111.docx | Placeholder timeline for reporting test | Central | 105
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt176024 | 104 |  |  | 12 days | 2024-03-21 | 2024-03-21 | 2024-04-02 | 2024-04-04 | Completed | QC completed | 700112 | Archive release | Jamie Carter | L. Bennett | CSV | NonClinical_SEND_Datasets_tt176024_0112.csv | Sample entry for dashboard validation | Central | 106
[5 empty] | 4.2.3.2 |  | Study report [tt176045fin] and related information | 105 |  |  | 25 days | 2024-03-18 | 2024-03-18 | 2024-04-12 | 2024-04-09 | Completed | QC completed | 700113 | Submission build | Taylor Chen | L. Bennett | DOCX | Study_report_tt176045fin_and_related_information_0113.docx | Timing estimate is illustrative | Central | 107
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt176045 | 106 |  |  | 32 days | 2024-03-19 | 2024-03-19 | 2024-04-20 |  | In Progress | Publishing build in progress | 700114 | Authoring | Jordan Patel | L. Bennett | CSV | NonClinical_SEND_Datasets_tt176045_0114.csv | Timing estimate is illustrative | Central | 108
[5 empty] | 4.2.3.2 |  | Study report [tt181033fin] and related information | 107 |  |  | 24 days | 2024-03-26 | 2024-03-30 | 2024-04-19 | 2024-04-19 | Completed | QC completed | 700115 |  | Jamie Carter | M. Sullivan | PDF | Study_report_tt181033fin_and_related_information_0115.pdf | Sample entry for dashboard validation | Central | 109
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt181033 | 108 |  |  | 29 days | 2024-03-19 | 2024-03-19 | 2024-04-17 | 2024-04-17 | Completed | Released to archive | 700116 | Publishing QC | Casey Rivera | R. Gupta | CSV | NonClinical_SEND_Datasets_tt181033_0116.csv | Placeholder timeline for reporting test | Central | 110
[5 empty] | 4.2.3.2 |  | Study report [tt182506fin] and related information | 109 |  |  | 24 days | 2024-03-24 | 2024-03-25 | 2024-04-17 | 2024-04-18 | Completed | Completed as planned | 700117 |  | Alex Kim | R. Gupta | PDF | Study_report_tt182506fin_and_related_information_0117.pdf | Timing estimate is illustrative | Central | 111
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt182506 | 110 |  |  | 18 days | 2024-03-23 | 2024-03-28 | 2024-04-10 | 2024-04-13 | Completed | Released to archive | 700118 | Publishing QC | Casey Rivera | M. Sullivan | CSV | NonClinical_SEND_Datasets_tt182506_0118.csv | Sample entry for dashboard validation | Central | 112
[5 empty] | 4.2.3.2 |  | Study report [tt186041fin] and related information | 111 |  |  | 34 days | 2024-03-22 | 2024-03-24 | 2024-04-25 | 2024-04-27 | Completed |  | 700119 |  | Casey Rivera | A. Shah | PDF | Study_report_tt186041fin_and_related_information_0119.pdf | Timing estimate is illustrative | Central | 113
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt186041 | 112 |  |  | 14 days | 2024-03-26 | 2024-03-27 | 2024-04-09 | 2024-04-16 | Completed | QC completed | 700120 |  | Sam Brooks | L. Bennett | CSV | NonClinical_SEND_Datasets_tt186041_0120.csv | Sample entry for dashboard validation | Central | 114
[5 empty] | 4.2.3.3 |  | 4.2.3.3 Genotoxicity | 113 |  |  | 30 days | 2024-03-26 | 2024-03-30 | 2024-04-25 | 2024-04-27 | Completed | Filed in baseline wave | 700121 | Submission build | Jamie Carter | A. Shah | PDF | Genotoxicity_0121.pdf | Timing estimate is illustrative | Central | 115
[5 empty] | 4.2.3.3.1 |  | 4.2.3.3.1 In vitro | 114 |  |  | 30 days | 2024-03-26 | 2024-03-24 | 2024-04-25 | 2024-04-24 | Completed | Filed in baseline wave | 700122 |  | Alex Kim | A. Shah | PDF | In_vitro_0122.pdf | Sample entry for dashboard validation | Central | 116
[5 empty] | 4.2.3.3.1 |  | Study report [tt178133fin] and related information | 115 |  |  | 8 days | 2024-03-30 | 2024-04-02 | 2024-04-07 | 2024-04-11 | Completed | Completed as planned | 700123 | Publishing QC | Morgan Lee | M. Sullivan | PDF | Study_report_tt178133fin_and_related_information_0123.pdf | Dummy data added for planning demo | Central | 117
[5 empty] | 4.2.3.3.1 |  | Study report [tt188042fin] and related information | 116 |  |  | 16 days | 2024-03-29 | 2024-03-30 | 2024-04-14 | 2024-04-17 | Completed | Filed in baseline wave | 700124 | Submission build | Taylor Chen | N. Ortiz | PDF | Study_report_tt188042fin_and_related_information_0124.pdf | Dummy data added for planning demo | Central | 118
[5 empty] | 4.2.3.3.1 |  | Study report [tt188699fin] and related information | 117 |  |  | 34 days | 2024-03-28 | 2024-04-02 | 2024-05-01 |  | In Progress | Publishing build in progress | 700125 |  | Morgan Lee | M. Sullivan | DOCX | Study_report_tt188699fin_and_related_information_0125.docx | Timing estimate is illustrative | Central | 119
[5 empty] | 4.2.3.4 |  | 4.2.3.4 Carcinogenicity | 118 |  |  | 12 days | 2024-04-01 | 2024-04-05 | 2024-04-13 | 2024-04-19 | Completed |  | 700126 |  | Taylor Chen | M. Sullivan | DOCX | Carcinogenicity_0126.docx | Placeholder timeline for reporting test | Central | 120
[5 empty] | 4.2.3.4.1 |  | 4.2.3.4.1 Long term studies [Species] | 119 |  |  | 24 days | 2024-04-01 | 2024-03-30 | 2024-04-25 | 2024-04-28 | Completed | QC completed | 700127 | Archive release | Casey Rivera | R. Gupta | PDF | Long_term_studies_Species_0127.pdf | Placeholder timeline for reporting test | Central | 121
[5 empty] | 4.2.3.4.1 |  | Study report [WOE001mk0001] and related information | 120 |  |  | 7 days | 2024-03-25 | 2024-03-24 | 2024-04-01 | 2024-04-02 | Completed | QC completed | 700128 |  | Taylor Chen | A. Shah | DOCX | Study_report_WOE001mk0001_and_related_information_0128.docx | Sample entry for dashboard validation | Central | 122
[5 empty] | 4.2.3.4.1 |  | NonClinical SEND Datasets WOE001mk0001 | 121 |  |  | 7 days | 2024-03-30 | 2024-03-31 | 2024-04-06 | 2024-04-11 | Completed | Filed in baseline wave | 700129 | Publishing QC | Taylor Chen | R. Gupta | XLSX | NonClinical_SEND_Datasets_WOE001mk0001_0129.xlsx | Sample entry for dashboard validation | Central | 123
[5 empty] | 4.2.3.4.1 |  | Study report [WOE001CAPRATE] and related information | 122 |  |  | 20 days | 2024-04-03 | 2024-04-02 | 2024-04-23 | 2024-04-30 | Completed | Released to archive | 700130 |  | Jordan Patel | R. Gupta | PDF | Study_report_WOE001CAPRATE_and_related_information_0130.pdf | Sample entry for dashboard validation | Central | 124
[5 empty] | 4.2.3.4.1 |  | NonClinical SEND Datasets WOE001CAPRATE | 123 |  |  | 23 days | 2024-03-30 | 2024-03-31 | 2024-04-22 | 2024-04-22 | Completed |  | 700131 | Archive release | Casey Rivera | N. Ortiz | XLSX | NonClinical_SEND_Datasets_WOE001CAPRATE_0131.xlsx | Timing estimate is illustrative | Central | 125
[5 empty] | 4.2.3.4.2 |  | 4.2.3.4.2 Short or medium term studies | 124 |  |  | 16 days | 2024-03-30 | 2024-04-03 | 2024-04-15 | 2024-04-20 | Completed | Released to archive | 700132 | Archive release | Sam Brooks | M. Sullivan | DOCX | Short_or_medium_term_studies_0132.docx | Timing estimate is illustrative | Central | 126
[5 empty] | 4.2.3.4.2 |  | Study report [tt249005fin] and related information | 125 |  |  | 7 days | 2024-04-02 | 2024-04-07 | 2024-04-09 | 2024-04-05 | Completed | Filed in baseline wave | 700133 | Publishing QC | Morgan Lee | R. Gupta | PDF | Study_report_tt249005fin_and_related_information_0133.pdf | Sample entry for dashboard validation | Central | 127
[5 empty] | 4.2.3.4.2 |  | NonClinical Datasets tt249005 | 126 |  |  | 14 days | 2024-03-29 | 2024-03-26 | 2024-04-12 | 2024-04-15 | Completed | Filed in baseline wave | 700134 | Archive release | Casey Rivera | R. Gupta | CSV | NonClinical_Datasets_tt249005_0134.csv | Placeholder timeline for reporting test | Central | 128
[5 empty] | 4.2.3.5 |  | 4.2.3.5 Reproductive and developmental toxicity | 127 |  |  | 29 days | 2024-04-05 | 2024-04-07 | 2024-05-04 | 2024-05-01 | Completed | Filed in baseline wave | 700135 | Publishing QC | Morgan Lee | L. Bennett | PDF | Reproductive_and_developmental_toxicity_0135.pdf | Sample entry for dashboard validation | Central | 129
[5 empty] | 4.2.3.5.1 |  | 4.2.3.5.1 Fertility and early embryonic development | 128 |  |  | 13 days | 2024-04-01 | 2024-04-03 | 2024-04-14 |  | In Progress | Publishing build in progress | 700136 | Authoring | Alex Kim | N. Ortiz | DOCX | Fertility_and_early_embryonic_development_0136.docx | Sample entry for dashboard validation | Central | 130
[5 empty] | 4.2.3.5.1 |  | Study report [tt217040fin] and related information | 129 |  |  | 30 days | 2024-04-02 |  | 2024-05-02 |  | Not Started | Pending authoring start | 700137 |  | Casey Rivera | A. Shah | PDF | Study_report_tt217040fin_and_related_information_0137.pdf | Sample entry for dashboard validation | Central | 131
[5 empty] | 4.2.3.5.1 |  | Study report [tt217050fin] and related information | 130 |  |  | 28 days | 2024-04-06 | 2024-04-09 | 2024-05-04 |  | In Progress | Awaiting final source document | 700138 | Authoring | Sam Brooks | M. Sullivan | PDF | Study_report_tt217050fin_and_related_information_0138.pdf | Placeholder timeline for reporting test | Central | 132
[5 empty] | 4.2.3.5.1 |  | Study report [tt217070fin] and related information | 131 |  |  | 27 days | 2024-04-08 | 2024-04-10 | 2024-05-05 | 2024-05-01 | Completed | Filed in baseline wave | 700139 | Publishing QC | Jordan Patel | L. Bennett | DOCX | Study_report_tt217070fin_and_related_information_0139.docx | Dummy data added for planning demo | Central | 133
[5 empty] | 4.2.3.5.1 |  | Study report [tt217090fin] and related information | 132 |  |  | 32 days | 2024-04-03 | 2024-04-01 | 2024-05-05 | 2024-05-07 | Completed | Filed in baseline wave | 700140 | Publishing QC | Alex Kim | M. Sullivan | DOCX | Study_report_tt217090fin_and_related_information_0140.docx | Timing estimate is illustrative | Central | 134
[5 empty] | 4.2.3.5.2 |  | 4.2.3.5.2 Embryofetal development | 133 |  |  | 31 days | 2024-04-07 | 2024-04-06 | 2024-05-08 | 2024-05-11 | Completed | Completed as planned | 700141 |  | Morgan Lee | A. Shah | PDF | Embryofetal_development_0141.pdf | Placeholder timeline for reporting test | Central | 135
[5 empty] | 4.2.3.5.2 |  | Study report [tt217004fin] and related information | 134 |  |  | 29 days | 2024-04-04 | 2024-04-02 | 2024-05-03 | 2024-05-01 | Completed | Released to archive | 700142 | Submission build | Morgan Lee | M. Sullivan | DOCX | Study_report_tt217004fin_and_related_information_0142.docx | Sample entry for dashboard validation | Central | 136
[5 empty] | 4.2.3.5.2 |  | Study report [tt217014fin] and related information | 135 |  |  | 7 days | 2024-04-06 | 2024-04-08 | 2024-04-13 | 2024-04-20 | Completed | Filed in baseline wave | 700143 | Archive release | Alex Kim | L. Bennett | DOCX | Study_report_tt217014fin_and_related_information_0143.docx | Placeholder timeline for reporting test | Central | 137
[5 empty] | 4.2.3.5.2 |  | Study report [tt217020fin] and related information | 136 |  |  | 29 days | 2024-04-12 | 2024-04-11 | 2024-05-11 | 2024-05-15 | Completed | QC completed | 700144 | Archive release | Sam Brooks | L. Bennett | DOCX | Study_report_tt217020fin_and_related_information_0144.docx | Timing estimate is illustrative | Central | 138
[5 empty] | 4.2.3.5.2 |  | Study report [tt217024fin] and related information | 137 |  |  | 23 days | 2024-04-05 | 2024-04-06 | 2024-04-28 | 2024-04-28 | Completed |  | 700145 | Archive release | Casey Rivera | A. Shah | DOCX | Study_report_tt217024fin_and_related_information_0145.docx | Timing estimate is illustrative | Central | 139
[5 empty] | 4.2.3.5.2 |  | Study report [tt217030fin] and related information | 138 |  |  | 26 days | 2024-04-05 | 2024-04-06 | 2024-05-01 |  | In Progress | Metadata check in progress | 700146 | Authoring | Sam Brooks | M. Sullivan | DOCX | Study_report_tt217030fin_and_related_information_0146.docx | Timing estimate is illustrative | Central | 140
[5 empty] | 4.2.3.5.2 |  | Study report [tt217034fin] and related information | 139 |  |  | 28 days | 2024-04-13 | 2024-04-18 | 2024-05-11 | 2024-05-09 | Completed |  | 700147 | Archive release | Morgan Lee | L. Bennett | DOCX | Study_report_tt217034fin_and_related_information_0147.docx | Dummy data added for planning demo | Central | 141
[5 empty] | 4.2.3.5.2 |  | Study report [tt217060fin] and related information | 140 |  |  | 23 days | 2024-04-07 | 2024-04-04 | 2024-04-30 | 2024-04-28 | Completed | Filed in baseline wave | 700148 | Publishing QC | Jordan Patel | A. Shah | DOCX | Study_report_tt217060fin_and_related_information_0148.docx | Timing estimate is illustrative | Central | 142
[5 empty] | 4.2.3.5.2 |  | Study report [tt217080fin] and related information | 141 |  |  | 8 days | 2024-04-07 | 2024-04-10 | 2024-04-15 | 2024-04-21 | Completed | Released to archive | 700149 |  | Taylor Chen | M. Sullivan | DOCX | Study_report_tt217080fin_and_related_information_0149.docx | Dummy data added for planning demo | Central | 143
[5 empty] | 4.2.3.5.3 |  | 4.2.3.5.3 Prenatal and postnatal development, including maternal function | 142 |  |  | 14 days | 2024-04-12 | 2024-04-10 | 2024-04-26 | 2024-04-22 | Completed | Filed in baseline wave | 700150 |  | Jamie Carter | A. Shah | DOCX | Prenatal_and_postnatal_development_including_maternal_functi_0150.docx | Dummy data added for planning demo | Central | 144
[5 empty] | 4.2.3.5.3 |  | Study report [tt249016fin] and related information | 143 |  |  | 24 days | 2024-04-13 | 2024-04-16 | 2024-05-07 | 2024-05-08 | Completed | Completed as planned | 700151 |  | Morgan Lee | M. Sullivan | PDF | Study_report_tt249016fin_and_related_information_0151.pdf | Dummy data added for planning demo | Central | 145
[5 empty] | 4.2.3.5.3 |  | Study report [WOE001CAPRATEPPND] and related information | 144 |  |  | 9 days | 2024-04-12 | 2024-04-18 | 2024-04-21 |  | In Progress | Draft in QC review | 700152 | Authoring | Sam Brooks | N. Ortiz | DOCX | Study_report_WOE001CAPRATEPPND_and_related_information_0152.docx | Timing estimate is illustrative | Central | 146
[5 empty] | 4.2.3.6 |  | 4.2.3.6 Local tolerance | 145 |  |  | 23 days | 2024-04-12 | 2024-04-11 | 2024-05-05 | 2024-05-09 | Completed |  | 700153 |  | Sam Brooks | A. Shah | XLSX | Local_tolerance_0153.xlsx | Placeholder timeline for reporting test | Central | 147
[5 empty] | 4.2.3.6 |  | Study report [tt247832] and related information | 146 |  |  | 29 days | 2024-04-16 | 2024-04-14 | 2024-05-15 | 2024-05-13 | Completed | Filed in baseline wave | 700154 |  | Casey Rivera | M. Sullivan | DOCX | Study_report_tt247832_and_related_information_0154.docx | Timing estimate is illustrative | Central | 148
[5 empty] | 4.2.3.6 |  | Study report [tt247833] and related information | 147 |  |  | 26 days | 2024-04-18 | 2024-04-20 | 2024-05-14 | 2024-05-15 | Completed |  | 700155 | Archive release | Jamie Carter | R. Gupta | DOCX | Study_report_tt247833_and_related_information_0155.docx | Sample entry for dashboard validation | Central | 149
[5 empty] | 4.2.3.7 |  | 4.2.3.7 Other toxicity studies | 148 |  |  | 26 days | 2024-04-16 | 2024-04-21 | 2024-05-12 | 2024-05-11 | Completed | Released to archive | 700156 |  | Sam Brooks | R. Gupta | DOCX | Other_toxicity_studies_0156.docx | Sample entry for dashboard validation | Central | 150
[5 empty] | 4.2.3.7.2 |  | 4.2.3.7.2 Immunotoxicity | 149 |  |  | 19 days | 2024-04-18 | 2024-04-15 | 2024-05-07 | 2024-05-07 | Completed |  | 700157 | Publishing QC | Taylor Chen | N. Ortiz | DOCX | Immunotoxicity_0157.docx | Dummy data added for planning demo | Central | 151
[5 empty] | 4.2.3.7.2 |  | Study report [TT227826FIN] and related information | 150 |  |  | 14 days | 2024-04-16 | 2024-04-18 | 2024-04-30 | 2024-04-26 | Completed | QC completed | 700158 |  | Taylor Chen | M. Sullivan | PDF | Study_report_TT227826FIN_and_related_information_0158.pdf | Dummy data added for planning demo | Central | 152
[5 empty] | 4.2.3.7.6 |  | 4.2.3.7.6 Impurities | 151 |  |  | 21 days | 2024-04-12 | 2024-04-11 | 2024-05-03 | 2024-05-03 | Completed | QC completed | 700159 |  | Jordan Patel | N. Ortiz | DOCX | Impurities_0159.docx | Placeholder timeline for reporting test | Central | 153
[5 empty] | 4.2.3.7.6 |  | Study report [tt191030fin] and related information | 152 |  |  | 25 days | 2024-04-14 | 2024-04-14 | 2024-05-09 | 2024-05-16 | Completed | Completed as planned | 700160 | Archive release | Jamie Carter | L. Bennett | PDF | Study_report_tt191030fin_and_related_information_0160.pdf | Sample entry for dashboard validation | Central | 154
[5 empty] | 4.2.3.7.6 |  | Study report [tt251006fin] and related information | 153 |  |  | 26 days | 2024-04-14 | 2024-04-11 | 2024-05-10 | 2024-05-17 | Completed |  | 700161 |  | Alex Kim | A. Shah | DOCX | Study_report_tt251006fin_and_related_information_0161.docx | Placeholder timeline for reporting test | Central | 155
[5 empty] | 4.2.3.7.6 |  | Study report [pk002l006722648] and related information | 154 |  |  | 20 days | 2024-04-20 | 2024-04-19 | 2024-05-10 |  | In Progress | Awaiting final source document | 700162 |  | Alex Kim | L. Bennett | PDF | Study_report_pk002l006722648_and_related_information_0162.pdf | Placeholder timeline for reporting test | Central | 156
[5 empty] | 4.2.3.7.6 |  | Study report [tt249052fin] and related information | 155 |  |  | 8 days | 2024-04-23 | 2024-04-22 | 2024-05-01 | 2024-05-02 | Completed |  | 700163 | Submission build | Jordan Patel | A. Shah | DOCX | Study_report_tt249052fin_and_related_information_0163.docx | Sample entry for dashboard validation | Central | 157
[5 empty] | 4.2.3.7.6 |  | Study report [tt258005fin] and related information | 156 |  |  | 9 days | 2024-04-23 | 2024-04-24 | 2024-05-02 | 2024-05-04 | Completed | Filed in baseline wave | 700164 | Submission build | Morgan Lee | A. Shah | DOCX | Study_report_tt258005fin_and_related_information_0164.docx | Dummy data added for planning demo | Central | 158
[5 empty] | 4.2.3.7.6 |  | Study report [tt258025] and related information | 157 |  |  | 19 days | 2024-04-24 | 2024-04-27 | 2024-05-13 | 2024-05-17 | Completed | Released to archive | 700165 | Submission build | Jamie Carter | N. Ortiz | DOCX | Study_report_tt258025_and_related_information_0165.docx | Timing estimate is illustrative | Central | 159
[5 empty] | 4.2.3.7.6 |  | Study report [TT248064FIN] and related information | 158 |  |  | 19 days | 2024-04-23 | 2024-04-23 | 2024-05-12 | 2024-05-16 | Completed |  | 700166 |  | Jordan Patel | N. Ortiz | PDF | Study_report_TT248064FIN_and_related_information_0166.pdf | Placeholder timeline for reporting test | Central | 160
[5 empty] | 4.2.3.7.6 |  | Study report [tt221032fin] and related information | 159 |  |  | 17 days | 2024-04-23 | 2024-04-21 | 2024-05-10 | 2024-05-07 | Completed | Released to archive | 700167 |  | Morgan Lee | R. Gupta | PDF | Study_report_tt221032fin_and_related_information_0167.pdf | Placeholder timeline for reporting test | Central | 161
[5 empty] | 4.2.3.7.6 |  | NonClinical Datasets tt221032 | 160 |  |  | 26 days | 2024-04-23 | 2024-04-24 | 2024-05-19 | 2024-05-17 | Completed | QC completed | 700168 |  | Jamie Carter | L. Bennett | ZIP | NonClinical_Datasets_tt221032_0168.zip | Timing estimate is illustrative | Central | 162
[5 empty] | 4.2.3.7.6 |  | Study report [TT248090FIN] and related information | 161 |  |  | 8 days | 2024-04-25 | 2024-04-26 | 2024-05-03 |  | In Progress | Awaiting final source document | 700169 | Publishing prep | Jordan Patel | A. Shah | PDF | Study_report_TT248090FIN_and_related_information_0169.pdf | Dummy data added for planning demo | Central | 163
[5 empty] | 4.2.3.7.6 |  | Study report [TT258026FIN] and related information | 162 |  |  | 26 days | 2024-04-22 | 2024-04-24 | 2024-05-18 |  | In Progress | Draft in QC review | 700170 | Publishing prep | Sam Brooks | A. Shah | DOCX | Study_report_TT258026FIN_and_related_information_0170.docx | Sample entry for dashboard validation | Central | 164
[5 empty] | 4.2.3.7.6 |  | Study report [TT258085FIN] and related information | 163 |  |  | 7 days | 2024-04-26 | 2024-05-01 | 2024-05-03 | 2024-05-02 | Completed | Filed in baseline wave | 700171 |  | Taylor Chen | R. Gupta | DOCX | Study_report_TT258085FIN_and_related_information_0171.docx | Timing estimate is illustrative | Central | 165
[5 empty] | 4.2.3.7.6 |  | Study report [TT259042FIN] and related information | 164 |  |  | 19 days | 2024-04-20 | 2024-04-25 | 2024-05-09 | 2024-05-05 | Completed | QC completed | 700172 | Submission build | Alex Kim | R. Gupta | PDF | Study_report_TT259042FIN_and_related_information_0172.pdf | Placeholder timeline for reporting test | Central | 166
[5 empty] | 4.2.3.7.6 |  | Study report [pk002l007006016] and related information | 165 |  |  | 21 days | 2024-04-20 | 2024-04-17 | 2024-05-11 | 2024-05-08 | Completed | Released to archive | 700173 | Archive release | Sam Brooks | R. Gupta | PDF | Study_report_pk002l007006016_and_related_information_0173.pdf | Dummy data added for planning demo | Central | 167
[5 empty] | 4.2.3.7.6 |  | Study report [TT258083FIN] and related information | 166 |  |  | 34 days | 2024-04-25 | 2024-04-29 | 2024-05-29 |  | In Progress | Awaiting final source document | 700174 | Regional alignment | Taylor Chen | A. Shah | DOCX | Study_report_TT258083FIN_and_related_information_0174.docx | Sample entry for dashboard validation | Central | 168
[5 empty] | 4.2.3.7.6 |  | Study report [TT258086FIN] and related information | 167 |  |  | 9 days | 2024-04-30 | 2024-05-05 | 2024-05-09 | 2024-05-12 | Completed |  | 700175 | Publishing QC | Alex Kim | N. Ortiz | DOCX | Study_report_TT258086FIN_and_related_information_0175.docx | Placeholder timeline for reporting test | Central | 169
[5 empty] | 4.2.3.7.6 |  | Study report [TT259036FIN] and related information | 168 |  |  | 19 days | 2024-04-29 | 2024-04-26 | 2024-05-18 | 2024-05-19 | Completed | QC completed | 700176 | Archive release | Sam Brooks | R. Gupta | PDF | Study_report_TT259036FIN_and_related_information_0176.pdf | Placeholder timeline for reporting test | Central | 170
[5 empty] | 4.2.3.7.6 |  | Study report [pk002l007006333] and related information | 169 |  |  | 27 days | 2024-04-23 | 2024-04-26 | 2024-05-20 | 2024-05-16 | Completed |  | 700177 | Archive release | Jordan Patel | N. Ortiz | DOCX | Study_report_pk002l007006333_and_related_information_0177.docx | Sample entry for dashboard validation | Central | 171
[5 empty] | 4.2.3.7.6 |  | Study report [TT258084FIN] and related information | 170 |  |  | 9 days | 2024-04-25 | 2024-04-30 | 2024-05-04 | 2024-05-10 | Completed |  | 700178 | Submission build | Casey Rivera | N. Ortiz | PDF | Study_report_TT258084FIN_and_related_information_0178.pdf | Sample entry for dashboard validation | Central | 172
[5 empty] | 4.2.3.7.7 |  | 4.2.3.7.7 Other | 171 |  |  | 26 days | 2024-04-28 | 2024-05-03 | 2024-05-24 | 2024-05-22 | Completed | Filed in baseline wave | 700179 | Submission build | Taylor Chen | M. Sullivan | XLSX | Other_0179.xlsx | Timing estimate is illustrative | Central | 173
[5 empty] | 4.2.3.7.7 |  | Study report [tt176032fin] and related information | 172 |  |  | 16 days | 2024-04-27 | 2024-05-02 | 2024-05-13 | 2024-05-11 | Completed | Released to archive | 700180 | Submission build | Sam Brooks | M. Sullivan | PDF | Study_report_tt176032fin_and_related_information_0180.pdf | Placeholder timeline for reporting test | Central | 174
[5 empty] | 4.2.3.7.7 |  | Study report [tt181401fin] and related information | 173 |  |  | 24 days | 2024-04-26 | 2024-04-24 | 2024-05-20 | 2024-05-18 | Completed | QC completed | 700181 | Submission build | Sam Brooks | A. Shah | DOCX | Study_report_tt181401fin_and_related_information_0181.docx | Sample entry for dashboard validation | Central | 175
[5 empty] | 4.2.3.7.7 |  | Study report [tt184604fin] and related information | 174 |  |  | 16 days | 2024-05-02 | 2024-05-03 | 2024-05-18 | 2024-05-16 | Completed | Filed in baseline wave | 700182 | Publishing QC | Jordan Patel | N. Ortiz | PDF | Study_report_tt184604fin_and_related_information_0182.pdf | Placeholder timeline for reporting test | Central | 176
[5 empty] | 4.2.3.7.7 |  | Study report [tt187801fin] and related information | 175 |  |  | 26 days | 2024-04-29 | 2024-04-26 | 2024-05-25 | 2024-05-26 | Completed | Completed as planned | 700183 |  | Jordan Patel | M. Sullivan | DOCX | Study_report_tt187801fin_and_related_information_0183.docx | Placeholder timeline for reporting test | Central | 177
[5 empty] | 4.2.3.7.7 |  | Study report [tt191009fin] and related information | 176 |  |  | 34 days | 2024-04-29 | 2024-05-03 | 2024-06-02 | 2024-05-31 | Completed | Filed in baseline wave | 700184 | Submission build | Jordan Patel | A. Shah | DOCX | Study_report_tt191009fin_and_related_information_0184.docx | Dummy data added for planning demo | Central | 178
[5 empty] | 4.2.3.7.7 |  | Study report [tt197888fin] and related information | 177 |  |  | 20 days | 2024-05-01 | 2024-05-01 | 2024-05-21 | 2024-05-20 | Completed | Completed as planned | 700185 | Submission build | Casey Rivera | M. Sullivan | DOCX | Study_report_tt197888fin_and_related_information_0185.docx | Placeholder timeline for reporting test | Central | 179
[5 empty] | 4.2.3.7.7 |  | Study report [tt197033fin] and related information | 178 |  |  | 35 days | 2024-05-05 | 2024-05-08 | 2024-06-09 | 2024-06-05 | Completed |  | 700186 |  | Sam Brooks | R. Gupta | DOCX | Study_report_tt197033fin_and_related_information_0186.docx | Dummy data added for planning demo | Central | 180
[5 empty] | 4.2.3.7.7 |  | Study report [tt197043fin] and related information | 179 |  |  | 10 days | 2024-05-07 | 2024-05-04 | 2024-05-17 | 2024-05-16 | Completed |  | 700187 |  | Casey Rivera | A. Shah | DOCX | Study_report_tt197043fin_and_related_information_0187.docx | Dummy data added for planning demo | Central | 181
[5 empty] | 4.2.3.7.7 |  | Study report [tt207063fin] and related information | 180 |  |  | 16 days | 2024-05-02 | 2024-05-03 | 2024-05-18 | 2024-05-18 | Completed | Released to archive | 700188 | Submission build | Casey Rivera | R. Gupta | PDF | Study_report_tt207063fin_and_related_information_0188.pdf | Timing estimate is illustrative | Central | 182
[5 empty] | 4.2.3.7.7 |  | Study report [tt211024fin] and related information | 181 |  |  | 33 days | 2024-05-07 | 2024-05-05 | 2024-06-09 | 2024-06-16 | Completed |  | 700189 | Publishing QC | Jordan Patel | M. Sullivan | PDF | Study_report_tt211024fin_and_related_information_0189.pdf | Sample entry for dashboard validation | Central | 183
[5 empty] | 4.2.3.7.7 |  | Study report [tt211025fin] and related information | 182 |  |  | 17 days | 2024-05-06 | 2024-05-05 | 2024-05-23 | 2024-05-26 | Completed |  | 700190 | Submission build | Casey Rivera | A. Shah | DOCX | Study_report_tt211025fin_and_related_information_0190.docx | Placeholder timeline for reporting test | Central | 184
[5 empty] | 4.2.3.7.7 |  | Study report [tt212560fin] and related information | 183 |  |  | 29 days | 2024-05-03 | 2024-05-01 | 2024-06-01 | 2024-05-29 | Completed | Released to archive | 700191 | Archive release | Alex Kim | M. Sullivan | DOCX | Study_report_tt212560fin_and_related_information_0191.docx | Timing estimate is illustrative | Central | 185
[5 empty] | 4.2.3.7.7 |  | Study report [tt231004fin] and related information | 184 |  |  | 24 days | 2024-05-08 | 2024-05-07 | 2024-06-01 | 2024-06-02 | Completed |  | 700192 | Submission build | Jordan Patel | N. Ortiz | PDF | Study_report_tt231004fin_and_related_information_0192.pdf | Dummy data added for planning demo | Central | 186
[5 empty] | 4.2.3.7.7 |  | Study report [TT179828188FIN] and related information | 185 |  |  | 16 days | 2024-05-08 | 2024-05-12 | 2024-05-24 | 2024-05-24 | Completed | Filed in baseline wave | 700193 | Publishing QC | Jordan Patel | N. Ortiz | PDF | Study_report_TT179828188FIN_and_related_information_0193.pdf | Placeholder timeline for reporting test | Central | 187
[5 empty] | 4.3 |  | 4.3 Literature references | 186 |  |  | 103 days | 2024-05-03 | 2024-05-07 | 2024-08-14 | 2024-08-18 | Completed | Completed as planned | 700194 |  | Casey Rivera | N. Ortiz | PDF | Literature_references_0194.pdf | Sample entry for dashboard validation | Central | 188
[5 empty] | 5 |  | Module 5 Clinical Study Reports | 187 |  |  | 194 days | 2024-05-10 | 2024-05-07 | 2024-11-20 | 2024-11-19 | Completed |  | 700195 | Archive release | Taylor Chen | M. Sullivan | PDF | Module_5_Clinical_Study_Reports_0195.pdf | Dummy data added for planning demo | Central | 189
[5 empty] | 5.2 |  | 5.2 Tabular listing of all clinical studies | 188 |  |  | 63 days | 2024-05-06 | 2024-05-08 | 2024-07-08 | 2024-07-04 | Completed | Filed in baseline wave | 700196 | Publishing QC | Sam Brooks | M. Sullivan | ZIP | Tabular_listing_of_all_clinical_studies_0196.zip | Placeholder timeline for reporting test | Central | 190
[5 empty] | 5.2 |  | 5.2 Table of all clinical studies (US) | 189 |  |  | 56 days | 2024-05-09 | 2024-05-12 | 2024-07-04 | 2024-07-02 | Completed | Filed in baseline wave | 700197 | Archive release | Taylor Chen | M. Sullivan | ZIP | Table_of_all_clinical_studies_US_0197.zip | Timing estimate is illustrative | Central | 191
[5 empty] | 5.2 |  | 5.2 Summary Level Clinical Site Information (US) | 190 |  |  | 140 days | 2024-05-12 | 2024-05-09 | 2024-09-29 | 2024-09-26 | Completed | QC completed | 700198 | Archive release | Morgan Lee | L. Bennett | PDF | Summary_Level_Clinical_Site_Information_US_0198.pdf | Sample entry for dashboard validation | Central | 192
[5 empty] | 5.2 |  | 5.2 Study Administrative Structure Table (EU) | 191 |  |  | 53 days | 2024-05-14 | 2024-05-13 | 2024-07-06 | 2024-07-03 | Completed | QC completed | 700199 | Archive release | Taylor Chen | L. Bennett | ZIP | Study_Administrative_Structure_Table_EU_0199.zip | Timing estimate is illustrative | Central | 193
[5 empty] | 5.2 |  | 5.2 Subjects Recruited by Sites Table (EU) | 192 |  |  | 123 days | 2024-05-09 | 2024-05-14 | 2024-09-09 | 2024-09-06 | Completed | Released to archive | 700200 |  | Jamie Carter | R. Gupta | CSV | Subjects_Recruited_by_Sites_Table_EU_0200.csv | Placeholder timeline for reporting test | Central | 194
[5 empty] | 5.3 |  | 5.3 Clinical study reports and related information | 193 |  |  | 112 days | 2024-05-11 | 2024-05-13 | 2024-08-31 | 2024-08-29 | Completed |  | 700201 |  | Casey Rivera | M. Sullivan | DOCX | Clinical_study_reports_and_related_information_0201.docx | Sample entry for dashboard validation | Central | 195
[5 empty] | 5.3.1 |  | 5.3.1 Reports of biopharmaceutic studies | 194 |  |  | 59 days | 2024-05-09 | 2024-05-10 | 2024-07-07 | 2024-07-06 | Completed | Completed as planned | 700202 | Publishing QC | Alex Kim | L. Bennett | XLSX | Reports_of_biopharmaceutic_studies_0202.xlsx | Dummy data added for planning demo | Central | 196
[5 empty] | 5.3.1.1 |  | 5.3.1.1 p022mk0001 | 195 |  |  | 32 days | 2024-05-11 | 2024-05-14 | 2024-06-12 | 2024-06-14 | Completed | Completed as planned | 700203 | Archive release | Morgan Lee | M. Sullivan | XLSX | p022mk0001_0203.xlsx | Timing estimate is illustrative | Central | 197
[5 empty] | 5.3.1.1 |  | Study report [p022mk0001] and related information | 196 |  |  | 27 days | 2024-05-09 | 2024-05-10 | 2024-06-05 | 2024-06-05 | Completed | Completed as planned | 700204 | Archive release | Morgan Lee | M. Sullivan | DOCX | Study_report_p022mk0001_and_related_information_0204.docx | Dummy data added for planning demo | Central | 198
[5 empty] | 5.3.1.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p022mk0001 | 197 |  |  | 28 days | 2024-05-10 | 2024-05-13 | 2024-06-07 | 2024-06-14 | Completed |  | 700205 |  | Alex Kim | N. Ortiz | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_0205.xlsx | Placeholder timeline for reporting test | Central | 199
[5 empty] | 5.3.1.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 198 |  |  | 28 days | 2024-05-15 | 2024-05-19 | 2024-06-12 | 2024-06-08 | Completed | Filed in baseline wave | 700206 |  | Jordan Patel | L. Bennett | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_0206.zip | Placeholder timeline for reporting test | Central | 200
[5 empty] | 5.3.1.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 199 |  |  | 32 days | 2024-05-17 | 2024-05-15 | 2024-06-18 |  | In Progress | Pending cross-functional signoff | 700207 | Publishing prep | Taylor Chen | R. Gupta | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_0207.zip | Dummy data added for planning demo | Central | 201
[5 empty] | 5.3.1.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 200 |  |  | 25 days | 2024-05-14 | 2024-05-16 | 2024-06-08 | 2024-06-05 | Completed | Filed in baseline wave | 700208 | Archive release | Jamie Carter | A. Shah | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0208.docx | Sample entry for dashboard validation | Central | 202
[5 empty] | 5.3.1.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p022mk0001 | 201 |  |  | 33 days | 2024-05-19 | 2024-05-22 | 2024-06-21 | 2024-06-19 | Completed |  | 700209 | Publishing QC | Jamie Carter | R. Gupta | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p022mk0001_0209.zip | Placeholder timeline for reporting test | Central | 203
[5 empty] | 5.3.1.1 |  | Analysis datasets - ADAM format | 202 |  |  | 15 days | 2024-05-12 | 2024-05-16 | 2024-05-27 | 2024-05-26 | Completed | QC completed | 700210 |  | Jamie Carter | R. Gupta | XLSX | Analysis_datasets_ADAM_format_0210.xlsx | Placeholder timeline for reporting test | Central | 204
[5 empty] | 5.3.1.1 |  | Data definition for analysis datasets - ADAM format (define file) | 203 |  |  | 10 days | 2024-05-15 | 2024-05-12 | 2024-05-25 | 2024-05-24 | Completed | Completed as planned | 700211 |  | Taylor Chen | A. Shah | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0211.csv | Timing estimate is illustrative | Central | 205
[5 empty] | 5.3.1.1 |  | Analysis Data Reviewers Guide | 204 |  |  | 17 days | 2024-05-16 | 2024-05-22 | 2024-06-02 |  | In Progress | Metadata check in progress | 700212 | Publishing prep | Jordan Patel | A. Shah | ZIP | Analysis_Data_Reviewers_Guide_0212.zip | Timing estimate is illustrative | Central | 206
[5 empty] | 5.3.1.1 |  | Analysis programs | 205 |  |  | 30 days | 2024-05-17 | 2024-05-20 | 2024-06-16 | 2024-06-23 | Completed |  | 700213 | Publishing QC | Alex Kim | R. Gupta | ZIP | Analysis_programs_0213.zip | Dummy data added for planning demo | Central | 207
[5 empty] | 5.3.1.1 |  | 5.3.1.1 p033mk0001 | 206 |  |  | 21 days | 2024-05-19 | 2024-05-18 | 2024-06-09 |  | In Progress | Pending cross-functional signoff | 700214 | Publishing prep | Alex Kim | M. Sullivan | DOCX | p033mk0001_0214.docx | Timing estimate is illustrative | Central | 208
[5 empty] | 5.3.1.1 |  | Study report [p033mk0001] and related information | 207 |  |  | 13 days | 2024-05-20 | 2024-05-21 | 2024-06-02 | 2024-06-06 | Completed | QC completed | 700215 |  | Sam Brooks | A. Shah | DOCX | Study_report_p033mk0001_and_related_information_0215.docx | Timing estimate is illustrative | Central | 209
[5 empty] | 5.3.1.1 |  | Case Report Forms - CRF FOLDER p033mk0001 | 208 |  |  | 15 days | 2024-05-18 | 2024-05-23 | 2024-06-02 | 2024-06-06 | Completed | Completed as planned | 700216 | Submission build | Taylor Chen | R. Gupta | DOCX | Case_Report_Forms_CRF_FOLDER_p033mk0001_0216.docx | Placeholder timeline for reporting test | Central | 210
[5 empty] | 5.3.1.1 |  | Listing of Case Report Forms (CRFs TOC) | 209 |  |  | 29 days | 2024-05-18 | 2024-05-19 | 2024-06-16 |  | In Progress | Awaiting final source document | 700217 | Authoring | Morgan Lee | M. Sullivan | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_0217.csv | Sample entry for dashboard validation | Central | 211
[5 empty] | 5.3.1.1 |  | Case Report Forms - eCRFs (by site) for US | 210 |  |  | 11 days | 2024-05-17 | 2024-05-14 | 2024-05-28 | 2024-05-25 | Completed | Released to archive | 700218 | Publishing QC | Alex Kim | L. Bennett | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0218.docx | Timing estimate is illustrative | Central | 212
[5 empty] | 5.3.1.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p033mk0001 | 211 |  |  | 26 days | 2024-05-24 | 2024-05-26 | 2024-06-19 | 2024-06-18 | Completed |  | 700219 | Publishing QC | Jamie Carter | L. Bennett | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p03_0219.zip | Timing estimate is illustrative | Central | 213
[5 empty] | 5.3.1.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 212 |  |  | 33 days | 2024-05-19 | 2024-05-24 | 2024-06-21 |  | In Progress | Draft in QC review | 700220 | Regional alignment | Morgan Lee | L. Bennett | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_0220.csv | Timing estimate is illustrative | Central | 214
[5 empty] | 5.3.1.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 213 |  |  | 11 days | 2024-05-22 | 2024-05-24 | 2024-06-02 |  | In Progress | Metadata check in progress | 700221 | Regional alignment | Jordan Patel | R. Gupta | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_0221.csv | Sample entry for dashboard validation | Central | 215
[5 empty] | 5.3.1.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 214 |  |  | 7 days | 2024-05-26 | 2024-05-24 | 2024-06-02 | 2024-06-03 | Completed | Released to archive | 700222 |  | Jamie Carter | N. Ortiz | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0222.docx | Placeholder timeline for reporting test | Central | 216
[5 empty] | 5.3.1.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p033mk0001 | 215 |  |  | 23 days | 2024-05-22 | 2024-05-20 | 2024-06-14 | 2024-06-15 | Completed |  | 700223 | Publishing QC | Jamie Carter | R. Gupta | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p033mk0001_0223.zip | Sample entry for dashboard validation | Central | 217
[5 empty] | 5.3.1.1 |  | Analysis datasets - ADAM format | 216 |  |  | 25 days | 2024-05-26 | 2024-05-26 | 2024-06-20 | 2024-06-24 | Completed | Filed in baseline wave | 700224 |  | Casey Rivera | A. Shah | CSV | Analysis_datasets_ADAM_format_0224.csv | Timing estimate is illustrative | Central | 218
[5 empty] | 5.3.1.1 |  | Data definition for analysis datasets - ADAM format (define file) | 217 |  |  | 32 days | 2024-05-27 |  | 2024-06-28 |  | Not Started | Resource assignment not yet confirmed | 700225 |  | Jamie Carter | R. Gupta | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0225.zip | Timing estimate is illustrative | Central | 219
[5 empty] | 5.3.1.1 |  | Analysis Data Reviewers Guide | 218 |  |  | 28 days | 2024-05-23 | 2024-05-27 | 2024-06-20 | 2024-06-17 | Completed |  | 700226 |  | Casey Rivera | R. Gupta | ZIP | Analysis_Data_Reviewers_Guide_0226.zip | Dummy data added for planning demo | Central | 220
[5 empty] | 5.3.1.1 |  | Analysis programs | 219 |  |  | 12 days | 2024-05-29 | 2024-06-01 | 2024-06-10 | 2024-06-07 | Completed |  | 700227 | Publishing QC | Sam Brooks | M. Sullivan | TXT | Analysis_programs_0227.txt | Placeholder timeline for reporting test | Central | 221
[5 empty] | 5.3.1.1 |  | 5.3.1.1 p040mk0001 | 220 |  |  | 27 days | 2024-05-30 | 2024-05-28 | 2024-06-26 | 2024-06-25 | Completed | Filed in baseline wave | 700228 |  | Jamie Carter | A. Shah | PDF | p040mk0001_0228.pdf | Timing estimate is illustrative | Central | 222
[5 empty] | 5.3.1.1 |  | Study report [p040mk0001] and related information | 221 |  |  | 24 days | 2024-05-30 | 2024-06-03 | 2024-06-23 | 2024-06-22 | Completed | Filed in baseline wave | 700229 | Archive release | Morgan Lee | M. Sullivan | DOCX | Study_report_p040mk0001_and_related_information_0229.docx | Sample entry for dashboard validation | Central | 223
[5 empty] | 5.3.1.1 |  | Case Report Forms - CRF FOLDER | 222 |  |  | 9 days | 2024-05-29 | 2024-06-03 | 2024-06-07 | 2024-06-09 | Completed | Filed in baseline wave | 700230 | Archive release | Alex Kim | R. Gupta | PDF | Case_Report_Forms_CRF_FOLDER_0230.pdf | Dummy data added for planning demo | Central | 224
[5 empty] | 5.3.1.1 |  | Listing of Case Report Forms (CRFs TOC) | 223 |  |  | 33 days | 2024-06-01 |  | 2024-07-04 |  | Not Started | Planned for upcoming wave | 700231 |  | Jamie Carter | R. Gupta | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_0231.xlsx | Timing estimate is illustrative | Central | 225
[5 empty] | 5.3.1.1 |  | Case Report Forms - eCRFs (by site) Category 1 and 2 for US | 224 |  |  | 29 days | 2024-05-31 | 2024-06-02 | 2024-06-29 | 2024-07-06 | Completed | Released to archive | 700232 |  | Casey Rivera | L. Bennett | PDF | Case_Report_Forms_eCRFs_by_site_Category_1_and_2_for_US_0232.pdf | Timing estimate is illustrative | Central | 226
[5 empty] | 5.3.1.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER | 225 |  |  | 11 days | 2024-06-02 | 2024-06-05 | 2024-06-13 | 2024-06-14 | Completed | Released to archive | 700233 | Submission build | Morgan Lee | N. Ortiz | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_0233.xlsx | Dummy data added for planning demo | Central | 227
[5 empty] | 5.3.1.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format SDTM or Legacy format( Choose the correct Data format with team) | 226 |  |  | 27 days | 2024-05-27 | 2024-05-31 | 2024-06-23 | 2024-06-29 | Completed | Released to archive | 700234 | Submission build | Alex Kim | N. Ortiz | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_0234.zip | Sample entry for dashboard validation | Central | 228
[5 empty] | 5.3.1.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format SDTM or Legacy format( Choose the correct Data format with team) (define file) | 227 |  |  | 35 days | 2024-06-03 | 2024-06-06 | 2024-07-08 | 2024-07-13 | Completed | Filed in baseline wave | 700235 |  | Taylor Chen | L. Bennett | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_0235.zip | Sample entry for dashboard validation | Central | 229
[5 empty] | 5.3.1.1 |  | Annotated Case Report Forms (CRFs) - SDTM format or Legacy format( Choose the correct Data format with team) | 228 |  |  | 18 days | 2024-06-02 | 2024-06-05 | 2024-06-20 | 2024-06-25 | Completed | Completed as planned | 700236 |  | Casey Rivera | N. Ortiz | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_or_Legacy_forma_0236.docx | Sample entry for dashboard validation | Central | 230
[5 empty] | 5.3.1.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER | 229 |  |  | 25 days | 2024-06-05 | 2024-06-02 | 2024-06-30 | 2024-07-05 | Completed | Released to archive | 700237 | Archive release | Alex Kim | M. Sullivan | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_0237.csv | Dummy data added for planning demo | Central | 231
[5 empty] | 5.3.1.1 |  | Analysis datasets - ADAM format | 230 |  |  | 30 days | 2024-05-30 | 2024-05-31 | 2024-06-29 | 2024-07-02 | Completed |  | 700238 | Publishing QC | Taylor Chen | M. Sullivan | XLSX | Analysis_datasets_ADAM_format_0238.xlsx | Timing estimate is illustrative | Central | 232
[5 empty] | 5.3.1.1 |  | Data definition for analysis datasets - ADAM format (define file) | 231 |  |  | 27 days | 2024-06-05 | 2024-06-03 | 2024-07-02 | 2024-07-08 | Completed |  | 700239 |  | Morgan Lee | M. Sullivan | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0239.xlsx | Placeholder timeline for reporting test | Central | 233
[5 empty] | 5.3.1.1 |  | Analysis Data Reviewers Guide | 232 |  |  | 31 days | 2024-06-07 | 2024-06-11 | 2024-07-08 | 2024-07-12 | Completed | Released to archive | 700240 |  | Sam Brooks | R. Gupta | CSV | Analysis_Data_Reviewers_Guide_0240.csv | Placeholder timeline for reporting test | Central | 234
[5 empty] | 5.3.1.1 |  | Analysis programs | 233 |  |  | 16 days | 2024-06-03 | 2024-06-04 | 2024-06-19 | 2024-06-26 | Completed |  | 700241 | Archive release | Alex Kim | L. Bennett | ZIP | Analysis_programs_0241.zip | Dummy data added for planning demo | Central | 235
[5 empty] | 5.3.1.2 |  | 5.3.1.2 p004mk0001 | 234 |  |  | 32 days | 2024-06-04 | 2024-06-01 | 2024-07-06 | 2024-07-06 | Completed | Released to archive | 700242 | Publishing QC | Jordan Patel | M. Sullivan | PDF | p004mk0001_0242.pdf | Placeholder timeline for reporting test | Central | 236
[5 empty] | 5.3.1.2 |  | Study report [p004mk0001] and related information | 235 |  |  | 11 days | 2024-06-04 | 2024-06-05 | 2024-06-15 | 2024-06-15 | Completed | Completed as planned | 700243 | Publishing QC | Taylor Chen | N. Ortiz | PDF | Study_report_p004mk0001_and_related_information_0243.pdf | Sample entry for dashboard validation | Central | 237
[5 empty] | 5.3.1.2 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p004mk0001 | 236 |  |  | 32 days | 2024-06-06 | 2024-06-06 | 2024-07-08 | 2024-07-11 | Completed | Filed in baseline wave | 700244 |  | Jamie Carter | A. Shah | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_0244.csv | Dummy data added for planning demo | Central | 238
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 237 |  |  | 26 days | 2024-06-04 | 2024-06-04 | 2024-06-30 |  | In Progress | Publishing build in progress | 700245 | Regional alignment | Jamie Carter | L. Bennett | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_0245.xlsx | Sample entry for dashboard validation | Central | 239
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 238 |  |  | 13 days | 2024-06-04 | 2024-06-06 | 2024-06-17 | 2024-06-13 | Completed | QC completed | 700246 | Publishing QC | Alex Kim | N. Ortiz | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_0246.csv | Sample entry for dashboard validation | Central | 240
[5 empty] | 5.3.1.2 |  | Annotated Case Report Forms (CRFs) - SDTM format | 239 |  |  | 16 days | 2024-06-10 | 2024-06-15 | 2024-06-26 | 2024-06-25 | Completed | Released to archive | 700247 |  | Casey Rivera | R. Gupta | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0247.pdf | Sample entry for dashboard validation | Central | 241
[5 empty] | 5.3.1.2 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p004mk0001 | 240 |  |  | 16 days | 2024-06-03 | 2024-06-08 | 2024-06-19 |  | In Progress | Publishing build in progress | 700248 | Publishing prep | Taylor Chen | A. Shah | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p004mk0001_0248.xlsx | Placeholder timeline for reporting test | Central | 242
[5 empty] | 5.3.1.2 |  | Analysis datasets - ADAM format | 241 |  |  | 26 days | 2024-06-10 | 2024-06-12 | 2024-07-06 |  | In Progress | Metadata check in progress | 700249 | Publishing prep | Morgan Lee | A. Shah | CSV | Analysis_datasets_ADAM_format_0249.csv | Sample entry for dashboard validation | Central | 243
[5 empty] | 5.3.1.2 |  | Data definition for analysis datasets - ADAM format (define file) | 242 |  |  | 31 days | 2024-06-11 | 2024-06-11 | 2024-07-12 | 2024-07-19 | Completed |  | 700250 | Submission build | Taylor Chen | R. Gupta | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0250.zip | Timing estimate is illustrative | Central | 244
[5 empty] | 5.3.1.2 |  | Analysis Data Reviewers Guide | 243 |  |  | 24 days | 2024-06-10 | 2024-06-07 | 2024-07-04 | 2024-07-01 | Completed | Completed as planned | 700251 |  | Alex Kim | M. Sullivan | XLSX | Analysis_Data_Reviewers_Guide_0251.xlsx | Sample entry for dashboard validation | Central | 245
[5 empty] | 5.3.1.2 |  | Analysis programs | 244 |  |  | 14 days | 2024-06-11 | 2024-06-12 | 2024-06-25 | 2024-06-24 | Completed | Completed as planned | 700252 | Publishing QC | Taylor Chen | A. Shah | ZIP | Analysis_programs_0252.zip | Timing estimate is illustrative | Central | 246
[5 empty] | 5.3.1.2 |  | 5.3.1.2 p005mk0001 | 245 |  |  | 29 days | 2024-06-07 | 2024-06-06 | 2024-07-06 |  | In Progress | Pending cross-functional signoff | 700253 | QC review | Casey Rivera | M. Sullivan | PDF | p005mk0001_0253.pdf | Dummy data added for planning demo | Central | 247
[5 empty] | 5.3.1.2 |  | Study report [p005mk0001] and related information | 246 |  |  | 15 days | 2024-06-09 | 2024-06-07 | 2024-06-24 | 2024-06-30 | Completed | Released to archive | 700254 | Archive release | Jamie Carter | L. Bennett | DOCX | Study_report_p005mk0001_and_related_information_0254.docx | Placeholder timeline for reporting test | Central | 248
[5 empty] | 5.3.1.2 |  | Case Report Forms - CRF FOLDER p005mk0001 | 247 |  |  | 31 days | 2024-06-09 | 2024-06-06 | 2024-07-10 | 2024-07-12 | Completed | Released to archive | 700255 | Archive release | Alex Kim | R. Gupta | DOCX | Case_Report_Forms_CRF_FOLDER_p005mk0001_0255.docx | Timing estimate is illustrative | Central | 249
[5 empty] | 5.3.1.2 |  | Listing of Case Report Forms (CRFs TOC) | 248 |  |  | 9 days | 2024-06-15 | 2024-06-15 | 2024-06-24 | 2024-06-29 | Completed | Released to archive | 700256 | Submission build | Sam Brooks | L. Bennett | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_0256.xlsx | Timing estimate is illustrative | Central | 250
[5 empty] | 5.3.1.2 |  | Case Report Forms - eCRFs (by site) for US | 249 |  |  | 31 days | 2024-06-17 | 2024-06-15 | 2024-07-18 | 2024-07-21 | Completed | QC completed | 700257 | Publishing QC | Alex Kim | A. Shah | PDF | Case_Report_Forms_eCRFs_by_site_for_US_0257.pdf | Placeholder timeline for reporting test | Central | 251
[5 empty] | 5.3.1.2 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p005mk0001 | 250 |  |  | 7 days | 2024-06-16 | 2024-06-16 | 2024-06-23 |  | In Progress | Regional review underway | 700258 | Authoring | Alex Kim | L. Bennett | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_0258.csv | Timing estimate is illustrative | Central | 252
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 251 |  |  | 35 days | 2024-06-15 | 2024-06-12 | 2024-07-20 | 2024-07-24 | Completed | Released to archive | 700259 |  | Casey Rivera | L. Bennett | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_0259.zip | Dummy data added for planning demo | Central | 253
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 252 |  |  | 14 days | 2024-06-18 | 2024-06-22 | 2024-07-02 | 2024-06-29 | Completed |  | 700260 |  | Morgan Lee | R. Gupta | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_0260.zip | Placeholder timeline for reporting test | Central | 254
[5 empty] | 5.3.1.2 |  | Annotated Case Report Forms (CRFs) - SDTM format | 253 |  |  | 8 days | 2024-06-17 | 2024-06-15 | 2024-06-25 | 2024-06-26 | Completed |  | 700261 | Archive release | Alex Kim | L. Bennett | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0261.docx | Timing estimate is illustrative | Central | 255
[5 empty] | 5.3.1.2 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p005mk0001 | 254 |  |  | 24 days | 2024-06-13 | 2024-06-16 | 2024-07-07 | 2024-07-13 | Completed | Filed in baseline wave | 700262 | Archive release | Sam Brooks | L. Bennett | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p005mk0001_0262.xlsx | Placeholder timeline for reporting test | Central | 256
[5 empty] | 5.3.1.2 |  | Analysis datasets - ADAM format | 255 |  |  | 9 days | 2024-06-19 | 2024-06-24 | 2024-06-28 |  | In Progress | Regional review underway | 700263 | QC review | Jordan Patel | A. Shah | XLSX | Analysis_datasets_ADAM_format_0263.xlsx | Dummy data added for planning demo | Central | 257
[5 empty] | 5.3.1.2 |  | Data definition for analysis datasets - ADAM format (define file) | 256 |  |  | 22 days | 2024-06-16 | 2024-06-21 | 2024-07-08 | 2024-07-14 | Completed | QC completed | 700264 |  | Taylor Chen | L. Bennett | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0264.xlsx | Dummy data added for planning demo | Central | 258
[5 empty] | 5.3.1.2 |  | Analysis Data Reviewers Guide | 257 |  |  | 8 days | 2024-06-18 | 2024-06-15 | 2024-06-26 | 2024-06-28 | Completed | Completed as planned | 700265 | Submission build | Jamie Carter | M. Sullivan | CSV | Analysis_Data_Reviewers_Guide_0265.csv | Timing estimate is illustrative | Central | 259
[5 empty] | 5.3.1.2 |  | Analysis programs | 258 |  |  | 9 days | 2024-06-17 | 2024-06-16 | 2024-06-26 | 2024-06-29 | Completed | Completed as planned | 700266 |  | Taylor Chen | A. Shah | ZIP | Analysis_programs_0266.zip | Timing estimate is illustrative | Central | 260
[5 empty] | 5.3.1.2 |  | 5.3.1.2 p009mk0001 | 259 |  |  | 12 days | 2024-06-14 | 2024-06-15 | 2024-06-26 | 2024-06-23 | Completed | Released to archive | 700267 |  | Jordan Patel | M. Sullivan | PDF | p009mk0001_0267.pdf | Dummy data added for planning demo | Central | 261
[5 empty] | 5.3.1.2 |  | Study report [p009mk0001] and related information | 260 |  |  | 22 days | 2024-06-16 | 2024-06-16 | 2024-07-08 | 2024-07-05 | Completed | Filed in baseline wave | 700268 |  | Morgan Lee | L. Bennett | DOCX | Study_report_p009mk0001_and_related_information_0268.docx | Dummy data added for planning demo | Central | 262
[5 empty] | 5.3.1.2 |  | Case Report Forms - CRF FOLDER p009mk0001 | 261 |  |  | 11 days | 2024-06-24 | 2024-06-24 | 2024-07-05 | 2024-07-01 | Completed |  | 700269 | Submission build | Morgan Lee | A. Shah | PDF | Case_Report_Forms_CRF_FOLDER_p009mk0001_0269.pdf | Placeholder timeline for reporting test | Central | 263
[5 empty] | 5.3.1.2 |  | Listing of Case Report Forms (CRFs TOC) | 262 |  |  | 31 days | 2024-06-18 | 2024-06-20 | 2024-07-19 | 2024-07-23 | Completed | Filed in baseline wave | 700270 |  | Jordan Patel | M. Sullivan | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_0270.xlsx | Timing estimate is illustrative | Central | 264
[5 empty] | 5.3.1.2 |  | Case Report Forms - eCRFs (by site) for US | 263 |  |  | 32 days | 2024-06-18 | 2024-06-22 | 2024-07-20 |  | In Progress | Awaiting final source document | 700271 | Authoring | Casey Rivera | A. Shah | PDF | Case_Report_Forms_eCRFs_by_site_for_US_0271.pdf | Dummy data added for planning demo | Central | 265
[5 empty] | 5.3.1.2 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p009mk0001 | 264 |  |  | 9 days | 2024-06-19 | 2024-06-20 | 2024-06-28 | 2024-06-30 | Completed | Released to archive | 700272 | Submission build | Jordan Patel | N. Ortiz | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_0272.zip | Placeholder timeline for reporting test | Central | 266
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 265 |  |  | 21 days | 2024-06-26 | 2024-06-25 | 2024-07-17 | 2024-07-22 | Completed | Completed as planned | 700273 |  | Jordan Patel | L. Bennett | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_0273.zip | Dummy data added for planning demo | Central | 267
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 266 |  |  | 18 days | 2024-06-22 | 2024-06-27 | 2024-07-10 | 2024-07-09 | Completed | Filed in baseline wave | 700274 | Publishing QC | Taylor Chen | A. Shah | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_0274.zip | Placeholder timeline for reporting test | Central | 268
[5 empty] | 5.3.1.2 |  | Annotated Case Report Forms (CRFs) - SDTM format p009mk0001 | 267 |  |  | 23 days | 2024-06-27 | 2024-06-27 | 2024-07-20 | 2024-07-20 | Completed | Completed as planned | 700275 | Submission build | Alex Kim | N. Ortiz | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_p009mk0001_0275.docx | Sample entry for dashboard validation | Central | 269
[5 empty] | 5.3.1.2 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER | 268 |  |  | 12 days | 2024-06-22 | 2024-06-19 | 2024-07-04 | 2024-06-30 | Completed | QC completed | 700276 | Archive release | Jordan Patel | L. Bennett | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_0276.csv | Placeholder timeline for reporting test | Central | 270
[5 empty] | 5.3.1.2 |  | Analysis datasets - ADAM format | 269 |  |  | 8 days | 2024-06-27 | 2024-06-24 | 2024-07-05 | 2024-07-09 | Completed | Filed in baseline wave | 700277 | Submission build | Jamie Carter | A. Shah | CSV | Analysis_datasets_ADAM_format_0277.csv | Dummy data added for planning demo | Central | 271
[5 empty] | 5.3.1.2 |  | Data definition for analysis datasets - ADAM format (define file) | 270 |  |  | 35 days | 2024-06-22 | 2024-06-26 | 2024-07-27 | 2024-08-01 | Completed |  | 700278 | Archive release | Casey Rivera | N. Ortiz | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0278.zip | Placeholder timeline for reporting test | Central | 272
[5 empty] | 5.3.1.2 |  | Analysis Data Reviewers Guide | 271 |  |  | 31 days | 2024-06-24 | 2024-06-24 | 2024-07-25 | 2024-07-22 | Completed | Filed in baseline wave | 700279 |  | Jamie Carter | N. Ortiz | CSV | Analysis_Data_Reviewers_Guide_0279.csv | Timing estimate is illustrative | Central | 273
[5 empty] | 5.3.1.2 |  | Analysis programs | 272 |  |  | 22 days | 2024-06-23 | 2024-06-20 | 2024-07-15 | 2024-07-17 | Completed | Filed in baseline wave | 700280 | Submission build | Taylor Chen | L. Bennett | ZIP | Analysis_programs_0280.zip | Sample entry for dashboard validation | Central | 274
[5 empty] | 5.3.1.2 |  | 5.3.1.2 p025mk0001 | 273 |  |  | 11 days | 2024-06-28 | 2024-06-28 | 2024-07-09 | 2024-07-15 | Completed | QC completed | 700281 | Archive release | Jordan Patel | R. Gupta | PDF | p025mk0001_0281.pdf | Dummy data added for planning demo | Central | 275
[5 empty] | 5.3.1.2 |  | Study report [p025mk0001] and related information | 274 |  |  | 15 days | 2024-06-23 | 2024-06-27 | 2024-07-08 | 2024-07-11 | Completed | Released to archive | 700282 | Submission build | Jamie Carter | R. Gupta | PDF | Study_report_p025mk0001_and_related_information_0282.pdf | Placeholder timeline for reporting test | Central | 276
[5 empty] | 5.3.1.2 |  | Case Report Forms - CRF FOLDER p025mk0001 | 275 |  |  | 32 days | 2024-06-26 | 2024-06-25 | 2024-07-28 | 2024-08-02 | Completed |  | 700283 | Submission build | Alex Kim | L. Bennett | DOCX | Case_Report_Forms_CRF_FOLDER_p025mk0001_0283.docx | Timing estimate is illustrative | Central | 277
[5 empty] | 5.3.1.2 |  | Listing of Case Report Forms (CRFs TOC) | 276 |  |  | 33 days | 2024-07-01 | 2024-06-28 | 2024-08-03 | 2024-08-10 | Completed | Released to archive | 700284 | Submission build | Jordan Patel | R. Gupta | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_0284.csv | Timing estimate is illustrative | Central | 278
[5 empty] | 5.3.1.2 |  | Case Report Forms - eCRFs (by site) for US | 277 |  |  | 25 days | 2024-06-27 | 2024-07-01 | 2024-07-22 |  | In Progress | Draft in QC review | 700285 | Authoring | Casey Rivera | M. Sullivan | PDF | Case_Report_Forms_eCRFs_by_site_for_US_0285.pdf | Sample entry for dashboard validation | Central | 279
[5 empty] | 5.3.1.2 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p025mk0001 | 278 |  |  | 19 days | 2024-07-03 | 2024-07-01 | 2024-07-22 | 2024-07-25 | Completed | Released to archive | 700286 | Submission build | Alex Kim | M. Sullivan | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_0286.xlsx | Sample entry for dashboard validation | Central | 280
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 279 |  |  | 11 days | 2024-06-29 | 2024-06-29 | 2024-07-10 | 2024-07-16 | Completed | Completed as planned | 700287 | Publishing QC | Casey Rivera | R. Gupta | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_0287.xlsx | Sample entry for dashboard validation | Central | 281
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 280 |  |  | 21 days | 2024-06-27 | 2024-06-26 | 2024-07-18 | 2024-07-25 | Completed | Released to archive | 700288 | Submission build | Jamie Carter | R. Gupta | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_0288.zip | Sample entry for dashboard validation | Central | 282
[5 empty] | 5.3.1.2 |  | Annotated Case Report Forms (CRFs) - SDTM format | 281 |  |  | 34 days | 2024-06-27 | 2024-06-30 | 2024-07-31 | 2024-08-07 | Completed | QC completed | 700289 |  | Alex Kim | R. Gupta | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0289.docx | Placeholder timeline for reporting test | Central | 283
[5 empty] | 5.3.1.2 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p025mk0001 | 282 |  |  | 25 days | 2024-07-06 | 2024-07-04 | 2024-07-31 | 2024-08-05 | Completed | QC completed | 700290 | Publishing QC | Taylor Chen | R. Gupta | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p025mk0001_0290.xlsx | Dummy data added for planning demo | Central | 284
[5 empty] | 5.3.1.2 |  | Analysis datasets - ADAM format | 283 |  |  | 18 days | 2024-07-04 | 2024-07-01 | 2024-07-22 | 2024-07-23 | Completed | QC completed | 700291 | Submission build | Sam Brooks | M. Sullivan | ZIP | Analysis_datasets_ADAM_format_0291.zip | Dummy data added for planning demo | Central | 285
[5 empty] | 5.3.1.2 |  | Data definition for analysis datasets - ADAM format (define file) | 284 |  |  | 29 days | 2024-07-07 | 2024-07-06 | 2024-08-05 | 2024-08-06 | Completed | Filed in baseline wave | 700292 |  | Alex Kim | L. Bennett | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0292.zip | Timing estimate is illustrative | Central | 286
[5 empty] | 5.3.1.2 |  | Analysis Data Reviewers Guide | 285 |  |  | 17 days | 2024-07-03 | 2024-07-04 | 2024-07-20 | 2024-07-24 | Completed | Released to archive | 700293 | Archive release | Alex Kim | A. Shah | CSV | Analysis_Data_Reviewers_Guide_0293.csv | Placeholder timeline for reporting test | Central | 287
[5 empty] | 5.3.1.2 |  | Analysis programs | 286 |  |  | 22 days | 2024-07-07 | 2024-07-05 | 2024-07-29 | 2024-08-01 | Completed |  | 700294 |  | Morgan Lee | L. Bennett | TXT | Analysis_programs_0294.txt | Dummy data added for planning demo | Central | 288
[5 empty] | 5.3.1.2 |  | 5.3.1.2 p035mk0001 | 287 |  |  | 35 days | 2024-07-04 | 2024-07-03 | 2024-08-08 |  | In Progress | Draft in QC review | 700295 | Regional alignment | Jordan Patel | R. Gupta | PDF | p035mk0001_0295.pdf | Dummy data added for planning demo | Central | 289
[5 empty] | 5.3.1.2 |  | Study report [p035mk0001] and related information | 288 |  |  | 15 days | 2024-07-03 | 2024-07-02 | 2024-07-18 | 2024-07-21 | Completed | Filed in baseline wave | 700296 | Submission build | Taylor Chen | A. Shah | DOCX | Study_report_p035mk0001_and_related_information_0296.docx | Sample entry for dashboard validation | Central | 290
[5 empty] | 5.3.1.2 |  | Case Report Forms - CRF FOLDER p035mk0001 | 289 |  |  | 11 days | 2024-07-10 | 2024-07-13 | 2024-07-21 | 2024-07-24 | Completed | Completed as planned | 700297 | Archive release | Jordan Patel | A. Shah | PDF | Case_Report_Forms_CRF_FOLDER_p035mk0001_0297.pdf | Timing estimate is illustrative | Central | 291
[5 empty] | 5.3.1.2 |  | Listing of Case Report Forms (CRFs TOC) | 290 |  |  | 27 days | 2024-07-10 | 2024-07-12 | 2024-08-06 | 2024-08-12 | Completed | QC completed | 700298 |  | Taylor Chen | M. Sullivan | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_0298.zip | Sample entry for dashboard validation | Central | 292
[5 empty] | 5.3.1.2 |  | Case Report Forms - eCRFs (by site) for US | 291 |  |  | 16 days | 2024-07-10 | 2024-07-11 | 2024-07-26 | 2024-07-24 | Completed | QC completed | 700299 | Submission build | Casey Rivera | R. Gupta | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0299.docx | Dummy data added for planning demo | Central | 293
[5 empty] | 5.3.1.2 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p035mk0001 | 292 |  |  | 18 days | 2024-07-06 | 2024-07-05 | 2024-07-24 | 2024-07-29 | Completed | Filed in baseline wave | 700300 |  | Morgan Lee | N. Ortiz | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p03_0300.xlsx | Timing estimate is illustrative | Central | 294
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 293 |  |  | 14 days | 2024-07-06 | 2024-07-08 | 2024-07-20 | 2024-07-25 | Completed | Filed in baseline wave | 700301 |  | Morgan Lee | R. Gupta | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_0301.xlsx | Timing estimate is illustrative | Central | 295
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 294 |  |  | 29 days | 2024-07-13 | 2024-07-15 | 2024-08-11 | 2024-08-12 | Completed | Filed in baseline wave | 700302 | Archive release | Casey Rivera | M. Sullivan | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_0302.xlsx | Placeholder timeline for reporting test | Central | 296
[5 empty] | 5.3.1.2 |  | Annotated Case Report Forms (CRFs) - SDTM format | 295 |  |  | 7 days | 2024-07-06 | 2024-07-10 | 2024-07-13 | 2024-07-11 | Completed | Released to archive | 700303 | Archive release | Jordan Patel | A. Shah | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0303.docx | Placeholder timeline for reporting test | Central | 297
[5 empty] | 5.3.1.2 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p035mk0001 | 296 |  |  | 35 days | 2024-07-13 | 2024-07-12 | 2024-08-17 | 2024-08-22 | Completed | Released to archive | 700304 | Archive release | Sam Brooks | A. Shah | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p035mk0001_0304.zip | Sample entry for dashboard validation | Central | 298
[5 empty] | 5.3.1.2 |  | Analysis datasets - ADAM format | 297 |  |  | 11 days | 2024-07-07 | 2024-07-05 | 2024-07-18 | 2024-07-18 | Completed | Completed as planned | 700305 |  | Taylor Chen | N. Ortiz | CSV | Analysis_datasets_ADAM_format_0305.csv | Placeholder timeline for reporting test | Central | 299
[5 empty] | 5.3.1.2 |  | Data definition for analysis datasets - ADAM format (define file) | 298 |  |  | 17 days | 2024-07-08 | 2024-07-08 | 2024-07-25 | 2024-07-30 | Completed |  | 700306 | Submission build | Jamie Carter | R. Gupta | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0306.xlsx | Dummy data added for planning demo | Central | 300
[5 empty] | 5.3.1.2 |  | Analysis Data Reviewers Guide | 299 |  |  | 24 days | 2024-07-09 | 2024-07-08 | 2024-08-02 |  | In Progress | Pending cross-functional signoff | 700307 | Regional alignment | Jordan Patel | L. Bennett | CSV | Analysis_Data_Reviewers_Guide_0307.csv | Dummy data added for planning demo | Central | 301
[5 empty] | 5.3.1.2 |  | Analysis programs | 300 |  |  | 19 days | 2024-07-13 | 2024-07-16 | 2024-08-01 | 2024-08-02 | Completed | Released to archive | 700308 | Archive release | Alex Kim | R. Gupta | TXT | Analysis_programs_0308.txt | Placeholder timeline for reporting test | Central | 302
[5 empty] | 5.3.3 |  | 5.3.3 Reports of human pharmacokinetic (PK) studies | 301 |  |  | 48 days | 2024-07-13 | 2024-07-12 | 2024-08-30 |  | In Progress | Awaiting final source document | 700309 | Regional alignment | Sam Brooks | L. Bennett | DOCX | Reports_of_human_pharmacokinetic_PK_studies_0309.docx | Placeholder timeline for reporting test | Central | 303
[5 empty] | 5.3.3.1 |  | 5.3.3.1 p001mk0001 | 302 |  |  | 32 days | 2024-07-11 | 2024-07-14 | 2024-08-12 | 2024-08-19 | Completed | Released to archive | 700310 | Submission build | Jamie Carter | M. Sullivan | XLSX | p001mk0001_0310.xlsx | Dummy data added for planning demo | Central | 304
[5 empty] | 5.3.3.1 |  | Study report [p001mk0001] and related information | 303 |  |  | 13 days | 2024-07-12 | 2024-07-17 | 2024-07-25 | 2024-07-26 | Completed | Completed as planned | 700311 |  | Jamie Carter | L. Bennett | PDF | Study_report_p001mk0001_and_related_information_0311.pdf | Dummy data added for planning demo | Central | 305
[5 empty] | 5.3.3.1 |  | Case Report Forms - CRF FOLDER p001mk0001 | 304 |  |  | 27 days | 2024-07-17 | 2024-07-21 | 2024-08-13 |  | In Progress | Awaiting final source document | 700312 |  | Casey Rivera | M. Sullivan | PDF | Case_Report_Forms_CRF_FOLDER_p001mk0001_0312.pdf | Timing estimate is illustrative | Central | 306
[5 empty] | 5.3.3.1 |  | Listing of Case Report Forms (CRFs TOC) | 305 |  |  | 33 days | 2024-07-13 | 2024-07-18 | 2024-08-15 | 2024-08-18 | Completed | Completed as planned | 700313 | Archive release | Jamie Carter | M. Sullivan | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_0313.csv | Sample entry for dashboard validation | Central | 307
[5 empty] | 5.3.3.1 |  | Case Report Forms - eCRFs (by site) for US | 306 |  |  | 30 days | 2024-07-20 | 2024-07-17 | 2024-08-19 | 2024-08-15 | Completed | Filed in baseline wave | 700314 | Archive release | Morgan Lee | L. Bennett | PDF | Case_Report_Forms_eCRFs_by_site_for_US_0314.pdf | Placeholder timeline for reporting test | Central | 308
[5 empty] | 5.3.3.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p001mk0001 | 307 |  |  | 12 days | 2024-07-18 | 2024-07-18 | 2024-07-30 | 2024-07-26 | Completed | Completed as planned | 700315 | Archive release | Casey Rivera | A. Shah | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_0315.zip | Placeholder timeline for reporting test | Central | 309
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 308 |  |  | 25 days | 2024-07-20 | 2024-07-21 | 2024-08-14 | 2024-08-20 | Completed | Released to archive | 700316 | Publishing QC | Morgan Lee | M. Sullivan | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_0316.zip | Dummy data added for planning demo | Central | 310
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 309 |  |  | 12 days | 2024-07-18 | 2024-07-17 | 2024-07-30 | 2024-07-31 | Completed | Released to archive | 700317 | Submission build | Morgan Lee | N. Ortiz | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_0317.xlsx | Placeholder timeline for reporting test | Central | 311
[5 empty] | 5.3.3.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 310 |  |  | 20 days | 2024-07-19 | 2024-07-21 | 2024-08-08 | 2024-08-04 | Completed | QC completed | 700318 | Archive release | Taylor Chen | A. Shah | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0318.pdf | Timing estimate is illustrative | Central | 312
[5 empty] | 5.3.3.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p001mk0001 | 311 |  |  | 26 days | 2024-07-16 | 2024-07-21 | 2024-08-11 | 2024-08-12 | Completed | QC completed | 700319 | Archive release | Morgan Lee | R. Gupta | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p001mk0001_0319.xlsx | Placeholder timeline for reporting test | Central | 313
[5 empty] | 5.3.3.1 |  | Analysis datasets - ADAM format | 312 |  |  | 7 days | 2024-07-17 | 2024-07-18 | 2024-07-24 | 2024-07-25 | Completed | Released to archive | 700320 |  | Morgan Lee | N. Ortiz | XLSX | Analysis_datasets_ADAM_format_0320.xlsx | Timing estimate is illustrative | Central | 314
[5 empty] | 5.3.3.1 |  | Data definition for analysis datasets - ADAM format (define file) | 313 |  |  | 23 days | 2024-07-18 | 2024-07-18 | 2024-08-10 | 2024-08-14 | Completed |  | 700321 |  | Jamie Carter | M. Sullivan | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0321.zip | Dummy data added for planning demo | Central | 315
[5 empty] | 5.3.3.1 |  | Analysis Data Reviewers Guide | 314 |  |  | 21 days | 2024-07-23 | 2024-07-22 | 2024-08-13 |  | In Progress | Awaiting final source document | 700322 | Authoring | Casey Rivera | R. Gupta | CSV | Analysis_Data_Reviewers_Guide_0322.csv | Placeholder timeline for reporting test | Central | 316
[5 empty] | 5.3.3.1 |  | Analysis programs | 315 |  |  | 33 days | 2024-07-19 | 2024-07-24 | 2024-08-21 | 2024-08-22 | Completed | Filed in baseline wave | 700323 | Archive release | Alex Kim | A. Shah | ZIP | Analysis_programs_0323.zip | Timing estimate is illustrative | Central | 317
[5 empty] | 5.3.3.1 |  | 5.3.3.1 p003mk0001 | 316 |  |  | 29 days | 2024-07-20 | 2024-07-19 | 2024-08-18 | 2024-08-17 | Completed | Filed in baseline wave | 700324 | Publishing QC | Casey Rivera | A. Shah | PDF | p003mk0001_0324.pdf | Dummy data added for planning demo | Central | 318
[5 empty] | 5.3.3.1 |  | Study report [p003mk0001] and related information | 317 |  |  | 31 days | 2024-07-25 | 2024-07-25 | 2024-08-25 | 2024-08-22 | Completed | Completed as planned | 700325 |  | Taylor Chen | A. Shah | DOCX | Study_report_p003mk0001_and_related_information_0325.docx | Dummy data added for planning demo | Central | 319
[5 empty] | 5.3.3.1 |  | Case Report Forms - CRF FOLDER | 318 |  |  | 8 days | 2024-07-23 | 2024-07-20 | 2024-07-31 | 2024-07-28 | Completed | Completed as planned | 700326 |  | Jordan Patel | M. Sullivan | PDF | Case_Report_Forms_CRF_FOLDER_0326.pdf | Timing estimate is illustrative | Central | 320
[5 empty] | 5.3.3.1 |  | Listing of Case Report Forms (CRFs TOC) | 319 |  |  | 7 days | 2024-07-24 | 2024-07-25 | 2024-07-31 | 2024-08-05 | Completed | QC completed | 700327 | Archive release | Jordan Patel | M. Sullivan | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_0327.zip | Timing estimate is illustrative | Central | 321
[5 empty] | 5.3.3.1 |  | Case Report Forms - eCRFs (by site) Category 1 and 2 for US | 320 |  |  | 25 days | 2024-07-28 | 2024-07-25 | 2024-08-22 | 2024-08-26 | Completed | Filed in baseline wave | 700328 | Submission build | Morgan Lee | N. Ortiz | PDF | Case_Report_Forms_eCRFs_by_site_Category_1_and_2_for_US_0328.pdf | Dummy data added for planning demo | Central | 322
[5 empty] | 5.3.3.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER | 321 |  |  | 23 days | 2024-07-24 | 2024-07-29 | 2024-08-16 |  | In Progress | Metadata check in progress | 700329 |  | Jordan Patel | L. Bennett | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_0329.zip | Dummy data added for planning demo | Central | 323
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data tabulation datasets - SDTM or Legacy format( Choose the correct Data format with team) | 322 |  |  | 33 days | 2024-07-23 | 2024-07-26 | 2024-08-25 | 2024-08-27 | Completed | Filed in baseline wave | 700330 |  | Jordan Patel | L. Bennett | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_0330.xlsx | Placeholder timeline for reporting test | Central | 324
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM or Legacy format (define file)( Choose the correct Data format with team) | 323 |  |  | 21 days | 2024-07-23 | 2024-07-22 | 2024-08-13 | 2024-08-16 | Completed | QC completed | 700331 | Archive release | Taylor Chen | A. Shah | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_0331.xlsx | Placeholder timeline for reporting test | Central | 325
[5 empty] | 5.3.3.1 |  | Annotated Case Report Forms (CRFs) - SDTM or Legacy format ( Choose the correct Data format with team) | 324 |  |  | 10 days | 2024-07-29 | 2024-08-02 | 2024-08-08 | 2024-08-13 | Completed | QC completed | 700332 |  | Jordan Patel | M. Sullivan | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_or_Legacy_format_Choos_0332.docx | Placeholder timeline for reporting test | Central | 326
[5 empty] | 5.3.3.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER | 325 |  |  | 13 days | 2024-07-29 | 2024-08-03 | 2024-08-11 |  | In Progress | Regional review underway | 700333 | Publishing prep | Jordan Patel | A. Shah | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_0333.zip | Sample entry for dashboard validation | Central | 327
[5 empty] | 5.3.3.1 |  | Analysis datasets - ADAM format | 326 |  |  | 19 days | 2024-07-25 | 2024-07-23 | 2024-08-13 | 2024-08-10 | Completed | Filed in baseline wave | 700334 |  | Casey Rivera | M. Sullivan | XLSX | Analysis_datasets_ADAM_format_0334.xlsx | Timing estimate is illustrative | Central | 328
[5 empty] | 5.3.3.1 |  | Data definition for analysis datasets - ADAM format (define file) | 327 |  |  | 18 days | 2024-07-25 |  | 2024-08-12 |  | Not Started | Waiting on dependency from Module 3 | 700335 |  | Jordan Patel | M. Sullivan | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0335.csv | Dummy data added for planning demo | Central | 329
[5 empty] | 5.3.3.1 |  | Analysis Data Reviewers Guide | 328 |  |  | 33 days | 2024-07-28 | 2024-08-01 | 2024-08-30 | 2024-08-30 | Completed |  | 700336 |  | Morgan Lee | L. Bennett | CSV | Analysis_Data_Reviewers_Guide_0336.csv | Sample entry for dashboard validation | Central | 330
[5 empty] | 5.3.3.1 |  | Analysis programs | 329 |  |  | 22 days | 2024-07-31 | 2024-07-30 | 2024-08-22 | 2024-08-25 | Completed | Completed as planned | 700337 | Publishing QC | Morgan Lee | L. Bennett | TXT | Analysis_programs_0337.txt | Timing estimate is illustrative | Central | 331
[5 empty] | 5.3.3.1 |  | 5.3.3.1 p006mk0001 | 330 |  |  | 7 days | 2024-07-28 | 2024-07-25 | 2024-08-04 | 2024-08-01 | Completed | Released to archive | 700338 | Publishing QC | Jordan Patel | L. Bennett | XLSX | p006mk0001_0338.xlsx | Placeholder timeline for reporting test | Central | 332
[5 empty] | 5.3.3.1 |  | Study report [p006mk0001] and related information | 331 |  |  | 16 days | 2024-07-28 | 2024-07-26 | 2024-08-13 | 2024-08-10 | Completed |  | 700339 |  | Jamie Carter | L. Bennett | PDF | Study_report_p006mk0001_and_related_information_0339.pdf | Placeholder timeline for reporting test | Central | 333
[5 empty] | 5.3.3.1 |  | Case Report Forms - CRF FOLDER p006mk0001 | 332 |  |  | 22 days | 2024-08-03 | 2024-08-08 | 2024-08-25 | 2024-08-26 | Completed |  | 700340 |  | Alex Kim | A. Shah | DOCX | Case_Report_Forms_CRF_FOLDER_p006mk0001_0340.docx | Dummy data added for planning demo | Central | 334
[5 empty] | 5.3.3.1 |  | Listing of Case Report Forms (CRFs TOC) | 333 |  |  | 21 days | 2024-08-03 | 2024-08-06 | 2024-08-24 | 2024-08-27 | Completed | Released to archive | 700341 | Publishing QC | Alex Kim | N. Ortiz | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_0341.zip | Placeholder timeline for reporting test | Central | 335
[5 empty] | 5.3.3.1 |  | Case Report Forms - eCRFs (by site) for US | 334 |  |  | 22 days | 2024-07-30 | 2024-07-31 | 2024-08-21 | 2024-08-28 | Completed | Released to archive | 700342 |  | Jamie Carter | A. Shah | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0342.docx | Sample entry for dashboard validation | Central | 336
[5 empty] | 5.3.3.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p006mk0001 | 335 |  |  | 24 days | 2024-08-05 | 2024-08-11 | 2024-08-29 |  | In Progress | Draft in QC review | 700343 | Regional alignment | Morgan Lee | L. Bennett | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_0343.zip | Sample entry for dashboard validation | Central | 337
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 336 |  |  | 31 days | 2024-08-03 |  | 2024-09-03 |  | Not Started | Waiting on dependency from Module 3 | 700344 |  | Alex Kim | A. Shah | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_0344.zip | Dummy data added for planning demo | Central | 338
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 337 |  |  | 33 days | 2024-08-01 | 2024-07-29 | 2024-09-03 | 2024-09-09 | Completed | QC completed | 700345 |  | Alex Kim | L. Bennett | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_0345.csv | Placeholder timeline for reporting test | Central | 339
[5 empty] | 5.3.3.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 338 |  |  | 18 days | 2024-08-06 | 2024-08-06 | 2024-08-24 | 2024-08-23 | Completed | Filed in baseline wave | 700346 | Archive release | Taylor Chen | A. Shah | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0346.pdf | Placeholder timeline for reporting test | Central | 340
[5 empty] | 5.3.3.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p006mk0001 | 339 |  |  | 17 days | 2024-08-01 | 2024-08-06 | 2024-08-18 | 2024-08-19 | Completed | Completed as planned | 700347 |  | Sam Brooks | L. Bennett | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p006mk0001_0347.zip | Sample entry for dashboard validation | Central | 341
[5 empty] | 5.3.3.1 |  | Analysis datasets - ADAM format | 340 |  |  | 7 days | 2024-08-05 | 2024-08-02 | 2024-08-12 | 2024-08-13 | Completed | Released to archive | 700348 |  | Casey Rivera | R. Gupta | ZIP | Analysis_datasets_ADAM_format_0348.zip | Dummy data added for planning demo | Central | 342
[5 empty] | 5.3.3.1 |  | Data definition for analysis datasets - ADAM format (define file) | 341 |  |  | 10 days | 2024-08-08 | 2024-08-08 | 2024-08-18 | 2024-08-19 | Completed | Released to archive | 700349 |  | Jamie Carter | R. Gupta | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0349.xlsx | Placeholder timeline for reporting test | Central | 343
[5 empty] | 5.3.3.1 |  | Analysis Data Reviewers Guide | 342 |  |  | 20 days | 2024-08-07 | 2024-08-05 | 2024-08-27 | 2024-08-31 | Completed | Filed in baseline wave | 700350 | Archive release | Morgan Lee | A. Shah | CSV | Analysis_Data_Reviewers_Guide_0350.csv | Sample entry for dashboard validation | Central | 344
[5 empty] | 5.3.3.1 |  | Analysis programs | 343 |  |  | 26 days | 2024-08-05 | 2024-08-03 | 2024-08-31 | 2024-09-07 | Completed |  | 700351 | Publishing QC | Taylor Chen | R. Gupta | TXT | Analysis_programs_0351.txt | Dummy data added for planning demo | Central | 345
[5 empty] | 5.3.3.1 |  | 5.3.3.1 p010mk0001 | 344 |  |  | 22 days | 2024-08-11 | 2024-08-13 | 2024-09-02 | 2024-08-30 | Completed | QC completed | 700352 |  | Jamie Carter | R. Gupta | DOCX | p010mk0001_0352.docx | Placeholder timeline for reporting test | Central | 346
[5 empty] | 5.3.3.1 |  | Study report [p010mk0001] and related information | 345 |  |  | 20 days | 2024-08-07 | 2024-08-12 | 2024-08-27 | 2024-08-30 | Completed |  | 700353 | Submission build | Alex Kim | M. Sullivan | PDF | Study_report_p010mk0001_and_related_information_0353.pdf | Sample entry for dashboard validation | Central | 347
[5 empty] | 5.3.3.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p010mk0001 | 346 |  |  | 28 days | 2024-08-07 | 2024-08-12 | 2024-09-04 |  | In Progress | Metadata check in progress | 700354 |  | Jamie Carter | M. Sullivan | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_0354.csv | Dummy data added for planning demo | Central | 348
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 347 |  |  | 13 days | 2024-08-13 | 2024-08-12 | 2024-08-26 | 2024-08-25 | Completed | Filed in baseline wave | 700355 | Archive release | Jamie Carter | L. Bennett | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_0355.csv | Placeholder timeline for reporting test | Central | 349
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 348 |  |  | 27 days | 2024-08-06 | 2024-08-09 | 2024-09-02 | 2024-09-02 | Completed | QC completed | 700356 | Submission build | Morgan Lee | M. Sullivan | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_0356.xlsx | Sample entry for dashboard validation | Central | 350
[5 empty] | 5.3.3.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 349 |  |  | 10 days | 2024-08-09 | 2024-08-06 | 2024-08-19 | 2024-08-18 | Completed | QC completed | 700357 |  | Casey Rivera | M. Sullivan | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0357.docx | Sample entry for dashboard validation | Central | 351
[5 empty] | 5.3.3.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p010mk0001 | 350 |  |  | 13 days | 2024-08-07 | 2024-08-06 | 2024-08-20 | 2024-08-16 | Completed | QC completed | 700358 | Archive release | Sam Brooks | M. Sullivan | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p010mk0001_0358.xlsx | Dummy data added for planning demo | Central | 352
[5 empty] | 5.3.3.1 |  | Analysis datasets - ADAM format | 351 |  |  | 32 days | 2024-08-14 | 2024-08-12 | 2024-09-15 | 2024-09-16 | Completed |  | 700359 | Archive release | Jamie Carter | A. Shah | CSV | Analysis_datasets_ADAM_format_0359.csv | Placeholder timeline for reporting test | Central | 353
[5 empty] | 5.3.3.1 |  | Data definition for analysis datasets - ADAM format (define file) | 352 |  |  | 19 days | 2024-08-09 | 2024-08-09 | 2024-08-28 |  | In Progress | Awaiting final source document | 700360 | Authoring | Taylor Chen | M. Sullivan | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0360.xlsx | Placeholder timeline for reporting test | Central | 354
[5 empty] | 5.3.3.1 |  | Analysis Data Reviewers Guide | 353 |  |  | 35 days | 2024-08-15 | 2024-08-13 | 2024-09-19 | 2024-09-20 | Completed | QC completed | 700361 |  | Sam Brooks | L. Bennett | ZIP | Analysis_Data_Reviewers_Guide_0361.zip | Timing estimate is illustrative | Central | 355
[5 empty] | 5.3.3.1 |  | Analysis programs | 354 |  |  | 13 days | 2024-08-15 | 2024-08-14 | 2024-08-28 | 2024-08-27 | Completed | QC completed | 700362 |  | Casey Rivera | R. Gupta | ZIP | Analysis_programs_0362.zip | Sample entry for dashboard validation | Central | 356
[5 empty] | 5.3.3.1 |  | 5.3.3.1 p012mk0001 | 355 |  |  | 18 days | 2024-08-17 | 2024-08-15 | 2024-09-04 | 2024-09-05 | Completed |  | 700363 |  | Casey Rivera | N. Ortiz | DOCX | p012mk0001_0363.docx | Timing estimate is illustrative | Central | 357
[5 empty] | 5.3.3.1 |  | Study report [p012mk0001 ] and related information | 356 |  |  | 22 days | 2024-08-15 | 2024-08-16 | 2024-09-06 | 2024-09-02 | Completed |  | 700364 | Publishing QC | Jamie Carter | A. Shah | PDF | Study_report_p012mk0001_and_related_information_0364.pdf | Placeholder timeline for reporting test | Central | 358
[5 empty] | 5.3.3.1 |  | Case Report Forms - CRF FOLDER p012mk0001 | 357 |  |  | 19 days | 2024-08-19 | 2024-08-21 | 2024-09-07 | 2024-09-13 | Completed | Completed as planned | 700365 |  | Jamie Carter | N. Ortiz | DOCX | Case_Report_Forms_CRF_FOLDER_p012mk0001_0365.docx | Sample entry for dashboard validation | Central | 359
[5 empty] | 5.3.3.1 |  | Listing of Case Report Forms (CRFs TOC) | 358 |  |  | 19 days | 2024-08-11 | 2024-08-13 | 2024-08-30 |  | In Progress | Metadata check in progress | 700366 | Authoring | Jamie Carter | N. Ortiz | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_0366.csv | Timing estimate is illustrative | Central | 360
[5 empty] | 5.3.3.1 |  | Case Report Forms - eCRFs (by site) for US | 359 |  |  | 21 days | 2024-08-14 | 2024-08-17 | 2024-09-04 | 2024-08-31 | Completed | QC completed | 700367 | Publishing QC | Jamie Carter | L. Bennett | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0367.docx | Sample entry for dashboard validation | Central | 361
[5 empty] | 5.3.3.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p012mk0001 | 360 |  |  | 29 days | 2024-08-17 | 2024-08-15 | 2024-09-15 | 2024-09-13 | Completed | QC completed | 700368 |  | Alex Kim | R. Gupta | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_0368.csv | Placeholder timeline for reporting test | Central | 362
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 361 |  |  | 29 days | 2024-08-20 | 2024-08-17 | 2024-09-18 | 2024-09-24 | Completed | Filed in baseline wave | 700369 |  | Jamie Carter | N. Ortiz | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_0369.xlsx | Sample entry for dashboard validation | Central | 363
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 362 |  |  | 27 days | 2024-08-17 | 2024-08-15 | 2024-09-13 | 2024-09-10 | Completed | Filed in baseline wave | 700370 | Submission build | Taylor Chen | N. Ortiz | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_0370.zip | Sample entry for dashboard validation | Central | 364
[5 empty] | 5.3.3.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 363 |  |  | 21 days | 2024-08-19 | 2024-08-18 | 2024-09-09 | 2024-09-09 | Completed | Filed in baseline wave | 700371 |  | Jamie Carter | R. Gupta | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0371.docx | Timing estimate is illustrative | Central | 365
[5 empty] | 5.3.3.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p012mk0001 | 364 |  |  | 20 days | 2024-08-16 | 2024-08-19 | 2024-09-05 | 2024-09-07 | Completed |  | 700372 | Submission build | Alex Kim | A. Shah | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p012mk0001_0372.zip | Timing estimate is illustrative | Central | 366
[5 empty] | 5.3.3.1 |  | Analysis datasets - ADAM format | 365 |  |  | 21 days | 2024-08-16 | 2024-08-15 | 2024-09-06 | 2024-09-02 | Completed | Released to archive | 700373 |  | Casey Rivera | M. Sullivan | CSV | Analysis_datasets_ADAM_format_0373.csv | Timing estimate is illustrative | Central | 367
[5 empty] | 5.3.3.1 |  | Data definition for analysis datasets - ADAM format (define file) | 366 |  |  | 18 days | 2024-08-17 | 2024-08-15 | 2024-09-04 | 2024-08-31 | Completed |  | 700374 |  | Jamie Carter | L. Bennett | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0374.zip | Sample entry for dashboard validation | Central | 368
[5 empty] | 5.3.3.1 |  | Analysis Data Reviewers Guide | 367 |  |  | 14 days | 2024-08-17 | 2024-08-17 | 2024-08-31 | 2024-08-31 | Completed | QC completed | 700375 |  | Casey Rivera | N. Ortiz | CSV | Analysis_Data_Reviewers_Guide_0375.csv | Timing estimate is illustrative | Central | 369
[5 empty] | 5.3.3.1 |  | Analysis programs | 368 |  |  | 33 days | 2024-08-20 | 2024-08-20 | 2024-09-22 | 2024-09-24 | Completed | Filed in baseline wave | 700376 |  | Jamie Carter | N. Ortiz | ZIP | Analysis_programs_0376.zip | Placeholder timeline for reporting test | Central | 370
[5 empty] | 5.3.3.1 |  | 5.3.3.1 p016mk0001 | 369 |  |  | 14 days | 2024-08-22 | 2024-08-22 | 2024-09-05 | 2024-09-06 | Completed |  | 700377 |  | Alex Kim | A. Shah | DOCX | p016mk0001_0377.docx | Timing estimate is illustrative | Central | 371
[5 empty] | 5.3.3.1 |  | Study report [p016mk0001] and related information | 370 |  |  | 29 days | 2024-08-23 | 2024-08-23 | 2024-09-21 | 2024-09-28 | Completed | Released to archive | 700378 |  | Sam Brooks | M. Sullivan | DOCX | Study_report_p016mk0001_and_related_information_0378.docx | Dummy data added for planning demo | Central | 372
[5 empty] | 5.3.3.1 |  | Case Report Forms - CRF FOLDER p016mk0001 | 371 |  |  | 24 days | 2024-08-20 | 2024-08-22 | 2024-09-13 | 2024-09-12 | Completed | Released to archive | 700379 | Archive release | Taylor Chen | M. Sullivan | PDF | Case_Report_Forms_CRF_FOLDER_p016mk0001_0379.pdf | Dummy data added for planning demo | Central | 373
[5 empty] | 5.3.3.1 |  | Listing of Case Report Forms (CRFs TOC) | 372 |  |  | 23 days | 2024-08-23 | 2024-08-24 | 2024-09-15 | 2024-09-17 | Completed | QC completed | 700380 | Submission build | Taylor Chen | A. Shah | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_0380.zip | Timing estimate is illustrative | Central | 374
[5 empty] | 5.3.3.1 |  | Case Report Forms - eCRFs (by site) for US | 373 |  |  | 12 days | 2024-08-24 | 2024-08-26 | 2024-09-05 | 2024-09-08 | Completed | Filed in baseline wave | 700381 | Publishing QC | Morgan Lee | M. Sullivan | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0381.docx | Timing estimate is illustrative | Central | 375
[5 empty] | 5.3.3.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p016mk0001 | 374 |  |  | 10 days | 2024-08-25 | 2024-08-24 | 2024-09-04 | 2024-09-07 | Completed | QC completed | 700382 | Archive release | Casey Rivera | R. Gupta | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_0382.csv | Placeholder timeline for reporting test | Central | 376
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 375 |  |  | 17 days | 2024-08-29 | 2024-08-28 | 2024-09-15 | 2024-09-16 | Completed | Released to archive | 700383 | Submission build | Taylor Chen | L. Bennett | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_0383.xlsx | Timing estimate is illustrative | Central | 377
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 376 |  |  | 8 days | 2024-08-24 | 2024-08-21 | 2024-09-01 | 2024-09-04 | Completed | QC completed | 700384 | Submission build | Sam Brooks | L. Bennett | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_0384.csv | Dummy data added for planning demo | Central | 378
[5 empty] | 5.3.3.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 377 |  |  | 8 days | 2024-08-29 | 2024-09-03 | 2024-09-06 | 2024-09-09 | Completed | Released to archive | 700385 |  | Alex Kim | N. Ortiz | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0385.pdf | Placeholder timeline for reporting test | Central | 379
[5 empty] | 5.3.3.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p016mk0001 | 378 |  |  | 13 days | 2024-08-24 | 2024-08-24 | 2024-09-06 |  | In Progress | Awaiting final source document | 700386 |  | Jamie Carter | R. Gupta | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p016mk0001_0386.zip | Timing estimate is illustrative | Central | 380
[5 empty] | 5.3.3.1 |  | Analysis datasets - ADAM format | 379 |  |  | 23 days | 2024-08-23 | 2024-08-22 | 2024-09-15 | 2024-09-17 | Completed | Completed as planned | 700387 | Submission build | Jamie Carter | L. Bennett | ZIP | Analysis_datasets_ADAM_format_0387.zip | Dummy data added for planning demo | Central | 381
[5 empty] | 5.3.3.1 |  | Data definition for analysis datasets - ADAM format (define file) | 380 |  |  | 7 days | 2024-08-29 | 2024-08-27 | 2024-09-05 | 2024-09-07 | Completed | QC completed | 700388 |  | Alex Kim | R. Gupta | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0388.xlsx | Dummy data added for planning demo | Central | 382
[5 empty] | 5.3.3.1 |  | Analysis Data Reviewers Guide | 381 |  |  | 21 days | 2024-08-26 | 2024-08-31 | 2024-09-16 |  | In Progress | Publishing build in progress | 700389 | Publishing prep | Taylor Chen | A. Shah | CSV | Analysis_Data_Reviewers_Guide_0389.csv | Dummy data added for planning demo | Central | 383
[5 empty] | 5.3.3.1 |  | Analysis programs | 382 |  |  | 17 days | 2024-09-01 | 2024-09-01 | 2024-09-18 |  | In Progress | Awaiting final source document | 700390 | Authoring | Jamie Carter | R. Gupta | TXT | Analysis_programs_0390.txt | Dummy data added for planning demo | Central | 384
[5 empty] | 5.3.3.3 |  | 5.3.3.3 p007mk0001 | 383 |  |  | 24 days | 2024-08-27 | 2024-08-31 | 2024-09-20 |  | In Progress | Draft in QC review | 700391 | Regional alignment | Morgan Lee | N. Ortiz | PDF | p007mk0001_0391.pdf | Sample entry for dashboard validation | Central | 385
[5 empty] | 5.3.3.3 |  | Study report [p007mk0001] and related information | 384 |  |  | 7 days | 2024-08-27 | 2024-08-27 | 2024-09-03 |  | In Progress | Publishing build in progress | 700392 | Regional alignment | Morgan Lee | N. Ortiz | PDF | Study_report_p007mk0001_and_related_information_0392.pdf | Placeholder timeline for reporting test | Central | 386
[5 empty] | 5.3.3.3 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p007mk0001 | 385 |  |  | 32 days | 2024-09-03 | 2024-09-04 | 2024-10-05 | 2024-10-11 | Completed |  | 700393 | Submission build | Morgan Lee | A. Shah | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_0393.csv | Timing estimate is illustrative | Central | 387
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 386 |  |  | 21 days | 2024-09-04 | 2024-09-09 | 2024-09-25 |  | In Progress | Metadata check in progress | 700394 |  | Taylor Chen | L. Bennett | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_0394.xlsx | Sample entry for dashboard validation | Central | 388
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 387 |  |  | 26 days | 2024-09-02 | 2024-09-05 | 2024-09-28 | 2024-09-25 | Completed | Completed as planned | 700395 |  | Morgan Lee | L. Bennett | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_0395.zip | Timing estimate is illustrative | Central | 389
[5 empty] | 5.3.3.3 |  | Annotated Case Report Forms (CRFs) - SDTM format | 388 |  |  | 22 days | 2024-08-31 | 2024-09-05 | 2024-09-22 | 2024-09-19 | Completed | QC completed | 700396 |  | Casey Rivera | A. Shah | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0396.docx | Placeholder timeline for reporting test | Central | 390
[5 empty] | 5.3.3.3 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p007mk0001 | 389 |  |  | 11 days | 2024-08-31 | 2024-09-01 | 2024-09-11 | 2024-09-10 | Completed |  | 700397 |  | Morgan Lee | M. Sullivan | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p007mk0001_0397.xlsx | Dummy data added for planning demo | Central | 391
[5 empty] | 5.3.3.3 |  | Analysis datasets - ADAM format | 390 |  |  | 23 days | 2024-08-30 | 2024-09-02 | 2024-09-22 | 2024-09-24 | Completed | Completed as planned | 700398 |  | Sam Brooks | M. Sullivan | CSV | Analysis_datasets_ADAM_format_0398.csv | Placeholder timeline for reporting test | Central | 392
[5 empty] | 5.3.3.3 |  | Data definition for analysis datasets - ADAM format (define file) | 391 |  |  | 25 days | 2024-09-03 | 2024-09-08 | 2024-09-28 | 2024-09-24 | Completed | Completed as planned | 700399 |  | Jordan Patel | N. Ortiz | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0399.csv | Dummy data added for planning demo | Central | 393
[5 empty] | 5.3.3.3 |  | Analysis Data Reviewers Guide | 392 |  |  | 20 days | 2024-09-01 | 2024-09-03 | 2024-09-21 |  | In Progress | Metadata check in progress | 700400 |  | Sam Brooks | L. Bennett | ZIP | Analysis_Data_Reviewers_Guide_0400.zip | Sample entry for dashboard validation | Central | 394
[5 empty] | 5.3.3.3 |  | Analysis programs | 393 |  |  | 17 days | 2024-09-05 | 2024-09-05 | 2024-09-22 |  | In Progress | Awaiting final source document | 700401 | QC review | Alex Kim | M. Sullivan | TXT | Analysis_programs_0401.txt | Dummy data added for planning demo | Central | 395
[5 empty] | 5.3.3.3 |  | 5.3.3.3 p011mk0001 | 394 |  |  | 24 days | 2024-09-07 | 2024-09-10 | 2024-10-01 | 2024-09-28 | Completed | Completed as planned | 700402 | Submission build | Sam Brooks | L. Bennett | DOCX | p011mk0001_0402.docx | Sample entry for dashboard validation | Central | 396
[5 empty] | 5.3.3.3 |  | Study report [p011mk0001] and related information | 395 |  |  | 16 days | 2024-09-09 | 2024-09-11 | 2024-09-25 | 2024-10-02 | Completed | Released to archive | 700403 | Archive release | Alex Kim | N. Ortiz | PDF | Study_report_p011mk0001_and_related_information_0403.pdf | Dummy data added for planning demo | Central | 397
[5 empty] | 5.3.3.3 |  | Case Report Forms - CRF FOLDER p011mk0001 | 396 |  |  | 10 days | 2024-09-05 | 2024-09-06 | 2024-09-15 |  | In Progress | Draft in QC review | 700404 | QC review | Casey Rivera | N. Ortiz | PDF | Case_Report_Forms_CRF_FOLDER_p011mk0001_0404.pdf | Sample entry for dashboard validation | Central | 398
[5 empty] | 5.3.3.3 |  | Listing of Case Report Forms (CRFs TOC) | 397 |  |  | 13 days | 2024-09-11 | 2024-09-15 | 2024-09-24 | 2024-09-22 | Completed | Released to archive | 700405 |  | Alex Kim | A. Shah | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_0405.xlsx | Timing estimate is illustrative | Central | 399
[5 empty] | 5.3.3.3 |  | Case Report Forms - eCRFs (by site) for US | 398 |  |  | 22 days | 2024-09-11 | 2024-09-15 | 2024-10-03 | 2024-10-08 | Completed | Filed in baseline wave | 700406 | Submission build | Morgan Lee | M. Sullivan | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0406.docx | Dummy data added for planning demo | Central | 400
[5 empty] | 5.3.3.3 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p011mk0001 | 399 |  |  | 7 days | 2024-09-09 | 2024-09-12 | 2024-09-16 | 2024-09-18 | Completed | Released to archive | 700407 |  | Taylor Chen | M. Sullivan | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_0407.csv | Dummy data added for planning demo | Central | 401
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 400 |  |  | 19 days | 2024-09-12 | 2024-09-16 | 2024-10-01 | 2024-09-30 | Completed | Completed as planned | 700408 |  | Alex Kim | L. Bennett | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_0408.zip | Placeholder timeline for reporting test | Central | 402
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 401 |  |  | 9 days | 2024-09-13 | 2024-09-16 | 2024-09-22 | 2024-09-25 | Completed | Completed as planned | 700409 |  | Taylor Chen | R. Gupta | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_0409.csv | Sample entry for dashboard validation | Central | 403
[5 empty] | 5.3.3.3 |  | Annotated Case Report Forms (CRFs) - SDTM format | 402 |  |  | 12 days | 2024-09-06 | 2024-09-06 | 2024-09-18 | 2024-09-21 | Completed | QC completed | 700410 |  | Jordan Patel | M. Sullivan | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0410.pdf | Placeholder timeline for reporting test | Central | 404
[5 empty] | 5.3.3.3 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p011mk0001 | 403 |  |  | 11 days | 2024-09-13 | 2024-09-17 | 2024-09-24 |  | In Progress | Publishing build in progress | 700411 | Publishing prep | Jamie Carter | L. Bennett | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p011mk0001_0411.xlsx | Timing estimate is illustrative | Central | 405
[5 empty] | 5.3.3.3 |  | Analysis datasets - ADAM format | 404 |  |  | 29 days | 2024-09-11 | 2024-09-15 | 2024-10-10 | 2024-10-08 | Completed | Filed in baseline wave | 700412 | Submission build | Jordan Patel | M. Sullivan | CSV | Analysis_datasets_ADAM_format_0412.csv | Dummy data added for planning demo | Central | 406
[5 empty] | 5.3.3.3 |  | Data definition for analysis datasets - ADAM format (define file) | 405 |  |  | 22 days | 2024-09-14 | 2024-09-14 | 2024-10-06 | 2024-10-10 | Completed | Completed as planned | 700413 | Publishing QC | Morgan Lee | R. Gupta | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0413.csv | Timing estimate is illustrative | Central | 407
[5 empty] | 5.3.3.3 |  | Analysis Data Reviewers Guide | 406 |  |  | 33 days | 2024-09-10 | 2024-09-16 | 2024-10-13 |  | In Progress | Draft in QC review | 700414 | Authoring | Morgan Lee | L. Bennett | XLSX | Analysis_Data_Reviewers_Guide_0414.xlsx | Timing estimate is illustrative | Central | 408
[5 empty] | 5.3.3.3 |  | Analysis programs | 407 |  |  | 24 days | 2024-09-10 | 2024-09-11 | 2024-10-04 | 2024-10-05 | Completed | QC completed | 700415 | Publishing QC | Jamie Carter | M. Sullivan | TXT | Analysis_programs_0415.txt | Timing estimate is illustrative | Central | 409
[5 empty] | 5.3.3.3 |  | 5.3.3.3 p020mk0001 | 408 |  |  | 26 days | 2024-09-17 | 2024-09-14 | 2024-10-13 | 2024-10-16 | Completed | Released to archive | 700416 | Publishing QC | Alex Kim | M. Sullivan | XLSX | p020mk0001_0416.xlsx | Dummy data added for planning demo | Central | 410
[5 empty] | 5.3.3.3 |  | Study report [p020mk0001] and related information | 409 |  |  | 8 days | 2024-09-18 | 2024-09-17 | 2024-09-26 | 2024-10-02 | Completed | Completed as planned | 700417 | Submission build | Morgan Lee | N. Ortiz | DOCX | Study_report_p020mk0001_and_related_information_0417.docx | Sample entry for dashboard validation | Central | 411
[5 empty] | 5.3.3.3 |  | Case Report Forms - CRF FOLDER p020mk0001 | 410 |  |  | 22 days | 2024-09-19 | 2024-09-17 | 2024-10-11 | 2024-10-09 | Completed | QC completed | 700418 | Archive release | Jamie Carter | N. Ortiz | PDF | Case_Report_Forms_CRF_FOLDER_p020mk0001_0418.pdf | Timing estimate is illustrative | Central | 412
[5 empty] | 5.3.3.3 |  | Listing of Case Report Forms (CRFs TOC) | 411 |  |  | 20 days | 2024-09-18 | 2024-09-15 | 2024-10-08 | 2024-10-07 | Completed | Released to archive | 700419 | Archive release | Morgan Lee | M. Sullivan | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_0419.xlsx | Dummy data added for planning demo | Central | 413
[5 empty] | 5.3.3.3 |  | Case Report Forms - eCRFs (by site) for US | 412 |  |  | 18 days | 2024-09-16 | 2024-09-19 | 2024-10-04 | 2024-10-05 | Completed | Filed in baseline wave | 700420 | Submission build | Jamie Carter | M. Sullivan | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0420.docx | Timing estimate is illustrative | Central | 414
[5 empty] | 5.3.3.3 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p020mk0001 | 413 |  |  | 32 days | 2024-09-14 | 2024-09-17 | 2024-10-16 | 2024-10-19 | Completed |  | 700421 | Archive release | Alex Kim | L. Bennett | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_0421.xlsx | Dummy data added for planning demo | Central | 415
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 414 |  |  | 9 days | 2024-09-21 | 2024-09-23 | 2024-09-30 | 2024-10-02 | Completed | Filed in baseline wave | 700422 |  | Alex Kim | L. Bennett | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_0422.xlsx | Timing estimate is illustrative | Central | 416
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 415 |  |  | 27 days | 2024-09-14 |  | 2024-10-11 |  | Not Started | On hold pending document availability | 700423 |  | Taylor Chen | R. Gupta | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_0423.csv | Sample entry for dashboard validation | Central | 417
[5 empty] | 5.3.3.3 |  | Annotated Case Report Forms (CRFs) - SDTM format | 416 |  |  | 34 days | 2024-09-22 | 2024-09-24 | 2024-10-26 | 2024-10-27 | Completed | Completed as planned | 700424 | Archive release | Taylor Chen | M. Sullivan | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0424.pdf | Sample entry for dashboard validation | Central | 418
[5 empty] | 5.3.3.3 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p020mk0001 | 417 |  |  | 27 days | 2024-09-22 | 2024-09-27 | 2024-10-19 | 2024-10-24 | Completed |  | 700425 |  | Sam Brooks | R. Gupta | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p020mk0001_0425.zip | Sample entry for dashboard validation | Central | 419
[5 empty] | 5.3.3.3 |  | Analysis datasets - ADAM format | 418 |  |  | 35 days | 2024-09-18 | 2024-09-15 | 2024-10-23 | 2024-10-27 | Completed | QC completed | 700426 |  | Sam Brooks | N. Ortiz | ZIP | Analysis_datasets_ADAM_format_0426.zip | Placeholder timeline for reporting test | Central | 420
[5 empty] | 5.3.3.3 |  | Data definition for analysis datasets - ADAM format (define file) | 419 |  |  | 9 days | 2024-09-19 | 2024-09-20 | 2024-09-28 | 2024-10-02 | Completed | QC completed | 700427 | Submission build | Alex Kim | A. Shah | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0427.zip | Placeholder timeline for reporting test | Central | 421
[5 empty] | 5.3.3.3 |  | Analysis Data Reviewers Guide | 420 |  |  | 33 days | 2024-09-19 | 2024-09-22 | 2024-10-22 | 2024-10-26 | Completed | Completed as planned | 700428 | Publishing QC | Jamie Carter | R. Gupta | CSV | Analysis_Data_Reviewers_Guide_0428.csv | Placeholder timeline for reporting test | Central | 422
[5 empty] | 5.3.3.3 |  | Analysis programs | 421 |  |  | 8 days | 2024-09-18 | 2024-09-16 | 2024-09-26 | 2024-09-29 | Completed | QC completed | 700429 |  | Sam Brooks | A. Shah | TXT | Analysis_programs_0429.txt | Placeholder timeline for reporting test | Central | 423
[5 empty] | 5.3.3.3 |  | 5.3.3.3 p030mk0001 | 422 |  |  | 32 days | 2024-09-21 | 2024-09-26 | 2024-10-23 | 2024-10-28 | Completed | Filed in baseline wave | 700430 | Archive release | Morgan Lee | R. Gupta | XLSX | p030mk0001_0430.xlsx | Timing estimate is illustrative | Central | 424
[5 empty] | 5.3.3.3 |  | Study report [p030mk0001] and related information | 423 |  |  | 23 days | 2024-09-24 | 2024-09-22 | 2024-10-17 | 2024-10-18 | Completed |  | 700431 |  | Jordan Patel | R. Gupta | DOCX | Study_report_p030mk0001_and_related_information_0431.docx | Dummy data added for planning demo | Central | 425
[5 empty] | 5.3.3.3 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p030mk0001 | 424 |  |  | 29 days | 2024-09-21 | 2024-09-24 | 2024-10-20 | 2024-10-17 | Completed | Completed as planned | 700432 | Publishing QC | Casey Rivera | N. Ortiz | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p03_0432.csv | Timing estimate is illustrative | Central | 426
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 425 |  |  | 9 days | 2024-09-26 | 2024-10-01 | 2024-10-05 | 2024-10-07 | Completed |  | 700433 |  | Taylor Chen | L. Bennett | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_0433.csv | Sample entry for dashboard validation | Central | 427
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 426 |  |  | 21 days | 2024-09-26 | 2024-09-30 | 2024-10-17 | 2024-10-24 | Completed | Released to archive | 700434 | Submission build | Jordan Patel | M. Sullivan | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_0434.xlsx | Sample entry for dashboard validation | Central | 428
[5 empty] | 5.3.3.3 |  | Annotated Case Report Forms (CRFs) - SDTM format | 427 |  |  | 11 days | 2024-09-28 | 2024-10-04 | 2024-10-09 |  | In Progress | Pending cross-functional signoff | 700435 | Authoring | Sam Brooks | N. Ortiz | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0435.docx | Sample entry for dashboard validation | Central | 429
[5 empty] | 5.3.3.3 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p030mk0001 | 428 |  |  | 30 days | 2024-09-21 | 2024-09-26 | 2024-10-21 | 2024-10-22 | Completed | Completed as planned | 700436 |  | Jamie Carter | L. Bennett | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p030mk0001_0436.xlsx | Dummy data added for planning demo | Central | 430
[5 empty] | 5.3.3.3 |  | Analysis datasets - ADAM format | 429 |  |  | 25 days | 2024-09-27 | 2024-10-02 | 2024-10-22 | 2024-10-20 | Completed | Completed as planned | 700437 | Archive release | Morgan Lee | R. Gupta | CSV | Analysis_datasets_ADAM_format_0437.csv | Placeholder timeline for reporting test | Central | 431
[5 empty] | 5.3.3.3 |  | Data definition for analysis datasets - ADAM format (define file) | 430 |  |  | 7 days | 2024-09-29 | 2024-09-29 | 2024-10-06 |  | In Progress | Pending cross-functional signoff | 700438 | Regional alignment | Alex Kim | R. Gupta | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0438.csv | Timing estimate is illustrative | Central | 432
[5 empty] | 5.3.3.3 |  | Analysis Data Reviewers Guide | 431 |  |  | 33 days | 2024-09-25 | 2024-09-23 | 2024-10-28 |  | In Progress | Draft in QC review | 700439 |  | Morgan Lee | A. Shah | XLSX | Analysis_Data_Reviewers_Guide_0439.xlsx | Sample entry for dashboard validation | Central | 433
[5 empty] | 5.3.3.3 |  | Analysis programs | 432 |  |  | 25 days | 2024-09-30 | 2024-10-04 | 2024-10-25 | 2024-10-26 | Completed | Released to archive | 700440 |  | Jamie Carter | M. Sullivan | ZIP | Analysis_programs_0440.zip | Timing estimate is illustrative | Central | 434
[5 empty] | 5.3.3.3 |  | 5.3.3.3 p032mk0001 | 433 |  |  | 27 days | 2024-10-02 | 2024-10-06 | 2024-10-29 | 2024-11-04 | Completed | Released to archive | 700441 | Submission build | Jamie Carter | R. Gupta | PDF | p032mk0001_0441.pdf | Sample entry for dashboard validation | Central | 435
[5 empty] | 5.3.3.3 |  | Study report [p032mk0001] and related information | 434 |  |  | 14 days | 2024-10-01 |  | 2024-10-15 |  | Not Started | Waiting on dependency from Module 3 | 700442 |  | Taylor Chen | A. Shah | DOCX | Study_report_p032mk0001_and_related_information_0442.docx | Placeholder timeline for reporting test | Central | 436
[5 empty] | 5.3.3.3 |  | Case Report Forms - CRF FOLDER p032mk0001 | 435 |  |  | 34 days | 2024-09-26 | 2024-09-23 | 2024-10-30 | 2024-11-04 | Completed | QC completed | 700443 |  | Sam Brooks | A. Shah | PDF | Case_Report_Forms_CRF_FOLDER_p032mk0001_0443.pdf | Timing estimate is illustrative | Central | 437
[5 empty] | 5.3.3.3 |  | Listing of Case Report Forms (CRFs TOC) | 436 |  |  | 25 days | 2024-10-04 | 2024-10-10 | 2024-10-29 |  | In Progress | Awaiting final source document | 700444 | Regional alignment | Taylor Chen | A. Shah | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_0444.xlsx | Timing estimate is illustrative | Central | 438
[5 empty] | 5.3.3.3 |  | Case Report Forms - eCRFs (by site) for US | 437 |  |  | 15 days | 2024-09-26 | 2024-09-27 | 2024-10-11 |  | In Progress | Regional review underway | 700445 |  | Casey Rivera | A. Shah | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0445.docx | Sample entry for dashboard validation | Central | 439
[5 empty] | 5.3.3.3 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p032mk0001 | 438 |  |  | 22 days | 2024-09-27 | 2024-09-25 | 2024-10-19 |  | In Progress | Metadata check in progress | 700446 | Regional alignment | Jordan Patel | L. Bennett | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p03_0446.xlsx | Placeholder timeline for reporting test | Central | 440
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 439 |  |  | 15 days | 2024-10-04 | 2024-10-02 | 2024-10-19 | 2024-10-23 | Completed | Filed in baseline wave | 700447 | Archive release | Jordan Patel | N. Ortiz | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_0447.csv | Dummy data added for planning demo | Central | 441
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 440 |  |  | 16 days | 2024-09-30 |  | 2024-10-16 |  | Not Started | On hold pending document availability | 700448 |  | Jordan Patel | A. Shah | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_0448.zip | Placeholder timeline for reporting test | Central | 442
[5 empty] | 5.3.3.3 |  | Annotated Case Report Forms (CRFs) - SDTM format | 441 |  |  | 7 days | 2024-10-01 | 2024-10-03 | 2024-10-08 |  | In Progress | Publishing build in progress | 700449 | Authoring | Morgan Lee | N. Ortiz | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0449.docx | Placeholder timeline for reporting test | Central | 443
[5 empty] | 5.3.3.3 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p032mk0001 | 442 |  |  | 19 days | 2024-10-03 |  | 2024-10-22 |  | Not Started | Planned for upcoming wave | 700450 |  | Alex Kim | N. Ortiz | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p032mk0001_0450.xlsx | Timing estimate is illustrative | Central | 444
[5 empty] | 5.3.3.3 |  | Analysis datasets - ADAM format | 443 |  |  | 23 days | 2024-10-07 | 2024-10-11 | 2024-10-30 |  | In Progress | Draft in QC review | 700451 | Publishing prep | Alex Kim | R. Gupta | CSV | Analysis_datasets_ADAM_format_0451.csv | Sample entry for dashboard validation | Central | 445
[5 empty] | 5.3.3.3 |  | Data definition for analysis datasets - ADAM format (define file) | 444 |  |  | 22 days | 2024-10-01 | 2024-10-01 | 2024-10-23 | 2024-10-19 | Completed | QC completed | 700452 |  | Taylor Chen | A. Shah | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0452.xlsx | Timing estimate is illustrative | Central | 446
[5 empty] | 5.3.3.3 |  | Analysis Data Reviewers Guide | 445 |  |  | 25 days | 2024-10-05 | 2024-10-03 | 2024-10-30 | 2024-11-05 | Completed |  | 700453 | Submission build | Jamie Carter | N. Ortiz | CSV | Analysis_Data_Reviewers_Guide_0453.csv | Timing estimate is illustrative | Central | 447
[5 empty] | 5.3.3.3 |  | Analysis programs | 446 |  |  | 24 days | 2024-10-05 |  | 2024-10-29 |  | Not Started | Resource assignment not yet confirmed | 700454 |  | Casey Rivera | A. Shah | ZIP | Analysis_programs_0454.zip | Sample entry for dashboard validation | Central | 448
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p023mk0001 | 447 |  |  | 27 days | 2024-10-06 |  | 2024-11-02 |  | Not Started | Planned for upcoming wave | 700455 |  | Alex Kim | L. Bennett | DOCX | p023mk0001_0455.docx | Placeholder timeline for reporting test | Central | 449
[5 empty] | 5.3.3.4 |  | Study report [p023mk0001] and related information | 448 |  |  | 18 days | 2024-10-09 | 2024-10-10 | 2024-10-27 |  | In Progress | Pending cross-functional signoff | 700456 |  | Morgan Lee | A. Shah | PDF | Study_report_p023mk0001_and_related_information_0456.pdf | Dummy data added for planning demo | Central | 450
[5 empty] | 5.3.3.4 |  | Case Report Forms - CRF FOLDER p023mk0001 | 449 |  |  | 9 days | 2024-10-07 | 2024-10-05 | 2024-10-16 | 2024-10-14 | Completed |  | 700457 | Archive release | Casey Rivera | N. Ortiz | DOCX | Case_Report_Forms_CRF_FOLDER_p023mk0001_0457.docx | Placeholder timeline for reporting test | Central | 451
[5 empty] | 5.3.3.4 |  | Listing of Case Report Forms (CRFs TOC) | 450 |  |  | 31 days | 2024-10-08 | 2024-10-10 | 2024-11-08 |  | In Progress | Awaiting final source document | 700458 | Publishing prep | Morgan Lee | N. Ortiz | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_0458.csv | Placeholder timeline for reporting test | Central | 452
[5 empty] | 5.3.3.4 |  | Case Report Forms - eCRFs (by site) for US | 451 |  |  | 29 days | 2024-10-05 | 2024-10-02 | 2024-11-03 | 2024-11-08 | Completed | Released to archive | 700459 | Publishing QC | Alex Kim | N. Ortiz | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0459.docx | Sample entry for dashboard validation | Central | 453
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p023mk0001 | 452 |  |  | 24 days | 2024-10-11 | 2024-10-09 | 2024-11-04 | 2024-11-08 | Completed | Completed as planned | 700460 |  | Sam Brooks | A. Shah | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_0460.csv | Sample entry for dashboard validation | Central | 454
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 453 |  |  | 19 days | 2024-10-11 | 2024-10-08 | 2024-10-30 | 2024-10-27 | Completed | Released to archive | 700461 | Archive release | Jordan Patel | L. Bennett | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_0461.xlsx | Timing estimate is illustrative | Central | 455
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 454 |  |  | 31 days | 2024-10-06 | 2024-10-08 | 2024-11-06 | 2024-11-05 | Completed | Completed as planned | 700462 |  | Sam Brooks | R. Gupta | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_0462.zip | Timing estimate is illustrative | Central | 456
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 455 |  |  | 22 days | 2024-10-10 |  | 2024-11-01 |  | Not Started | Planned for upcoming wave | 700463 |  | Morgan Lee | L. Bennett | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0463.pdf | Dummy data added for planning demo | Central | 457
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p023mk0001 | 456 |  |  | 33 days | 2024-10-10 | 2024-10-09 | 2024-11-12 |  | In Progress | Metadata check in progress | 700464 |  | Taylor Chen | L. Bennett | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p023mk0001_0464.xlsx | Timing estimate is illustrative | Central | 458
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 457 |  |  | 9 days | 2024-10-10 | 2024-10-09 | 2024-10-19 |  | In Progress | Awaiting final source document | 700465 | Publishing prep | Taylor Chen | N. Ortiz | ZIP | Analysis_datasets_ADAM_format_0465.zip | Placeholder timeline for reporting test | Central | 459
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 458 |  |  | 34 days | 2024-10-12 | 2024-10-18 | 2024-11-15 |  | In Progress | Pending cross-functional signoff | 700466 | Publishing prep | Sam Brooks | M. Sullivan | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0466.csv | Dummy data added for planning demo | Central | 460
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 459 |  |  | 27 days | 2024-10-15 | 2024-10-13 | 2024-11-11 |  | In Progress | Metadata check in progress | 700467 | Regional alignment | Jamie Carter | L. Bennett | CSV | Analysis_Data_Reviewers_Guide_0467.csv | Dummy data added for planning demo | Central | 461
[5 empty] | 5.3.3.4 |  | Analysis programs | 460 |  |  | 21 days | 2024-10-18 | 2024-10-23 | 2024-11-08 | 2024-11-04 | Completed | Filed in baseline wave | 700468 | Publishing QC | Morgan Lee | L. Bennett | TXT | Analysis_programs_0468.txt | Placeholder timeline for reporting test | Central | 462
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p024mk0001 | 461 |  |  | 19 days | 2024-10-10 | 2024-10-08 | 2024-10-29 | 2024-11-03 | Completed | Completed as planned | 700469 | Submission build | Sam Brooks | L. Bennett | PDF | p024mk0001_0469.pdf | Timing estimate is illustrative | Central | 463
[5 empty] | 5.3.3.4 |  | Study report [p024mk0001 ] and related information | 462 |  |  | 12 days | 2024-10-14 | 2024-10-12 | 2024-10-26 | 2024-11-01 | Completed | Completed as planned | 700470 | Publishing QC | Casey Rivera | L. Bennett | PDF | Study_report_p024mk0001_and_related_information_0470.pdf | Placeholder timeline for reporting test | Central | 464
[5 empty] | 5.3.3.4 |  | Case Report Forms - CRF FOLDER p024mk0001 | 463 |  |  | 14 days | 2024-10-16 | 2024-10-16 | 2024-10-30 | 2024-10-31 | Completed | Completed as planned | 700471 | Archive release | Taylor Chen | N. Ortiz | PDF | Case_Report_Forms_CRF_FOLDER_p024mk0001_0471.pdf | Sample entry for dashboard validation | Central | 465
[5 empty] | 5.3.3.4 |  | Listing of Case Report Forms (CRFs TOC) | 464 |  |  | 27 days | 2024-10-13 | 2024-10-11 | 2024-11-09 | 2024-11-06 | Completed | Completed as planned | 700472 | Publishing QC | Casey Rivera | R. Gupta | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_0472.zip | Dummy data added for planning demo | Central | 466
[5 empty] | 5.3.3.4 |  | Case Report Forms - eCRFs (by site) for US | 465 |  |  | 8 days | 2024-10-15 |  | 2024-10-23 |  | Not Started | Scheduled after current milestone | 700473 |  | Alex Kim | R. Gupta | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0473.docx | Dummy data added for planning demo | Central | 467
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p024mk0001 | 466 |  |  | 28 days | 2024-10-14 | 2024-10-11 | 2024-11-11 | 2024-11-11 | Completed | Released to archive | 700474 |  | Alex Kim | M. Sullivan | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_0474.csv | Timing estimate is illustrative | Central | 468
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 467 |  |  | 21 days | 2024-10-14 | 2024-10-17 | 2024-11-04 | 2024-11-09 | Completed |  | 700475 | Publishing QC | Morgan Lee | A. Shah | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_0475.csv | Placeholder timeline for reporting test | Central | 469
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 468 |  |  | 10 days | 2024-10-17 | 2024-10-15 | 2024-10-27 | 2024-11-01 | Completed | Filed in baseline wave | 700476 |  | Jordan Patel | M. Sullivan | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_0476.csv | Placeholder timeline for reporting test | Central | 470
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 469 |  |  | 22 days | 2024-10-21 | 2024-10-26 | 2024-11-12 |  | In Progress | Awaiting final source document | 700477 | QC review | Jordan Patel | A. Shah | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0477.pdf | Timing estimate is illustrative | Central | 471
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p024mk0001 | 470 |  |  | 25 days | 2024-10-20 | 2024-10-22 | 2024-11-14 | 2024-11-14 | Completed |  | 700478 |  | Jamie Carter | N. Ortiz | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p024mk0001_0478.xlsx | Sample entry for dashboard validation | Central | 472
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 471 |  |  | 26 days | 2024-10-20 | 2024-10-22 | 2024-11-15 | 2024-11-11 | Completed |  | 700479 |  | Sam Brooks | N. Ortiz | XLSX | Analysis_datasets_ADAM_format_0479.xlsx | Timing estimate is illustrative | Central | 473
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 472 |  |  | 33 days | 2024-10-25 | 2024-10-23 | 2024-11-27 |  | In Progress | Publishing build in progress | 700480 | Publishing prep | Jordan Patel | N. Ortiz | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0480.zip | Timing estimate is illustrative | Central | 474
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 473 |  |  | 17 days | 2024-10-18 | 2024-10-22 | 2024-11-04 | 2024-11-11 | Completed | Released to archive | 700481 |  | Sam Brooks | R. Gupta | ZIP | Analysis_Data_Reviewers_Guide_0481.zip | Placeholder timeline for reporting test | Central | 475
[5 empty] | 5.3.3.4 |  | Analysis programs | 474 |  |  | 20 days | 2024-10-22 | 2024-10-20 | 2024-11-11 | 2024-11-14 | Completed | Completed as planned | 700482 |  | Jordan Patel | A. Shah | ZIP | Analysis_programs_0482.zip | Timing estimate is illustrative | Central | 476
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p026mk0001 | 475 |  |  | 26 days | 2024-10-26 | 2024-10-30 | 2024-11-21 | 2024-11-28 | Completed | QC completed | 700483 |  | Jordan Patel | L. Bennett | PDF | p026mk0001_0483.pdf | Dummy data added for planning demo | Central | 477
[5 empty] | 5.3.3.4 |  | Study report [p026mk0001] and related information | 476 |  |  | 7 days | 2024-10-24 | 2024-10-21 | 2024-10-31 | 2024-11-04 | Completed | Completed as planned | 700484 | Submission build | Morgan Lee | L. Bennett | PDF | Study_report_p026mk0001_and_related_information_0484.pdf | Placeholder timeline for reporting test | Central | 478
[5 empty] | 5.3.3.4 |  | Case Report Forms - CRF FOLDER p026mk0001 | 477 |  |  | 7 days | 2024-10-20 | 2024-10-21 | 2024-10-27 | 2024-10-25 | Completed | Filed in baseline wave | 700485 | Archive release | Sam Brooks | N. Ortiz | DOCX | Case_Report_Forms_CRF_FOLDER_p026mk0001_0485.docx | Timing estimate is illustrative | Central | 479
[5 empty] | 5.3.3.4 |  | Listing of Case Report Forms (CRFs TOC) | 478 |  |  | 13 days | 2024-10-22 | 2024-10-23 | 2024-11-04 | 2024-11-01 | Completed | Completed as planned | 700486 | Submission build | Casey Rivera | A. Shah | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_0486.csv | Timing estimate is illustrative | Central | 480
[5 empty] | 5.3.3.4 |  | Case Report Forms - eCRFs (by site) for US | 479 |  |  | 21 days | 2024-10-25 | 2024-10-27 | 2024-11-15 | 2024-11-21 | Completed | Filed in baseline wave | 700487 |  | Jamie Carter | M. Sullivan | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0487.docx | Dummy data added for planning demo | Central | 481
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p026mk0001 | 480 |  |  | 11 days | 2024-10-22 | 2024-10-22 | 2024-11-02 |  | In Progress | Awaiting final source document | 700488 | QC review | Taylor Chen | L. Bennett | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_0488.zip | Placeholder timeline for reporting test | Central | 482
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 481 |  |  | 26 days | 2024-10-27 | 2024-10-27 | 2024-11-22 | 2024-11-18 | Completed |  | 700489 |  | Jordan Patel | M. Sullivan | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_0489.csv | Timing estimate is illustrative | Central | 483
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 482 |  |  | 14 days | 2024-10-28 | 2024-10-29 | 2024-11-11 | 2024-11-09 | Completed |  | 700490 |  | Casey Rivera | N. Ortiz | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_0490.zip | Dummy data added for planning demo | Central | 484
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 483 |  |  | 32 days | 2024-10-30 | 2024-10-29 | 2024-12-01 |  | In Progress | Awaiting final source document | 700491 |  | Casey Rivera | M. Sullivan | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0491.docx | Sample entry for dashboard validation | Central | 485
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p026mk0001 | 484 |  |  | 21 days | 2024-11-01 | 2024-11-03 | 2024-11-22 | 2024-11-26 | Completed | Released to archive | 700492 |  | Casey Rivera | R. Gupta | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p026mk0001_0492.zip | Sample entry for dashboard validation | Central | 486
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 485 |  |  | 13 days | 2024-10-24 | 2024-10-24 | 2024-11-06 | 2024-11-09 | Completed | Filed in baseline wave | 700493 |  | Jordan Patel | R. Gupta | CSV | Analysis_datasets_ADAM_format_0493.csv | Sample entry for dashboard validation | Central | 487
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 486 |  |  | 33 days | 2024-10-27 | 2024-11-01 | 2024-11-29 | 2024-11-26 | Completed | Filed in baseline wave | 700494 | Publishing QC | Morgan Lee | L. Bennett | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0494.zip | Placeholder timeline for reporting test | Central | 488
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 487 |  |  | 25 days | 2024-10-29 | 2024-11-03 | 2024-11-23 | 2024-11-28 | Completed | QC completed | 700495 |  | Casey Rivera | L. Bennett | CSV | Analysis_Data_Reviewers_Guide_0495.csv | Sample entry for dashboard validation | Central | 489
[5 empty] | 5.3.3.4 |  | Analysis programs | 488 |  |  | 32 days | 2024-10-31 | 2024-11-01 | 2024-12-02 | 2024-12-04 | Completed | Completed as planned | 700496 | Submission build | Casey Rivera | N. Ortiz | TXT | Analysis_programs_0496.txt | Dummy data added for planning demo | Central | 490
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p027mk0001 | 489 |  |  | 35 days | 2024-11-01 | 2024-11-06 | 2024-12-06 | 2024-12-10 | Completed |  | 700497 | Publishing QC | Jamie Carter | R. Gupta | PDF | p027mk0001_0497.pdf | Dummy data added for planning demo | Central | 491
[5 empty] | 5.3.3.4 |  | Study report [p027mk0001] and related information | 490 |  |  | 9 days | 2024-10-28 | 2024-11-02 | 2024-11-06 | 2024-11-05 | Completed | QC completed | 700498 | Submission build | Sam Brooks | R. Gupta | DOCX | Study_report_p027mk0001_and_related_information_0498.docx | Placeholder timeline for reporting test | Central | 492
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p027mk0001 | 491 |  |  | 13 days | 2024-11-01 | 2024-11-01 | 2024-11-14 |  | In Progress | Regional review underway | 700499 |  | Morgan Lee | A. Shah | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_0499.csv | Placeholder timeline for reporting test | Central | 493
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 492 |  |  | 32 days | 2024-11-02 |  | 2024-12-04 |  | Not Started | Scheduled after current milestone | 700500 |  | Jamie Carter | M. Sullivan | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_0500.zip | Dummy data added for planning demo | Central | 494
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 493 |  |  | 27 days | 2024-11-05 | 2024-11-04 | 2024-12-02 | 2024-12-04 | Completed | Filed in baseline wave | 700501 | Submission build | Sam Brooks | N. Ortiz | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_0501.csv | Timing estimate is illustrative | Central | 495
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 494 |  |  | 25 days | 2024-11-07 | 2024-11-12 | 2024-12-02 |  | In Progress | Regional review underway | 700502 | Regional alignment | Morgan Lee | A. Shah | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0502.docx | Timing estimate is illustrative | Central | 496
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p027mk0001 | 495 |  |  | 31 days | 2024-11-05 |  | 2024-12-06 |  | Not Started | Scheduled after current milestone | 700503 |  | Jordan Patel | L. Bennett | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p027mk0001_0503.csv | Dummy data added for planning demo | Central | 497
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 496 |  |  | 11 days | 2024-11-05 | 2024-11-05 | 2024-11-16 |  | In Progress | Metadata check in progress | 700504 | Authoring | Casey Rivera | R. Gupta | CSV | Analysis_datasets_ADAM_format_0504.csv | Timing estimate is illustrative | Central | 498
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 497 |  |  | 20 days | 2024-11-06 | 2024-11-10 | 2024-11-26 |  | In Progress | Regional review underway | 700505 |  | Morgan Lee | R. Gupta | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0505.zip | Dummy data added for planning demo | Central | 499
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 498 |  |  | 11 days | 2024-11-01 | 2024-11-03 | 2024-11-12 | 2024-11-17 | Completed |  | 700506 |  | Taylor Chen | L. Bennett | CSV | Analysis_Data_Reviewers_Guide_0506.csv | Timing estimate is illustrative | Central | 500
[5 empty] | 5.3.3.4 |  | Analysis programs | 499 |  |  | 9 days | 2024-11-08 | 2024-11-08 | 2024-11-17 | 2024-11-20 | Completed | Completed as planned | 700507 | Archive release | Taylor Chen | L. Bennett | TXT | Analysis_programs_0507.txt | Dummy data added for planning demo | Central | 501
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p028mk0001 | 500 |  |  | 10 days | 2024-11-04 | 2024-11-04 | 2024-11-14 |  | In Progress | Draft in QC review | 700508 |  | Casey Rivera | A. Shah | PDF | p028mk0001_0508.pdf | Timing estimate is illustrative | Central | 502
[5 empty] | 5.3.3.4 |  | Study report [p028mk0001] and related information | 501 |  |  | 19 days | 2024-11-04 | 2024-11-04 | 2024-11-23 | 2024-11-23 | Completed |  | 700509 | Publishing QC | Casey Rivera | A. Shah | DOCX | Study_report_p028mk0001_and_related_information_0509.docx | Dummy data added for planning demo | Central | 503
[5 empty] | 5.3.3.4 |  | Case Report Forms - CRF FOLDER p028mk0001 | 502 |  |  | 17 days | 2024-11-05 | 2024-11-09 | 2024-11-22 |  | In Progress | Publishing build in progress | 700510 | QC review | Alex Kim | N. Ortiz | DOCX | Case_Report_Forms_CRF_FOLDER_p028mk0001_0510.docx | Sample entry for dashboard validation | Central | 504
[5 empty] | 5.3.3.4 |  | Listing of Case Report Forms (CRFs TOC) | 503 |  |  | 19 days | 2024-11-05 |  | 2024-11-24 |  | Not Started | Pending authoring start | 700511 |  | Jordan Patel | N. Ortiz | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_0511.csv | Sample entry for dashboard validation | Central | 505
[5 empty] | 5.3.3.4 |  | Case Report Forms - eCRFs (by site) for US | 504 |  |  | 12 days | 2024-11-11 | 2024-11-13 | 2024-11-23 |  | In Progress | Pending cross-functional signoff | 700512 | QC review | Taylor Chen | L. Bennett | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0512.docx | Timing estimate is illustrative | Central | 506
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p028mk0001 | 505 |  |  | 11 days | 2024-11-05 | 2024-11-08 | 2024-11-16 | 2024-11-21 | Completed | Filed in baseline wave | 700513 |  | Morgan Lee | M. Sullivan | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_0513.csv | Sample entry for dashboard validation | Central | 507
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 506 |  |  | 25 days | 2024-11-13 | 2024-11-11 | 2024-12-08 | 2024-12-08 | Completed | Released to archive | 700514 | Archive release | Sam Brooks | R. Gupta | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_0514.csv | Timing estimate is illustrative | Central | 508
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 507 |  |  | 14 days | 2024-11-12 | 2024-11-15 | 2024-11-26 | 2024-11-29 | Completed | Released to archive | 700515 | Submission build | Sam Brooks | M. Sullivan | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_0515.xlsx | Sample entry for dashboard validation | Central | 509
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 508 |  |  | 14 days | 2024-11-07 | 2024-11-07 | 2024-11-21 |  | In Progress | Metadata check in progress | 700516 |  | Morgan Lee | A. Shah | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0516.pdf | Sample entry for dashboard validation | Central | 510
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p028mk0001 | 509 |  |  | 31 days | 2024-11-13 | 2024-11-16 | 2024-12-14 |  | In Progress | Draft in QC review | 700517 | Authoring | Taylor Chen | R. Gupta | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p028mk0001_0517.csv | Sample entry for dashboard validation | Central | 511
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 510 |  |  | 15 days | 2024-11-10 | 2024-11-07 | 2024-11-25 | 2024-11-28 | Completed | Completed as planned | 700518 | Publishing QC | Sam Brooks | L. Bennett | CSV | Analysis_datasets_ADAM_format_0518.csv | Placeholder timeline for reporting test | Central | 512
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 511 |  |  | 34 days | 2024-11-15 | 2024-11-12 | 2024-12-19 | 2024-12-15 | Completed | QC completed | 700519 | Publishing QC | Sam Brooks | N. Ortiz | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0519.csv | Sample entry for dashboard validation | Central | 513
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 512 |  |  | 21 days | 2024-11-16 | 2024-11-21 | 2024-12-07 | 2024-12-13 | Completed | Filed in baseline wave | 700520 |  | Jordan Patel | L. Bennett | CSV | Analysis_Data_Reviewers_Guide_0520.csv | Timing estimate is illustrative | Central | 514
[5 empty] | 5.3.3.4 |  | Analysis programs | 513 |  |  | 33 days | 2024-11-12 | 2024-11-10 | 2024-12-15 | 2024-12-13 | Completed | QC completed | 700521 | Publishing QC | Taylor Chen | L. Bennett | ZIP | Analysis_programs_0521.zip | Dummy data added for planning demo | Central | 515
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p031mk0001 | 514 |  |  | 28 days | 2024-11-10 | 2024-11-14 | 2024-12-08 | 2024-12-09 | Completed | Filed in baseline wave | 700522 | Submission build | Sam Brooks | A. Shah | XLSX | p031mk0001_0522.xlsx | Timing estimate is illustrative | Central | 516
[5 empty] | 5.3.3.4 |  | Study report [p031mk0001] and related information | 515 |  |  | 29 days | 2024-11-18 | 2024-11-23 | 2024-12-17 | 2024-12-23 | Completed | Completed as planned | 700523 |  | Sam Brooks | R. Gupta | DOCX | Study_report_p031mk0001_and_related_information_0523.docx | Dummy data added for planning demo | Central | 517
[5 empty] | 5.3.3.4 |  | Case Report Forms - CRF FOLDER p031mk0001 | 516 |  |  | 8 days | 2024-11-12 | 2024-11-13 | 2024-11-20 |  | In Progress | Awaiting final source document | 700524 | Publishing prep | Jordan Patel | N. Ortiz | PDF | Case_Report_Forms_CRF_FOLDER_p031mk0001_0524.pdf | Dummy data added for planning demo | Central | 518
[5 empty] | 5.3.3.4 |  | Listing of Case Report Forms (CRFs TOC) | 517 |  |  | 7 days | 2024-11-18 |  | 2024-11-25 |  | Not Started | Waiting on dependency from Module 3 | 700525 |  | Jamie Carter | N. Ortiz | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_0525.zip | Dummy data added for planning demo | Central | 519
[5 empty] | 5.3.3.4 |  | Case Report Forms - eCRFs (by site) for US | 518 |  |  | 35 days | 2024-11-16 | 2024-11-15 | 2024-12-21 | 2024-12-28 | Completed | Filed in baseline wave | 700526 | Publishing QC | Casey Rivera | M. Sullivan | PDF | Case_Report_Forms_eCRFs_by_site_for_US_0526.pdf | Placeholder timeline for reporting test | Central | 520
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p031mk0001 | 519 |  |  | 24 days | 2024-11-18 | 2024-11-19 | 2024-12-12 |  | In Progress | Pending cross-functional signoff | 700527 | Regional alignment | Casey Rivera | A. Shah | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p03_0527.xlsx | Timing estimate is illustrative | Central | 521
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 520 |  |  | 18 days | 2024-11-15 | 2024-11-12 | 2024-12-03 | 2024-12-05 | Completed | QC completed | 700528 | Publishing QC | Casey Rivera | N. Ortiz | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_0528.csv | Timing estimate is illustrative | Central | 522
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 521 |  |  | 28 days | 2024-11-15 | 2024-11-18 | 2024-12-13 |  | In Progress | Draft in QC review | 700529 | Authoring | Jordan Patel | L. Bennett | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_0529.csv | Sample entry for dashboard validation | Central | 523
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 522 |  |  | 29 days | 2024-11-16 | 2024-11-15 | 2024-12-15 | 2024-12-15 | Completed | Completed as planned | 700530 |  | Morgan Lee | L. Bennett | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0530.pdf | Placeholder timeline for reporting test | Central | 524
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p031mk0001 | 523 |  |  | 27 days | 2024-11-18 | 2024-11-21 | 2024-12-15 |  | In Progress | Regional review underway | 700531 | Regional alignment | Alex Kim | R. Gupta | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p031mk0001_0531.xlsx | Sample entry for dashboard validation | Central | 525
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 524 |  |  | 23 days | 2024-11-22 | 2024-11-23 | 2024-12-15 |  | In Progress | Pending cross-functional signoff | 700532 |  | Sam Brooks | A. Shah | XLSX | Analysis_datasets_ADAM_format_0532.xlsx | Dummy data added for planning demo | Central | 526
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 525 |  |  | 16 days | 2024-11-18 | 2024-11-21 | 2024-12-04 | 2024-12-03 | Completed |  | 700533 | Publishing QC | Alex Kim | N. Ortiz | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0533.csv | Sample entry for dashboard validation | Central | 527
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 526 |  |  | 13 days | 2024-11-21 | 2024-11-21 | 2024-12-04 | 2024-12-10 | Completed | Completed as planned | 700534 | Submission build | Sam Brooks | M. Sullivan | CSV | Analysis_Data_Reviewers_Guide_0534.csv | Placeholder timeline for reporting test | Central | 528
[5 empty] | 5.3.3.4 |  | Analysis programs | 527 |  |  | 15 days | 2024-11-20 | 2024-11-17 | 2024-12-05 | 2024-12-09 | Completed | Released to archive | 700535 | Archive release | Jamie Carter | A. Shah | ZIP | Analysis_programs_0535.zip | Placeholder timeline for reporting test | Central | 529
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p034mk0001 | 528 |  |  | 14 days | 2024-11-24 | 2024-11-21 | 2024-12-08 | 2024-12-14 | Completed | Filed in baseline wave | 700536 | Submission build | Taylor Chen | L. Bennett | XLSX | p034mk0001_0536.xlsx | Placeholder timeline for reporting test | Central | 530
[5 empty] | 5.3.3.4 |  | Study report [p034mk0001] and related information | 529 |  |  | 21 days | 2024-11-21 | 2024-11-20 | 2024-12-12 |  | In Progress | Publishing build in progress | 700537 | Authoring | Jordan Patel | A. Shah | PDF | Study_report_p034mk0001_and_related_information_0537.pdf | Timing estimate is illustrative | Central | 531
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p034mk0001 | 530 |  |  | 9 days | 2024-11-22 | 2024-11-27 | 2024-12-01 | 2024-11-30 | Completed | Filed in baseline wave | 700538 |  | Alex Kim | L. Bennett | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p03_0538.zip | Sample entry for dashboard validation | Central | 532
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 531 |  |  | 12 days | 2024-11-24 | 2024-11-25 | 2024-12-06 |  | In Progress | Publishing build in progress | 700539 | QC review | Taylor Chen | N. Ortiz | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_0539.csv | Placeholder timeline for reporting test | Central | 533
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 532 |  |  | 27 days | 2024-11-28 | 2024-12-02 | 2024-12-25 | 2024-12-22 | Completed | QC completed | 700540 |  | Casey Rivera | N. Ortiz | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_0540.csv | Sample entry for dashboard validation | Central | 534
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 533 |  |  | 23 days | 2024-11-27 | 2024-12-01 | 2024-12-20 |  | In Progress | Awaiting final source document | 700541 | Regional alignment | Alex Kim | L. Bennett | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0541.docx | Dummy data added for planning demo | Central | 535
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p034mk0001 | 534 |  |  | 26 days | 2024-11-26 | 2024-12-01 | 2024-12-22 | 2024-12-29 | Completed | Filed in baseline wave | 700542 | Archive release | Casey Rivera | L. Bennett | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p034mk0001_0542.csv | Sample entry for dashboard validation | Central | 536
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 535 |  |  | 19 days | 2024-11-27 | 2024-12-02 | 2024-12-16 |  | In Progress | Draft in QC review | 700543 | Publishing prep | Jordan Patel | L. Bennett | XLSX | Analysis_datasets_ADAM_format_0543.xlsx | Timing estimate is illustrative | Central | 537
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 536 |  |  | 7 days | 2024-11-26 | 2024-12-01 | 2024-12-03 | 2024-12-10 | Completed | QC completed | 700544 |  | Casey Rivera | L. Bennett | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0544.csv | Placeholder timeline for reporting test | Central | 538
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 537 |  |  | 22 days | 2024-11-30 | 2024-11-28 | 2024-12-22 | 2024-12-24 | Completed | Completed as planned | 700545 | Publishing QC | Casey Rivera | M. Sullivan | XLSX | Analysis_Data_Reviewers_Guide_0545.xlsx | Timing estimate is illustrative | Central | 539
[5 empty] | 5.3.3.4 |  | Analysis programs | 538 |  |  | 15 days | 2024-11-30 | 2024-12-03 | 2024-12-15 |  | In Progress | Pending cross-functional signoff | 700546 | Regional alignment | Sam Brooks | R. Gupta | ZIP | Analysis_programs_0546.zip | Sample entry for dashboard validation | Central | 540
[5 empty] | 5.3.5 |  | 5.3.5 Reports of efficacy and safety studies [hypercholest] | 539 |  |  | 67 days | 2024-12-01 | 2024-12-05 | 2025-02-06 | 2025-02-02 | Completed | QC completed | 700547 | Publishing QC | Sam Brooks | N. Ortiz | DOCX | Reports_of_efficacy_and_safety_studies_hypercholest_0547.docx | Sample entry for dashboard validation | Central | 541
[5 empty] | 5.3.5.1 |  | 5.3.5.1 p008mk0001 Study reports and related information of controlled clinical studies pertinent to the claimed indication [placebo] | 540 |  |  | 15 days | 2024-11-28 | 2024-11-27 | 2024-12-13 | 2024-12-09 | Completed | Completed as planned | 700548 | Publishing QC | Sam Brooks | L. Bennett | DOCX | p008mk0001_Study_reports_and_related_information_of_controll_0548.docx | Dummy data added for planning demo | Central | 542
[5 empty] | 5.3.5.1 |  | Study report [p008mk0001] and related information | 541 |  |  | 13 days | 2024-12-04 | 2024-12-04 | 2024-12-17 |  | In Progress | Publishing build in progress | 700549 | Publishing prep | Sam Brooks | R. Gupta | DOCX | Study_report_p008mk0001_and_related_information_0549.docx | Placeholder timeline for reporting test | Central | 543
[5 empty] | 5.3.5.1 |  | Clinical Study Report | 542 |  |  | 31 days | 2024-12-03 | 2024-12-02 | 2025-01-03 |  | In Progress | Draft in QC review | 700550 |  | Jamie Carter | R. Gupta | PDF | Clinical_Study_Report_0550.pdf | Placeholder timeline for reporting test | Central | 544
[5 empty] | 5.3.5.1 |  | Case Report Forms - CRF FOLDER p008mk0001 | 543 |  |  | 30 days | 2024-11-30 | 2024-12-01 | 2024-12-30 | 2024-12-26 | Completed | Filed in baseline wave | 700551 |  | Alex Kim | A. Shah | PDF | Case_Report_Forms_CRF_FOLDER_p008mk0001_0551.pdf | Sample entry for dashboard validation | Central | 545
[5 empty] | 5.3.5.1 |  | Listing of Case Report Forms (CRFs TOC) | 544 |  |  | 20 days | 2024-12-06 | 2024-12-10 | 2024-12-26 |  | In Progress | Awaiting final source document | 700552 | QC review | Morgan Lee | N. Ortiz | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_0552.zip | Timing estimate is illustrative | Central | 546
[5 empty] | 5.3.5.1 |  | Case Report Forms - eCRFs (by site) for US | 545 |  |  | 22 days | 2024-12-01 | 2024-11-29 | 2024-12-23 | 2024-12-26 | Completed |  | 700553 | Submission build | Jordan Patel | N. Ortiz | PDF | Case_Report_Forms_eCRFs_by_site_for_US_0553.pdf | Timing estimate is illustrative | Central | 547
[5 empty] | 5.3.5.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p008mk0001 | 546 |  |  | 15 days | 2024-12-02 |  | 2024-12-17 |  | Not Started | Scheduled after current milestone | 700554 |  | Casey Rivera | M. Sullivan | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_0554.xlsx | Timing estimate is illustrative | Central | 548
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 547 |  |  | 16 days | 2024-12-01 | 2024-11-29 | 2024-12-17 | 2024-12-17 | Completed | Completed as planned | 700555 | Archive release | Alex Kim | M. Sullivan | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_0555.xlsx | Sample entry for dashboard validation | Central | 549
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 548 |  |  | 28 days | 2024-12-07 | 2024-12-05 | 2025-01-04 |  | In Progress | Draft in QC review | 700556 | Publishing prep | Jamie Carter | A. Shah | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_0556.zip | Dummy data added for planning demo | Central | 550
[5 empty] | 5.3.5.1 |  | Study Data Reviewers Guide | 549 |  |  | 13 days | 2024-12-02 | 2024-11-29 | 2024-12-15 | 2024-12-17 | Completed |  | 700557 |  | Jamie Carter | R. Gupta | DOCX | Study_Data_Reviewers_Guide_0557.docx | Sample entry for dashboard validation | Central | 551
[5 empty] | 5.3.5.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 550 |  |  | 26 days | 2024-12-06 | 2024-12-08 | 2025-01-01 | 2025-01-07 | Completed | QC completed | 700558 | Archive release | Jamie Carter | N. Ortiz | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0558.docx | Sample entry for dashboard validation | Central | 552
[5 empty] | 5.3.5.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p008mk0001 | 551 |  |  | 26 days | 2024-12-08 | 2024-12-10 | 2025-01-03 | 2025-01-04 | Completed | Completed as planned | 700559 | Publishing QC | Casey Rivera | L. Bennett | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p008mk0001_0559.zip | Timing estimate is illustrative | Central | 553
[5 empty] | 5.3.5.1 |  | Analysis datasets - ADAM format | 552 |  |  | 26 days | 2024-12-03 | 2024-12-08 | 2024-12-29 | 2024-12-29 | Completed | Filed in baseline wave | 700560 | Archive release | Casey Rivera | M. Sullivan | ZIP | Analysis_datasets_ADAM_format_0560.zip | Sample entry for dashboard validation | Central | 554
[5 empty] | 5.3.5.1 |  | Data definition for analysis datasets - ADAM format (define file) | 553 |  |  | 20 days | 2024-12-11 | 2024-12-09 | 2024-12-31 |  | In Progress | Regional review underway | 700561 | Publishing prep | Alex Kim | R. Gupta | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0561.xlsx | Placeholder timeline for reporting test | Central | 555
[5 empty] | 5.3.5.1 |  | Analysis Data Reviewers Guide | 554 |  |  | 14 days | 2024-12-11 | 2024-12-15 | 2024-12-25 |  | In Progress | Regional review underway | 700562 |  | Jamie Carter | A. Shah | CSV | Analysis_Data_Reviewers_Guide_0562.csv | Sample entry for dashboard validation | Central | 556
[5 empty] | 5.3.5.1 |  | Analysis results Metadata (ARM) | 555 |  |  | 28 days | 2024-12-11 | 2024-12-10 | 2025-01-08 |  | In Progress | Regional review underway | 700563 | Regional alignment | Morgan Lee | M. Sullivan | PDF | Analysis_results_Metadata_ARM_0563.pdf | Timing estimate is illustrative | Central | 557
[5 empty] | 5.3.5.1 |  | Analysis programs | 556 |  |  | 35 days | 2024-12-13 | 2024-12-19 | 2025-01-17 |  | In Progress | Draft in QC review | 700564 | QC review | Casey Rivera | A. Shah | TXT | Analysis_programs_0564.txt | Sample entry for dashboard validation | Central | 558
[5 empty] | 5.3.5.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER P008SUPPmk0001 | 557 |  |  | 35 days | 2024-12-07 | 2024-12-05 | 2025-01-11 | 2025-01-14 | Completed |  | 700565 | Submission build | Jordan Patel | N. Ortiz | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_P00_0565.xlsx | Dummy data added for planning demo | Central | 559
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data tabulation datasets - SDTM/Legacy format | 558 |  |  | 20 days | 2024-12-07 |  | 2024-12-27 |  | Not Started | Planned for upcoming wave | 700566 |  | Jordan Patel | R. Gupta | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_0566.csv | Placeholder timeline for reporting test | Central | 560
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM/Legacy format (define.xml/define.pdf file) | 559 |  |  | 30 days | 2024-12-10 | 2024-12-14 | 2025-01-09 | 2025-01-15 | Completed | Completed as planned | 700567 | Submission build | Taylor Chen | L. Bennett | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_0567.xlsx | Placeholder timeline for reporting test | Central | 561
[5 empty] | 5.3.5.1 |  | Clinical Study Data Reviewers Guide (csdrg.pdf) | 560 |  |  | 25 days | 2024-12-10 | 2024-12-09 | 2025-01-04 |  | In Progress | Regional review underway | 700568 | Publishing prep | Casey Rivera | L. Bennett | DOCX | Clinical_Study_Data_Reviewers_Guide_csdrg_pdf_0568.docx | Timing estimate is illustrative | Central | 562
[5 empty] | 5.3.5.1 |  | Annotated Case Report Forms (CRFs) (acrf.pdf) | 561 |  |  | 15 days | 2024-12-11 | 2024-12-09 | 2024-12-26 | 2024-12-23 | Completed | Completed as planned | 700569 | Archive release | Sam Brooks | M. Sullivan | PDF | Annotated_Case_Report_Forms_CRFs_acrf_pdf_0569.pdf | Dummy data added for planning demo | Central | 563
[5 empty] | 5.3.5.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER P008SUPPmk0001 | 562 |  |  | 11 days | 2024-12-13 | 2024-12-17 | 2024-12-24 |  | In Progress | Pending cross-functional signoff | 700570 | Authoring | Morgan Lee | A. Shah | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_P008SUPPmk00_0570.zip | Timing estimate is illustrative | Central | 564
[5 empty] | 5.3.5.1 |  | Analysis datasets - ADAM format | 563 |  |  | 20 days | 2024-12-15 | 2024-12-17 | 2025-01-04 | 2025-01-10 | Completed | Filed in baseline wave | 700571 |  | Sam Brooks | M. Sullivan | ZIP | Analysis_datasets_ADAM_format_0571.zip | Timing estimate is illustrative | Central | 565
[5 empty] | 5.3.5.1 |  | Data definition for analysis datasets - ADAM format (define file) | 564 |  |  | 19 days | 2024-12-11 | 2024-12-15 | 2024-12-30 | 2024-12-31 | Completed | Filed in baseline wave | 700572 | Archive release | Jamie Carter | N. Ortiz | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0572.csv | Sample entry for dashboard validation | Central | 566
[5 empty] | 5.3.5.1 |  | Analysis Data Reviewers Guide | 565 |  |  | 26 days | 2024-12-12 | 2024-12-09 | 2025-01-07 | 2025-01-12 | Completed | QC completed | 700573 | Archive release | Taylor Chen | A. Shah | CSV | Analysis_Data_Reviewers_Guide_0573.csv | Sample entry for dashboard validation | Central | 567
[5 empty] | 5.3.5.1 |  | Analysis programs | 566 |  |  | 22 days | 2024-12-14 | 2024-12-17 | 2025-01-05 | 2025-01-01 | Completed | QC completed | 700574 | Submission build | Jamie Carter | N. Ortiz | ZIP | Analysis_programs_0574.zip | Dummy data added for planning demo | Central | 568
[5 empty] | 5.3.5.1 |  | 5.3.5.1 p013mk0001 Study reports and related information of controlled clinical studies pertinent to the claimed indication [placebo] | 567 |  |  | 34 days | 2024-12-13 | 2024-12-16 | 2025-01-16 | 2025-01-16 | Completed | Filed in baseline wave | 700575 | Publishing QC | Taylor Chen | L. Bennett | DOCX | p013mk0001_Study_reports_and_related_information_of_controll_0575.docx | Sample entry for dashboard validation | Central | 569
[5 empty] | 5.3.5.1 |  | Study report [p013mk0001] and related information | 568 |  |  | 18 days | 2024-12-19 | 2024-12-23 | 2025-01-06 |  | In Progress | Draft in QC review | 700576 |  | Sam Brooks | R. Gupta | DOCX | Study_report_p013mk0001_and_related_information_0576.docx | Timing estimate is illustrative | Central | 570
[5 empty] | 5.3.5.1 |  | P013 SAP | 569 |  |  | 19 days | 2024-12-20 | 2024-12-22 | 2025-01-08 | 2025-01-13 | Completed | Completed as planned | 700577 | Archive release | Casey Rivera | N. Ortiz | XLSX | P013_SAP_0577.xlsx | Timing estimate is illustrative | Central | 571
[5 empty] | 5.3.5.1 |  | Clinical Study Report | 570 |  |  | 29 days | 2024-12-20 | 2024-12-19 | 2025-01-18 | 2025-01-17 | Completed | Filed in baseline wave | 700578 | Submission build | Sam Brooks | A. Shah | DOCX | Clinical_Study_Report_0578.docx | Dummy data added for planning demo | Central | 572
[5 empty] | 5.3.5.1 |  | Case Report Forms - CRF FOLDER p013mk0001 | 571 |  |  | 19 days | 2024-12-16 |  | 2025-01-04 |  | Not Started | Scheduled after current milestone | 700579 |  | Sam Brooks | N. Ortiz | PDF | Case_Report_Forms_CRF_FOLDER_p013mk0001_0579.pdf | Dummy data added for planning demo | Central | 573
[5 empty] | 5.3.5.1 |  | Listing of Case Report Forms (CRFs TOC) | 572 |  |  | 22 days | 2024-12-19 | 2024-12-16 | 2025-01-10 | 2025-01-07 | Completed |  | 700580 | Archive release | Taylor Chen | L. Bennett | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_0580.xlsx | Sample entry for dashboard validation | Central | 574
[5 empty] | 5.3.5.1 |  | Case Report Forms - eCRFs (by site) for US | 573 |  |  | 8 days | 2024-12-18 | 2024-12-21 | 2024-12-26 | 2024-12-29 | Completed | QC completed | 700581 |  | Jordan Patel | L. Bennett | PDF | Case_Report_Forms_eCRFs_by_site_for_US_0581.pdf | Sample entry for dashboard validation | Central | 575
[5 empty] | 5.3.5.1 |  | Adjudication Packages (if applicable) | 574 |  |  | 15 days | 2024-12-21 | 2024-12-26 | 2025-01-05 |  | In Progress | Metadata check in progress | 700582 | Authoring | Alex Kim | A. Shah | PDF | Adjudication_Packages_if_applicable_0582.pdf | Dummy data added for planning demo | Central | 576
[5 empty] | 5.3.5.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p013mk0001 | 575 |  |  | 27 days | 2024-12-23 | 2024-12-29 | 2025-01-19 |  | In Progress | Awaiting final source document | 700583 | Authoring | Taylor Chen | M. Sullivan | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_0583.zip | Sample entry for dashboard validation | Central | 577
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 576 |  |  | 29 days | 2024-12-21 | 2024-12-21 | 2025-01-19 |  | In Progress | Publishing build in progress | 700584 | Regional alignment | Sam Brooks | L. Bennett | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_0584.csv | Timing estimate is illustrative | Central | 578
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 577 |  |  | 17 days | 2024-12-18 | 2024-12-23 | 2025-01-04 | 2025-01-02 | Completed | Released to archive | 700585 | Publishing QC | Casey Rivera | M. Sullivan | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_0585.zip | Sample entry for dashboard validation | Central | 579
[5 empty] | 5.3.5.1 |  | Study Data Reviewers Guide | 578 |  |  | 23 days | 2024-12-19 | 2024-12-25 | 2025-01-11 |  | In Progress | Regional review underway | 700586 | Authoring | Jamie Carter | N. Ortiz | PDF | Study_Data_Reviewers_Guide_0586.pdf | Timing estimate is illustrative | Central | 580
[5 empty] | 5.3.5.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 579 |  |  | 7 days | 2024-12-20 | 2024-12-23 | 2024-12-27 |  | In Progress | Draft in QC review | 700587 | Authoring | Jordan Patel | M. Sullivan | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0587.pdf | Timing estimate is illustrative | Central | 581
[5 empty] | 5.3.5.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p013mk0001 | 580 |  |  | 24 days | 2024-12-20 | 2024-12-17 | 2025-01-13 | 2025-01-10 | Completed | Completed as planned | 700588 |  | Morgan Lee | R. Gupta | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p013mk0001_0588.zip | Timing estimate is illustrative | Central | 582
[5 empty] | 5.3.5.1 |  | Analysis datasets - ADAM format | 581 |  |  | 28 days | 2024-12-25 | 2024-12-26 | 2025-01-22 | 2025-01-18 | Completed |  | 700589 | Archive release | Sam Brooks | M. Sullivan | CSV | Analysis_datasets_ADAM_format_0589.csv | Timing estimate is illustrative | Central | 583
[5 empty] | 5.3.5.1 |  | Data definition for analysis datasets - ADAM format (define file) | 582 |  |  | 29 days | 2024-12-27 | 2024-12-29 | 2025-01-25 | 2025-01-30 | Completed |  | 700590 |  | Jordan Patel | A. Shah | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0590.zip | Dummy data added for planning demo | Central | 584
[5 empty] | 5.3.5.1 |  | Analysis Data Reviewers Guide | 583 |  |  | 8 days | 2024-12-24 | 2024-12-25 | 2025-01-01 | 2024-12-31 | Completed | Filed in baseline wave | 700591 |  | Taylor Chen | N. Ortiz | ZIP | Analysis_Data_Reviewers_Guide_0591.zip | Placeholder timeline for reporting test | Central | 585
[5 empty] | 5.3.5.1 |  | Analysis results Metadata (ARM) | 584 |  |  | 11 days | 2024-12-25 | 2024-12-29 | 2025-01-05 |  | In Progress | Draft in QC review | 700592 |  | Morgan Lee | R. Gupta | DOCX | Analysis_results_Metadata_ARM_0592.docx | Timing estimate is illustrative | Central | 586
[5 empty] | 5.3.5.1 |  | Analysis programs | 585 |  |  | 21 days | 2024-12-28 | 2024-12-29 | 2025-01-18 | 2025-01-24 | Completed | Released to archive | 700593 | Submission build | Taylor Chen | N. Ortiz | ZIP | Analysis_programs_0593.zip | Placeholder timeline for reporting test | Central | 587
[5 empty] | 5.3.5.1 |  | 5.3.5.1 p017mk0001 Study reports and related information of controlled clinical studies pertinent to the claimed indication [placebo] | 586 |  |  | 29 days | 2024-12-25 | 2024-12-30 | 2025-01-23 | 2025-01-28 | Completed | Filed in baseline wave | 700594 |  | Jamie Carter | N. Ortiz | DOCX | p017mk0001_Study_reports_and_related_information_of_controll_0594.docx | Sample entry for dashboard validation | Central | 588
[5 empty] | 5.3.5.1 |  | Study report [p017mk0001 ] and related information | 587 |  |  | 7 days | 2024-12-29 |  | 2025-01-05 |  | Not Started | Pending authoring start | 700595 |  | Alex Kim | R. Gupta | PDF | Study_report_p017mk0001_and_related_information_0595.pdf | Dummy data added for planning demo | Central | 589
[5 empty] | 5.3.5.1 |  | P017 SAP | 588 |  |  | 20 days | 2025-01-01 | 2024-12-30 | 2025-01-21 | 2025-01-22 | Completed | QC completed | 700596 | Archive release | Jordan Patel | N. Ortiz | DOCX | P017_SAP_0596.docx | Dummy data added for planning demo | Central | 590
[5 empty] | 5.3.5.1 |  | Clinical Study Report | 589 |  |  | 19 days | 2024-12-25 |  | 2025-01-13 |  | Not Started | Pending authoring start | 700597 |  | Casey Rivera | A. Shah | PDF | Clinical_Study_Report_0597.pdf | Timing estimate is illustrative | Central | 591
[5 empty] | 5.3.5.1 |  | Case Report Forms - CRF FOLDER p017mk0001 | 590 |  |  | 30 days | 2025-01-02 | 2025-01-07 | 2025-02-01 |  | In Progress | Draft in QC review | 700598 |  | Morgan Lee | M. Sullivan | DOCX | Case_Report_Forms_CRF_FOLDER_p017mk0001_0598.docx | Placeholder timeline for reporting test | Central | 592
[5 empty] | 5.3.5.1 |  | Listing of Case Report Forms (CRFs TOC) | 591 |  |  | 35 days | 2024-12-26 | 2024-12-28 | 2025-01-30 | 2025-02-01 | Completed | Filed in baseline wave | 700599 | Archive release | Jamie Carter | M. Sullivan | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_0599.zip | Sample entry for dashboard validation | Central | 593
[5 empty] | 5.3.5.1 |  | Case Report Forms - eCRFs (by site) for US | 592 |  |  | 25 days | 2025-01-02 | 2024-12-30 | 2025-01-27 | 2025-02-02 | Completed |  | 700600 | Submission build | Sam Brooks | N. Ortiz | PDF | Case_Report_Forms_eCRFs_by_site_for_US_0600.pdf | Sample entry for dashboard validation | Central | 594
[5 empty] | 5.3.5.1 |  | Adjudication Packages (if applicable) | 593 |  |  | 8 days | 2024-12-30 |  | 2025-01-07 |  | Not Started | On hold pending document availability | 700601 |  | Morgan Lee | N. Ortiz | XLSX | Adjudication_Packages_if_applicable_0601.xlsx | Sample entry for dashboard validation | Central | 595
[5 empty] | 5.3.5.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p017mk0001 | 594 |  |  | 12 days | 2025-01-03 | 2025-01-05 | 2025-01-15 | 2025-01-18 | Completed |  | 700602 | Archive release | Morgan Lee | L. Bennett | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_0602.zip | Timing estimate is illustrative | Central | 596
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 595 |  |  | 27 days | 2025-01-01 | 2025-01-03 | 2025-01-28 |  | In Progress | Publishing build in progress | 700603 | Publishing prep | Jamie Carter | A. Shah | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_0603.zip | Dummy data added for planning demo | Central | 597
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 596 |  |  | 30 days | 2024-12-29 | 2024-12-27 | 2025-01-28 | 2025-01-26 | Completed |  | 700604 | Publishing QC | Alex Kim | R. Gupta | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_0604.zip | Sample entry for dashboard validation | Central | 598
[5 empty] | 5.3.5.1 |  | Study Data Reviewers Guide | 597 |  |  | 20 days | 2024-12-29 | 2024-12-29 | 2025-01-18 |  | In Progress | Publishing build in progress | 700605 | Regional alignment | Taylor Chen | M. Sullivan | PDF | Study_Data_Reviewers_Guide_0605.pdf | Sample entry for dashboard validation | Central | 599
[5 empty] | 5.3.5.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 598 |  |  | 26 days | 2024-12-29 | 2024-12-26 | 2025-01-24 | 2025-01-31 | Completed | Released to archive | 700606 |  | Sam Brooks | R. Gupta | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0606.pdf | Dummy data added for planning demo | Central | 600
[5 empty] | 5.3.5.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p017mk0001 | 599 |  |  | 12 days | 2025-01-06 | 2025-01-12 | 2025-01-18 |  | In Progress | Awaiting final source document | 700607 | QC review | Alex Kim | R. Gupta | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p017mk0001_0607.xlsx | Placeholder timeline for reporting test | Central | 601
[5 empty] | 5.3.5.1 |  | Analysis datasets - ADAM format | 600 |  |  | 20 days | 2024-12-31 | 2024-12-30 | 2025-01-20 | 2025-01-21 | Completed | Completed as planned | 700608 | Archive release | Sam Brooks | N. Ortiz | ZIP | Analysis_datasets_ADAM_format_0608.zip | Dummy data added for planning demo | Central | 602
[5 empty] | 5.3.5.1 |  | Data definition for analysis datasets - ADAM format (define file) | 601 |  |  | 16 days | 2025-01-04 | 2025-01-05 | 2025-01-20 | 2025-01-19 | Completed | Completed as planned | 700609 |  | Casey Rivera | N. Ortiz | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0609.csv | Dummy data added for planning demo | Central | 603
[5 empty] | 5.3.5.1 |  | Analysis Data Reviewers Guide | 602 |  |  | 35 days | 2025-01-08 | 2025-01-13 | 2025-02-12 |  | In Progress | Draft in QC review | 700610 | Publishing prep | Alex Kim | M. Sullivan | CSV | Analysis_Data_Reviewers_Guide_0610.csv | Placeholder timeline for reporting test | Central | 604
[5 empty] | 5.3.5.1 |  | Analysis results Metadata (ARM) | 603 |  |  | 18 days | 2025-01-05 | 2025-01-07 | 2025-01-23 | 2025-01-30 | Completed | Filed in baseline wave | 700611 |  | Morgan Lee | A. Shah | PDF | Analysis_results_Metadata_ARM_0611.pdf | Sample entry for dashboard validation | Central | 605
[5 empty] | 5.3.5.1 |  | Analysis programs | 604 |  |  | 13 days | 2025-01-09 | 2025-01-14 | 2025-01-22 | 2025-01-20 | Completed | Released to archive | 700612 | Publishing QC | Casey Rivera | A. Shah | ZIP | Analysis_programs_0612.zip | Placeholder timeline for reporting test | Central | 606
[5 empty] | 5.3.5.1 |  | 5.3.5.1 p018mk0001 Study reports and related information of controlled clinical studies pertinent to the claimed indication [no treatment] | 605 |  |  | 22 days | 2025-01-05 | 2025-01-06 | 2025-01-27 | 2025-01-28 | Completed | Released to archive | 700613 | Submission build | Taylor Chen | R. Gupta | PDF | p018mk0001_Study_reports_and_related_information_of_controll_0613.pdf | Sample entry for dashboard validation | Central | 607
[5 empty] | 5.3.5.1 |  | Study report [p018mk0001] and related information | 606 |  |  | 12 days | 2025-01-10 | 2025-01-13 | 2025-01-22 | 2025-01-18 | Completed | QC completed | 700614 | Submission build | Alex Kim | N. Ortiz | DOCX | Study_report_p018mk0001_and_related_information_0614.docx | Dummy data added for planning demo | Central | 608
[5 empty] | 5.3.5.1 |  | P018 SAP | 607 |  |  | 19 days | 2025-01-06 | 2025-01-08 | 2025-01-25 | 2025-01-21 | Completed | Filed in baseline wave | 700615 | Submission build | Casey Rivera | R. Gupta | PDF | P018_SAP_0615.pdf | Sample entry for dashboard validation | Central | 609
[5 empty] | 5.3.5.1 |  | Clinical Study Report | 608 |  |  | 24 days | 2025-01-11 | 2025-01-10 | 2025-02-04 | 2025-02-05 | Completed | Released to archive | 700616 |  | Sam Brooks | L. Bennett | PDF | Clinical_Study_Report_0616.pdf | Dummy data added for planning demo | Central | 610
[5 empty] | 5.3.5.1 |  | Case Report Forms - CRF FOLDER p018mk0001 | 609 |  |  | 32 days | 2025-01-06 | 2025-01-05 | 2025-02-07 | 2025-02-08 | Completed |  | 700617 | Publishing QC | Jamie Carter | N. Ortiz | PDF | Case_Report_Forms_CRF_FOLDER_p018mk0001_0617.pdf | Placeholder timeline for reporting test | Central | 611
[5 empty] | 5.3.5.1 |  | Listing of Case Report Forms (CRFs TOC) | 610 |  |  | 26 days | 2025-01-11 | 2025-01-15 | 2025-02-06 |  | In Progress | Publishing build in progress | 700618 | Publishing prep | Morgan Lee | L. Bennett | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_0618.xlsx | Sample entry for dashboard validation | Central | 612
[5 empty] | 5.3.5.1 |  | Case Report Forms - eCRFs (by site) for US | 611 |  |  | 26 days | 2025-01-09 | 2025-01-14 | 2025-02-04 | 2025-02-02 | Completed | Filed in baseline wave | 700619 | Archive release | Jamie Carter | A. Shah | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0619.docx | Timing estimate is illustrative | Central | 613
[5 empty] | 5.3.5.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p018mk0001 | 612 |  |  | 13 days | 2025-01-13 | 2025-01-12 | 2025-01-26 |  | In Progress | Regional review underway | 700620 |  | Taylor Chen | N. Ortiz | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_0620.xlsx | Timing estimate is illustrative | Central | 614
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 613 |  |  | 10 days | 2025-01-10 | 2025-01-07 | 2025-01-20 | 2025-01-20 | Completed | Filed in baseline wave | 700621 | Submission build | Casey Rivera | A. Shah | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_0621.zip | Timing estimate is illustrative | Central | 615
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 614 |  |  | 34 days | 2025-01-09 | 2025-01-12 | 2025-02-12 | 2025-02-16 | Completed | QC completed | 700622 | Submission build | Jordan Patel | R. Gupta | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_0622.csv | Sample entry for dashboard validation | Central | 616
[5 empty] | 5.3.5.1 |  | Study Data Reviewers Guide | 615 |  |  | 23 days | 2025-01-08 | 2025-01-06 | 2025-01-31 |  | In Progress | Metadata check in progress | 700623 | Authoring | Morgan Lee | R. Gupta | DOCX | Study_Data_Reviewers_Guide_0623.docx | Placeholder timeline for reporting test | Central | 617
[5 empty] | 5.3.5.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 616 |  |  | 14 days | 2025-01-15 | 2025-01-13 | 2025-01-29 |  | In Progress | Awaiting final source document | 700624 | Authoring | Alex Kim | A. Shah | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0624.docx | Timing estimate is illustrative | Central | 618
[5 empty] | 5.3.5.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p018mk0001 | 617 |  |  | 22 days | 2025-01-14 | 2025-01-12 | 2025-02-05 | 2025-02-07 | Completed | Filed in baseline wave | 700625 | Archive release | Casey Rivera | R. Gupta | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p018mk0001_0625.csv | Placeholder timeline for reporting test | Central | 619
[5 empty] | 5.3.5.1 |  | Analysis datasets - ADAM format | 618 |  |  | 10 days | 2025-01-11 | 2025-01-17 | 2025-01-21 |  | In Progress | Awaiting final source document | 700626 | Publishing prep | Morgan Lee | R. Gupta | ZIP | Analysis_datasets_ADAM_format_0626.zip | Placeholder timeline for reporting test | Central | 620
[5 empty] | 5.3.5.1 |  | Data definition for analysis datasets - ADAM format (define file) | 619 |  |  | 27 days | 2025-01-14 | 2025-01-17 | 2025-02-10 | 2025-02-07 | Completed | Completed as planned | 700627 | Submission build | Sam Brooks | M. Sullivan | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0627.xlsx | Dummy data added for planning demo | Central | 621
[5 empty] | 5.3.5.1 |  | Analysis Data Reviewers Guide | 620 |  |  | 13 days | 2025-01-14 | 2025-01-13 | 2025-01-27 |  | In Progress | Draft in QC review | 700628 |  | Taylor Chen | R. Gupta | CSV | Analysis_Data_Reviewers_Guide_0628.csv | Sample entry for dashboard validation | Central | 622
[5 empty] | 5.3.5.1 |  | Analysis results Metadata (ARM) | 621 |  |  | 24 days | 2025-01-15 | 2025-01-13 | 2025-02-08 |  | In Progress | Awaiting final source document | 700629 | QC review | Casey Rivera | M. Sullivan | XLSX | Analysis_results_Metadata_ARM_0629.xlsx | Placeholder timeline for reporting test | Central | 623
[5 empty] | 5.3.5.1 |  | Analysis programs | 622 |  |  | 18 days | 2025-01-20 |  | 2025-02-07 |  | Not Started | Scheduled after current milestone | 700630 |  | Sam Brooks | A. Shah | TXT | Analysis_programs_0630.txt | Dummy data added for planning demo | Central | 624
[5 empty] | 5.3.5.2 |  | 5.3.5.2 p019mk0001 Study reports and related information of uncontrolled clinical studies | 623 |  |  | 20 days | 2025-01-20 | 2025-01-26 | 2025-02-09 |  | In Progress | Draft in QC review | 700631 | QC review | Taylor Chen | R. Gupta | PDF | p019mk0001_Study_reports_and_related_information_of_uncontro_0631.pdf | Placeholder timeline for reporting test | Central | 625
[5 empty] | 5.3.5.2 |  | Study report [p019mk0001] and related information | 624 |  |  | 25 days | 2025-01-14 | 2025-01-14 | 2025-02-08 | 2025-02-15 | Completed | Released to archive | 700632 |  | Sam Brooks | M. Sullivan | PDF | Study_report_p019mk0001_and_related_information_0632.pdf | Timing estimate is illustrative | Central | 626
[5 empty] | 5.3.5.2 |  | Protocol 019-03 | 625 |  |  | 31 days | 2025-01-21 | 2025-01-27 | 2025-02-21 |  | In Progress | Publishing build in progress | 700633 | Regional alignment | Taylor Chen | R. Gupta | PDF | Protocol_019_03_0633.pdf | Timing estimate is illustrative | Central | 627
[5 empty] | 5.3.5.2 |  | P019 SAP-01 | 626 |  |  | 12 days | 2025-01-15 | 2025-01-13 | 2025-01-27 |  | In Progress | Pending cross-functional signoff | 700634 | Regional alignment | Taylor Chen | M. Sullivan | DOCX | P019_SAP_01_0634.docx | Placeholder timeline for reporting test | Central | 628
[5 empty] | 5.3.5.2 |  | P019 Summary Report for OMA | 627 |  |  | 16 days | 2025-01-18 | 2025-01-24 | 2025-02-03 |  | In Progress | Draft in QC review | 700635 | QC review | Jordan Patel | A. Shah | PDF | P019_Summary_Report_for_OMA_0635.pdf | Placeholder timeline for reporting test | Central | 629
[5 empty] | 5.3.5.2 |  | Case Report Forms - CRF FOLDER p019mk0001 | 628 |  |  | 27 days | 2025-01-16 | 2025-01-17 | 2025-02-12 | 2025-02-10 | Completed | QC completed | 700636 | Publishing QC | Sam Brooks | N. Ortiz | PDF | Case_Report_Forms_CRF_FOLDER_p019mk0001_0636.pdf | Dummy data added for planning demo | Central | 630
[5 empty] | 5.3.5.2 |  | Listing of Case Report Forms (CRFs TOC) | 629 |  |  | 27 days | 2025-01-17 | 2025-01-20 | 2025-02-13 |  | In Progress | Metadata check in progress | 700637 | Authoring | Sam Brooks | M. Sullivan | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_0637.csv | Timing estimate is illustrative | Central | 631
[5 empty] | 5.3.5.2 |  | Case Report Forms - eCRFs (by site) for US | 630 |  |  | 35 days | 2025-01-23 | 2025-01-26 | 2025-02-27 |  | In Progress | Draft in QC review | 700638 | Authoring | Jamie Carter | R. Gupta | PDF | Case_Report_Forms_eCRFs_by_site_for_US_0638.pdf | Placeholder timeline for reporting test | Central | 632
[5 empty] | 5.3.5.2 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p019mk0001 | 631 |  |  | 15 days | 2025-01-20 |  | 2025-02-04 |  | Not Started | Resource assignment not yet confirmed | 700639 |  | Sam Brooks | M. Sullivan | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_0639.xlsx | Sample entry for dashboard validation | Central | 633
[5 empty] | 5.3.5.2 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 632 |  |  | 34 days | 2025-01-22 | 2025-01-28 | 2025-02-25 |  | In Progress | Awaiting final source document | 700640 | Regional alignment | Jordan Patel | R. Gupta | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_0640.csv | Timing estimate is illustrative | Central | 634
[5 empty] | 5.3.5.2 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 633 |  |  | 11 days | 2025-01-25 | 2025-01-29 | 2025-02-05 |  | In Progress | Metadata check in progress | 700641 | QC review | Casey Rivera | A. Shah | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_0641.csv | Timing estimate is illustrative | Central | 635
[5 empty] | 5.3.5.2 |  | Study Data Reviewers Guide | 634 |  |  | 12 days | 2025-01-26 |  | 2025-02-07 |  | Not Started | Pending authoring start | 700642 |  | Jordan Patel | M. Sullivan | DOCX | Study_Data_Reviewers_Guide_0642.docx | Timing estimate is illustrative | Central | 636
[5 empty] | 5.3.5.2 |  | Annotated Case Report Forms (CRFs) - SDTM format | 635 |  |  | 7 days | 2025-01-24 | 2025-01-24 | 2025-01-31 |  | In Progress | Publishing build in progress | 700643 |  | Jordan Patel | A. Shah | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0643.pdf | Dummy data added for planning demo | Central | 637
[5 empty] | 5.3.5.2 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p019mk0001 | 636 |  |  | 14 days | 2025-01-27 | 2025-01-31 | 2025-02-10 |  | In Progress | Draft in QC review | 700644 |  | Jordan Patel | A. Shah | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p019mk0001_0644.zip | Dummy data added for planning demo | Central | 638
[5 empty] | 5.3.5.2 |  | Analysis datasets - ADAM format | 637 |  |  | 19 days | 2025-01-27 | 2025-01-24 | 2025-02-15 | 2025-02-21 | Completed | Completed as planned | 700645 | Submission build | Jordan Patel | A. Shah | CSV | Analysis_datasets_ADAM_format_0645.csv | Timing estimate is illustrative | Central | 639
[5 empty] | 5.3.5.2 |  | Data definition for analysis datasets - ADAM format (define file) | 638 |  |  | 32 days | 2025-01-22 |  | 2025-02-23 |  | Not Started | Planned for upcoming wave | 700646 |  | Taylor Chen | R. Gupta | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0646.zip | Dummy data added for planning demo | Central | 640
[5 empty] | 5.3.5.2 |  | Analysis Data Reviewers Guide | 639 |  |  | 11 days | 2025-01-25 | 2025-01-30 | 2025-02-05 |  | In Progress | Awaiting final source document | 700647 | Publishing prep | Morgan Lee | L. Bennett | XLSX | Analysis_Data_Reviewers_Guide_0647.xlsx | Timing estimate is illustrative | Central | 641
[5 empty] | 5.3.5.2 |  | Analysis Results Metadata (ARM) | 640 |  |  | 24 days | 2025-01-23 | 2025-01-29 | 2025-02-16 |  | In Progress | Draft in QC review | 700648 | Authoring | Jamie Carter | A. Shah | PDF | Analysis_Results_Metadata_ARM_0648.pdf | Placeholder timeline for reporting test | Central | 642
[5 empty] | 5.3.5.2 |  | Analysis programs | 641 |  |  | 23 days | 2025-01-25 |  | 2025-02-17 |  | Not Started | Scheduled after current milestone | 700649 |  | Jordan Patel | A. Shah | ZIP | Analysis_programs_0649.zip | Dummy data added for planning demo | Central | 643
[5 empty] | 5.3.5 |  | 5.3.5 Reports of efficacy and safety studies [hypercholest] | 642 |  |  | 47 days | 2025-01-27 | 2025-01-30 | 2025-03-15 |  | In Progress | Regional review underway | 700650 | Publishing prep | Jordan Patel | L. Bennett | XLSX | Reports_of_efficacy_and_safety_studies_hypercholest_0650.xlsx | Dummy data added for planning demo | Central | 644
[5 empty] | 5.3.5 |  | 5.3.5 Summary of Main Efficacy Results (EU) | 643 |  |  | 30 days | 2025-02-01 |  | 2025-03-03 |  | Not Started | Pending authoring start | 700651 |  | Alex Kim | R. Gupta | DOCX | Summary_of_Main_Efficacy_Results_EU_0651.docx | Dummy data added for planning demo | Central | 645
[5 empty] | 5.3.5.3 |  | 5.3.5.3 Reports of analyses of data from more than one study | 644 |  |  | 10 days | 2025-01-30 | 2025-01-29 | 2025-02-09 |  | In Progress | Draft in QC review | 700652 |  | Jordan Patel | N. Ortiz | DOCX | Reports_of_analyses_of_data_from_more_than_one_study_0652.docx | Placeholder timeline for reporting test | Central | 646
[5 empty] | 5.3.5.3.1 |  | 5.3.5.3.1 ClinPharm Pooled Summary of Safety (CPSOS) | 645 |  |  | 28 days | 2025-01-28 | 2025-01-30 | 2025-02-25 |  | In Progress | Pending cross-functional signoff | 700653 | Publishing prep | Morgan Lee | A. Shah | DOCX | ClinPharm_Pooled_Summary_of_Safety_CPSOS_0653.docx | Sample entry for dashboard validation | Central | 647
[5 empty] | 5.3.5.3.1 |  | Clin Pharm Summary of Safety | 646 |  |  | 15 days | 2025-01-31 |  | 2025-02-15 |  | Not Started | On hold pending document availability | 700654 |  | Jamie Carter | A. Shah | PDF | Clin_Pharm_Summary_of_Safety_0654.pdf | Timing estimate is illustrative | Central | 648
[5 empty] | 5.3.5.3.1 |  | Analysis Data Sets and Programs | 647 |  |  | 17 days | 2025-01-29 | 2025-02-02 | 2025-02-15 | 2025-02-22 | Completed | Released to archive | 700655 | Publishing QC | Alex Kim | M. Sullivan | CSV | Analysis_Data_Sets_and_Programs_0655.csv | Placeholder timeline for reporting test | Central | 649
[5 empty] | 5.3.5.3.1 |  | Analysis datasets - ADAM format or Legacy format( Choose the correct Data format with team) | 648 |  |  | 9 days | 2025-01-30 | 2025-01-30 | 2025-02-08 |  | In Progress | Awaiting final source document | 700656 | Regional alignment | Morgan Lee | R. Gupta | CSV | Analysis_datasets_ADAM_format_or_Legacy_format_Choose_the_co_0656.csv | Sample entry for dashboard validation | Central | 650
[5 empty] | 5.3.5.3.1 |  | Data definition for analysis datasets - ADAM format or Legacy format( Choose the correct Data format with team) | 649 |  |  | 29 days | 2025-02-04 |  | 2025-03-05 |  | Not Started | Resource assignment not yet confirmed | 700657 |  | Jamie Carter | R. Gupta | XLSX | Data_definition_for_analysis_datasets_ADAM_format_or_Legacy__0657.xlsx | Timing estimate is illustrative | Central | 651
[5 empty] | 5.3.5.3.2 |  | 5.3.5.3.2 Integrated Summary of Efficacy (ISE) | 650 |  |  | 20 days | 2025-02-04 | 2025-02-10 | 2025-02-24 |  | In Progress | Pending cross-functional signoff | 700658 | Regional alignment | Taylor Chen | M. Sullivan | PDF | Integrated_Summary_of_Efficacy_ISE_0658.pdf | Sample entry for dashboard validation | Central | 652
[5 empty] | 5.3.5.3.2 |  | Integrated Summary of Efficacy (ISE) | 651 |  |  | 25 days | 2025-01-30 | 2025-02-05 | 2025-02-24 |  | In Progress | Pending cross-functional signoff | 700659 | QC review | Sam Brooks | A. Shah | PDF | Integrated_Summary_of_Efficacy_ISE_0659.pdf | Placeholder timeline for reporting test | Central | 653
[5 empty] | 5.3.5.3.2 |  | Analysis Data Sets and Programs | 652 |  |  | 13 days | 2025-01-30 |  | 2025-02-12 |  | Not Started | Planned for upcoming wave | 700660 |  | Morgan Lee | M. Sullivan | CSV | Analysis_Data_Sets_and_Programs_0660.csv | Timing estimate is illustrative | Central | 654
[5 empty] | 5.3.5.3.2 |  | Analysis datasets - ADAM format | 653 |  |  | 8 days | 2025-02-01 |  | 2025-02-09 |  | Not Started | Waiting on dependency from Module 3 | 700661 |  | Jamie Carter | N. Ortiz | CSV | Analysis_datasets_ADAM_format_0661.csv | Sample entry for dashboard validation | Central | 655
[5 empty] | 5.3.5.3.2 |  | Data definition for analysis datasets - ADAM format | 654 |  |  | 33 days | 2025-02-02 |  | 2025-03-07 |  | Not Started | Scheduled after current milestone | 700662 |  | Jordan Patel | N. Ortiz | XLSX | Data_definition_for_analysis_datasets_ADAM_format_0662.xlsx | Dummy data added for planning demo | Central | 656
[5 empty] | 5.3.5.3.2 |  | Analysis programs | 655 |  |  | 10 days | 2025-02-03 |  | 2025-02-13 |  | Not Started | On hold pending document availability | 700663 |  | Jordan Patel | L. Bennett | ZIP | Analysis_programs_0663.zip | Sample entry for dashboard validation | Central | 657
[5 empty] | 5.3.5.3.3 |  | 5.3.5.3.3 Integrated Summary of Safety (ISS) | 656 |  |  | 8 days | 2025-02-06 | 2025-02-05 | 2025-02-14 |  | In Progress | Publishing build in progress | 700664 |  | Jamie Carter | N. Ortiz | PDF | Integrated_Summary_of_Safety_ISS_0664.pdf | Timing estimate is illustrative | Central | 658
[5 empty] | 5.3.5.3.3 |  | Integrated Summary of Safety (ISS) | 657 |  |  | 11 days | 2025-02-07 | 2025-02-05 | 2025-02-18 | 2025-02-14 | Completed |  | 700665 |  | Jordan Patel | N. Ortiz | DOCX | Integrated_Summary_of_Safety_ISS_0665.docx | Timing estimate is illustrative | Central | 659
[5 empty] | 5.3.5.3.3 |  | Analysis Data Sets and Programs - iss | 658 |  |  | 29 days | 2025-02-10 |  | 2025-03-11 |  | Not Started | Scheduled after current milestone | 700666 |  | Casey Rivera | R. Gupta | CSV | Analysis_Data_Sets_and_Programs_iss_0666.csv | Dummy data added for planning demo | Central | 660
[5 empty] | 5.3.5.3.3 |  | Analysis datasets - ADAM format | 659 |  |  | 10 days | 2025-02-07 | 2025-02-04 | 2025-02-17 | 2025-02-22 | Completed | Filed in baseline wave | 700667 |  | Jordan Patel | A. Shah | CSV | Analysis_datasets_ADAM_format_0667.csv | Sample entry for dashboard validation | Central | 661
[5 empty] | 5.3.5.3.3 |  | Data definition for analysis datasets - ADAM format | 660 |  |  | 24 days | 2025-02-11 | 2025-02-13 | 2025-03-07 |  | In Progress | Pending cross-functional signoff | 700668 |  | Morgan Lee | N. Ortiz | CSV | Data_definition_for_analysis_datasets_ADAM_format_0668.csv | Timing estimate is illustrative | Central | 662
[5 empty] | 5.3.5.3.3 |  | Analysis programs | 661 |  |  | 9 days | 2025-02-08 | 2025-02-08 | 2025-02-17 |  | In Progress | Regional review underway | 700669 | QC review | Casey Rivera | M. Sullivan | ZIP | Analysis_programs_0669.zip | Timing estimate is illustrative | Central | 663
[5 empty] | 5.3.5.3.3 |  | Analysis Data Reviewer Guide | 662 |  |  | 12 days | 2025-02-11 |  | 2025-02-23 |  | Not Started | Resource assignment not yet confirmed | 700670 |  | Taylor Chen | A. Shah | ZIP | Analysis_Data_Reviewer_Guide_0670.zip | Sample entry for dashboard validation | Central | 664
[5 empty] | 5.3.5.3.3 |  | Analysis Data Sets and Programs - iss-aep | 663 |  |  | 17 days | 2025-02-12 | 2025-02-16 | 2025-03-01 |  | In Progress | Publishing build in progress | 700671 | QC review | Alex Kim | R. Gupta | ZIP | Analysis_Data_Sets_and_Programs_iss_aep_0671.zip | Sample entry for dashboard validation | Central | 665
[5 empty] | 5.3.5.3.3 |  | Analysis ADAM datasets or Legacy format( Choose the correct Data format with team) | 664 |  |  | 15 days | 2025-02-09 | 2025-02-07 | 2025-02-24 | 2025-02-25 | Completed |  | 700672 | Archive release | Alex Kim | N. Ortiz | CSV | Analysis_ADAM_datasets_or_Legacy_format_Choose_the_correct_D_0672.csv | Timing estimate is illustrative | Central | 666
[5 empty] | 5.3.5.3.3 |  | Data definition for analysis datasets - ADAM format or Legacy format( Choose the correct Data format with team) (define.xml & define.pdf) | 665 |  |  | 10 days | 2025-02-15 | 2025-02-12 | 2025-02-25 | 2025-02-25 | Completed | Filed in baseline wave | 700673 |  | Jordan Patel | A. Shah | XLSX | Data_definition_for_analysis_datasets_ADAM_format_or_Legacy__0673.xlsx | Placeholder timeline for reporting test | Central | 667
[5 empty] | 5.3.5.3.3 |  | Analysis Data Reviewers Guide(adrg.pdf) | 666 |  |  | 25 days | 2025-02-08 | 2025-02-13 | 2025-03-05 |  | In Progress | Draft in QC review | 700674 | Authoring | Morgan Lee | A. Shah | CSV | Analysis_Data_Reviewers_Guide_adrg_pdf_0674.csv | Dummy data added for planning demo | Central | 668
[5 empty] | 5.3.5.3.3 |  | Analysis Results Metadata (If Applicable) ( analysis-results-metadata.pdf) | 667 |  |  | 31 days | 2025-02-13 | 2025-02-16 | 2025-03-16 | 2025-03-20 | Completed | Filed in baseline wave | 700675 | Archive release | Jamie Carter | L. Bennett | XLSX | Analysis_Results_Metadata_If_Applicable_analysis_results_met_0675.xlsx | Placeholder timeline for reporting test | Central | 669
[5 empty] | 5.3.5.3 |  | 5.3.5.3 Modeling & Simulation Reports | 668 |  |  | 29 days | 2025-02-10 | 2025-02-13 | 2025-03-11 |  | In Progress | Publishing build in progress | 700676 |  | Alex Kim | M. Sullivan | PDF | Modeling_Simulation_Reports_0676.pdf | Dummy data added for planning demo | Central | 670
[5 empty] | 5.3.5.3 |  | 5.3.5.3 Modeling & Simulation Report #1 | 669 |  |  | 22 days | 2025-02-15 | 2025-02-13 | 2025-03-09 |  | In Progress | Metadata check in progress | 700677 | QC review | Jordan Patel | L. Bennett | PDF | Modeling_Simulation_Report_1_0677.pdf | Dummy data added for planning demo | Central | 671
[5 empty] | 5.3.5.3 |  | 5.3.5.3 Modeling Dataset #1 | 670 |  |  | 35 days | 2025-02-12 | 2025-02-11 | 2025-03-19 | 2025-03-26 | Completed | Filed in baseline wave | 700678 |  | Taylor Chen | M. Sullivan | ZIP | Modeling_Dataset_1_0678.zip | Placeholder timeline for reporting test | Central | 672
[5 empty] | 5.3.5.3 |  | 5.3.5.3 Modeling & Simulation Report #2 | 671 |  |  | 32 days | 2025-02-17 | 2025-02-18 | 2025-03-21 | 2025-03-22 | Completed |  | 700679 |  | Alex Kim | L. Bennett | PDF | Modeling_Simulation_Report_2_0679.pdf | Timing estimate is illustrative | Central | 673
[5 empty] | 5.3.5.3 |  | 5.3.5.3 Modeling Dataset #2 | 672 |  |  | 11 days | 2025-02-12 | 2025-02-17 | 2025-02-23 |  | In Progress | Draft in QC review | 700680 | Authoring | Jordan Patel | R. Gupta | ZIP | Modeling_Dataset_2_0680.zip | Dummy data added for planning demo | Central | 674
[5 empty] | 5.3.5.4 |  | 5.3.5.4 Other Study reports and related information | 673 |  |  | 10 days | 2025-02-18 | 2025-02-18 | 2025-02-28 |  | In Progress | Metadata check in progress | 700681 | QC review | Alex Kim | R. Gupta | DOCX | Other_Study_reports_and_related_information_0681.docx | Placeholder timeline for reporting test | Central | 675
[5 empty] | 5.3.5.4 |  | BIMO Deliverables (CDER Only) Previously call OSI | 674 |  |  | 9 days | 2025-02-13 | 2025-02-17 | 2025-02-22 | 2025-02-22 | Completed | Released to archive | 700682 | Archive release | Jamie Carter | L. Bennett | XLSX | BIMO_Deliverables_CDER_Only_Previously_call_OSI_0682.xlsx | Timing estimate is illustrative | Central | 676
[5 empty] | 5.3.5.4 |  | Data Listing Dataset | 675 |  |  | 25 days | 2025-02-13 | 2025-02-16 | 2025-03-10 |  | In Progress | Metadata check in progress | 700683 | Regional alignment | Casey Rivera | M. Sullivan | ZIP | Data_Listing_Dataset_0683.zip | Timing estimate is illustrative | Central | 677
[5 empty] | 5.3.5.4 |  | Data definition for the BIMO deliverables | 676 |  |  | 18 days | 2025-02-20 | 2025-02-23 | 2025-03-10 |  | In Progress | Metadata check in progress | 700684 | Authoring | Sam Brooks | L. Bennett | XLSX | Data_definition_for_the_BIMO_deliverables_0684.xlsx | Sample entry for dashboard validation | Central | 678
[5 empty] | 5.3.5.3 |  | 5.3.5.3 iSAP - safety | 677 |  |  | 35 days | 2025-02-18 |  | 2025-03-25 |  | Not Started | On hold pending document availability | 700685 |  | Alex Kim | M. Sullivan | XLSX | iSAP_safety_0685.xlsx | Dummy data added for planning demo | Central | 679
[5 empty] | 5.3.5.3 |  | 5.3.5.3 iSAP - efficacy | 678 |  |  | 29 days | 2025-02-17 |  | 2025-03-18 |  | Not Started | Planned for upcoming wave | 700686 |  | Jordan Patel | A. Shah | DOCX | iSAP_efficacy_0686.docx | Sample entry for dashboard validation | Central | 680
[5 empty] | 5.4 |  | 5.4 Literature References | 679 |  |  | 117 days | 2025-02-17 | 2025-02-16 | 2025-06-14 |  | In Progress | Awaiting final source document | 700687 | Regional alignment | Jamie Carter | L. Bennett | XLSX | Literature_References_0687.xlsx | Dummy data added for planning demo | Central | 681
[5 empty] | 5.4 |  | 5.4 Literature References - EU RMP | 680 |  |  | 104 days | 2025-02-20 | 2025-02-26 | 2025-06-04 |  | In Progress | Publishing build in progress | 700688 | Authoring | Alex Kim | N. Ortiz | XLSX | Literature_References_EU_RMP_0688.xlsx | Dummy data added for planning demo | Central | 682
[5 empty] | 5.4 |  | 5.4 Literature References - Core RMP | 681 |  |  | 100 days | 2025-02-22 | 2025-02-24 | 2025-06-02 | 2025-05-30 | Completed | QC completed | 700689 | Archive release | Taylor Chen | L. Bennett | PDF | Literature_References_Core_RMP_0689.pdf | Sample entry for dashboard validation | Central | 683
|  |  | Phase 4 - Post Submission Activities |  | 5 |  | Phase 4 - Post Submission Activities | 682 |  |  | 8 days | 2025-02-17 | 2025-02-23 | 2025-02-25 |  | In Progress | Awaiting final source document | 700690 | Regional alignment | Jordan Patel | N. Ortiz | DOCX | Phase_4_Post_Submission_Activities_0690.docx | Dummy data added for planning demo | Central | 684
[5 empty] | 5 |  | Safety Update Report (SUR) | 683 |  |  | 105 days | 2025-02-23 |  | 2025-06-08 |  | Not Started | Waiting on dependency from Module 3 | 700691 |  | Jamie Carter | L. Bennett | DOCX | Safety_Update_Report_SUR_0691.docx | Timing estimate is illustrative | Central | 685
[5 empty] | 2.7 |  | Phase 3 Submission Components Safety Update Report (SUR) | 684 |  |  | 6 days | 2025-02-18 |  | 2025-02-24 |  | Not Started | On hold pending document availability | 700692 |  | Casey Rivera | R. Gupta | DOCX | Phase_3_Submission_Components_Safety_Update_Report_SUR_0692.docx | Timing estimate is illustrative | Central | 686
[5 empty] | 2 |  | Module 2 Summaries | 685 |  |  | 126 days | 2025-02-19 | 2025-02-22 | 2025-06-25 | 2025-06-22 | Completed | QC completed | 700693 |  | Jamie Carter | L. Bennett | XLSX | Module_2_Summaries_0693.xlsx | Timing estimate is illustrative | Central | 687
[5 empty] | 2.2 |  | 2.2 Introduction to summary | 686 |  |  | 68 days | 2025-02-23 |  | 2025-05-02 |  | Not Started | Planned for upcoming wave | 700694 |  | Casey Rivera | R. Gupta | DOCX | Introduction_to_summary_0694.docx | Timing estimate is illustrative | Central | 688
[5 empty] | 2.7 |  | 2.7 Clinical summary | 687 |  |  | 89 days | 2025-02-22 |  | 2025-05-22 |  | Not Started | Scheduled after current milestone | 700695 |  | Casey Rivera | M. Sullivan | PDF | Clinical_summary_0695.pdf | Sample entry for dashboard validation | Central | 689
[5 empty] | 2.7.4 |  | 2.7.4 Summary of Clinical Safety | 688 |  |  | 64 days | 2025-02-25 | 2025-02-23 | 2025-04-30 |  | In Progress | Pending cross-functional signoff | 700696 |  | Jordan Patel | A. Shah | PDF | Summary_of_Clinical_Safety_0696.pdf | Placeholder timeline for reporting test | Central | 690
[5 empty] | 2.7.4 |  | 2.7.4 Appendix - Narratives | 689 |  |  | 20 days | 2025-02-26 | 2025-03-02 | 2025-03-18 | 2025-03-16 | Completed | Released to archive | 700697 | Archive release | Alex Kim | L. Bennett | DOCX | Appendix_Narratives_0697.docx | Dummy data added for planning demo | Central | 691
[5 empty] | 2.7.5 |  | 2.7.5 References | 690 |  |  | 73 days | 2025-02-28 |  | 2025-05-12 |  | Not Started | On hold pending document availability | 700698 |  | Casey Rivera | M. Sullivan | PDF | References_0698.pdf | Dummy data added for planning demo | Central | 692
[5 empty] | 5 |  | Module 5 Clinical Study Reports | 691 |  |  | 138 days | 2025-02-25 | 2025-03-03 | 2025-07-13 |  | In Progress | Awaiting final source document | 700699 |  | Casey Rivera | N. Ortiz | DOCX | Module_5_Clinical_Study_Reports_0699.docx | Timing estimate is illustrative | Central | 693
[5 empty] | 5.3 |  | 5.3 Clinical study reports and related information | 692 |  |  | 131 days | 2025-02-25 | 2025-02-23 | 2025-07-06 |  | In Progress | Metadata check in progress | 700700 | Publishing prep | Alex Kim | R. Gupta | DOCX | Clinical_study_reports_and_related_information_0700.docx | Dummy data added for planning demo | Central | 694
[5 empty] | 5.3.5 |  | 5.3.5 Reports of efficacy and safety studies [Indication] | 693 |  |  | 61 days | 2025-03-02 |  | 2025-05-02 |  | Not Started | Scheduled after current milestone | 700701 |  | Casey Rivera | R. Gupta | DOCX | Reports_of_efficacy_and_safety_studies_Indication_0701.docx | Sample entry for dashboard validation | Central | 695
[5 empty] | 5.3.5.1 |  | 5.3.5.1 Study reports and related information of controlled clinical studies pertinent to the claimed indication [type of control] | 694 |  |  | 31 days | 2025-03-03 | 2025-03-03 | 2025-04-03 |  | In Progress | Publishing build in progress | 700702 | Regional alignment | Morgan Lee | N. Ortiz | PDF | Study_reports_and_related_information_of_controlled_clinical_0702.pdf | Sample entry for dashboard validation | Central | 696
[5 empty] | 5.3.5.1 |  | Case Report Forms - CRF FOLDER | 695 |  |  | 16 days | 2025-03-02 |  | 2025-03-18 |  | Not Started | On hold pending document availability | 700703 |  | Sam Brooks | L. Bennett | DOCX | Case_Report_Forms_CRF_FOLDER_0703.docx | Dummy data added for planning demo | Central | 697
[5 empty] | 5.3.5.1 |  | Listing of Case Report Forms (CRFs TOC) | 696 |  |  | 32 days | 2025-02-26 |  | 2025-03-30 |  | Not Started | Planned for upcoming wave | 700704 |  | Sam Brooks | A. Shah | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_0704.zip | Sample entry for dashboard validation | Central | 698
[5 empty] | 5.3.5.1 |  | Case Report Forms - eCRFs (by site) | 697 |  |  | 22 days | 2025-02-26 | 2025-03-04 | 2025-03-20 |  | In Progress | Draft in QC review | 700705 | Regional alignment | Taylor Chen | M. Sullivan | PDF | Case_Report_Forms_eCRFs_by_site_0705.pdf | Placeholder timeline for reporting test | Central | 699
[5 empty] | 5.3.5.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER | 698 |  |  | 13 days | 2025-03-04 | 2025-03-08 | 2025-03-17 | 2025-03-21 | Completed | Released to archive | 700706 | Publishing QC | Jordan Patel | L. Bennett | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_0706.xlsx | Placeholder timeline for reporting test | Central | 700
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 699 |  |  | 20 days | 2025-03-05 |  | 2025-03-25 |  | Not Started | On hold pending document availability | 700707 |  | Sam Brooks | L. Bennett | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_0707.xlsx | Placeholder timeline for reporting test | Central | 701
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 700 |  |  | 23 days | 2025-03-02 | 2025-03-03 | 2025-03-25 | 2025-03-25 | Completed | Released to archive | 700708 | Submission build | Alex Kim | L. Bennett | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_0708.xlsx | Dummy data added for planning demo | Central | 702
[5 empty] | 5.3.5.1 |  | Study Data Reviewers Guide | 701 |  |  | 11 days | 2025-02-28 | 2025-03-06 | 2025-03-11 |  | In Progress | Regional review underway | 700709 |  | Morgan Lee | R. Gupta | PDF | Study_Data_Reviewers_Guide_0709.pdf | Sample entry for dashboard validation | Central | 703
[5 empty] | 5.3.5.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 702 |  |  | 24 days | 2025-03-03 |  | 2025-03-27 |  | Not Started | Pending authoring start | 700710 |  | Taylor Chen | L. Bennett | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_0710.pdf | Sample entry for dashboard validation | Central | 704
[5 empty] | 5.3.5.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER | 703 |  |  | 27 days | 2025-03-03 | 2025-03-03 | 2025-03-30 |  | In Progress | Publishing build in progress | 700711 | Publishing prep | Taylor Chen | N. Ortiz | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_0711.csv | Timing estimate is illustrative | Central | 705
[5 empty] | 5.3.5.1 |  | Analysis datasets - ADAM format | 704 |  |  | 29 days | 2025-03-02 |  | 2025-03-31 |  | Not Started | Resource assignment not yet confirmed | 700712 |  | Alex Kim | M. Sullivan | CSV | Analysis_datasets_ADAM_format_0712.csv | Placeholder timeline for reporting test | Central | 706
[5 empty] | 5.3.5.1 |  | Data definition for analysis datasets - ADAM format (define file) | 705 |  |  | 12 days | 2025-03-10 |  | 2025-03-22 |  | Not Started | Pending authoring start | 700713 |  | Alex Kim | A. Shah | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0713.xlsx | Sample entry for dashboard validation | Central | 707
[5 empty] | 5.3.5.1 |  | Analysis results Metadata | 706 |  |  | 27 days | 2025-03-02 | 2025-03-02 | 2025-03-29 |  | In Progress | Draft in QC review | 700714 |  | Sam Brooks | M. Sullivan | PDF | Analysis_results_Metadata_0714.pdf | Sample entry for dashboard validation | Central | 708
[5 empty] | 5.3.5.1 |  | Analysis Data Reviewers Guide | 707 |  |  | 30 days | 2025-03-03 | 2025-03-08 | 2025-04-02 |  | In Progress | Regional review underway | 700715 | Publishing prep | Jordan Patel | N. Ortiz | ZIP | Analysis_Data_Reviewers_Guide_0715.zip | Timing estimate is illustrative | Central | 709
[5 empty] | 5.3.5.1 |  | Analysis programs | 708 |  |  | 13 days | 2025-03-08 | 2025-03-09 | 2025-03-21 |  | In Progress | Regional review underway | 700716 | Regional alignment | Jamie Carter | R. Gupta | ZIP | Analysis_programs_0716.zip | Placeholder timeline for reporting test | Central | 710
[5 empty] | 5.3.5.3 |  | 5.3.5.3 Reports of analyses of data from more than one study | 709 |  |  | 11 days | 2025-03-05 | 2025-03-04 | 2025-03-16 |  | In Progress | Draft in QC review | 700717 | Regional alignment | Taylor Chen | A. Shah | PDF | Reports_of_analyses_of_data_from_more_than_one_study_0717.pdf | Timing estimate is illustrative | Central | 711
[5 empty] | 5.3.5.3.3 |  | 5.3.5.3.3 Integrated Summary of Safety (US) (ISS) | 710 |  |  | 15 days | 2025-03-09 |  | 2025-03-24 |  | Not Started | Planned for upcoming wave | 700718 |  | Alex Kim | L. Bennett | DOCX | Integrated_Summary_of_Safety_US_ISS_0718.docx | Timing estimate is illustrative | Central | 712
[5 empty] | 5.3.5.3.3 |  | Integrated Summary of Safety (ISS) | 711 |  |  | 10 days | 2025-03-11 | 2025-03-09 | 2025-03-21 |  | In Progress | Publishing build in progress | 700719 | Authoring | Casey Rivera | A. Shah | PDF | Integrated_Summary_of_Safety_ISS_0719.pdf | Sample entry for dashboard validation | Central | 713
[5 empty] | 5.3.5.3.3 |  | Analysis Data Sets and Programs | 712 |  |  | 35 days | 2025-03-12 | 2025-03-17 | 2025-04-16 |  | In Progress | Awaiting final source document | 700720 | QC review | Morgan Lee | A. Shah | XLSX | Analysis_Data_Sets_and_Programs_0720.xlsx | Dummy data added for planning demo | Central | 714
[5 empty] | 5.3.5.3.3 |  | Analysis datasets - ADAM format | 713 |  |  | 17 days | 2025-03-08 |  | 2025-03-25 |  | Not Started | Scheduled after current milestone | 700721 |  | Taylor Chen | M. Sullivan | ZIP | Analysis_datasets_ADAM_format_0721.zip | Dummy data added for planning demo | Central | 715
[5 empty] | 5.3.5.3.3 |  | Data definition for analysis datasets - ADAM format | 714 |  |  | 23 days | 2025-03-09 | 2025-03-08 | 2025-04-01 |  | In Progress | Awaiting final source document | 700722 |  | Alex Kim | M. Sullivan | XLSX | Data_definition_for_analysis_datasets_ADAM_format_0722.xlsx | Timing estimate is illustrative | Central | 716
[5 empty] | 5.3.5.3.3 |  | Analysis programs | 715 |  |  | 34 days | 2025-03-11 | 2025-03-12 | 2025-04-14 |  | In Progress | Draft in QC review | 700723 | Publishing prep | Jordan Patel | N. Ortiz | ZIP | Analysis_programs_0723.zip | Timing estimate is illustrative | Central | 717
[5 empty] | 5.3.5.3.3 |  | Analysis Data Reviewer Guide | 716 |  |  | 15 days | 2025-03-12 | 2025-03-11 | 2025-03-27 |  | In Progress | Metadata check in progress | 700724 |  | Sam Brooks | R. Gupta | CSV | Analysis_Data_Reviewer_Guide_0724.csv | Sample entry for dashboard validation | Central | 718
[5 empty] | 5.4 |  | 5.4 Literature References | 717 |  |  | 110 days | 2025-03-15 |  | 2025-07-03 |  | Not Started | Pending authoring start | 700725 |  | Morgan Lee | N. Ortiz | PDF | Literature_References_0725.pdf | Placeholder timeline for reporting test | Central | 719
[8 empty] | 718 | [16 empty] | Central | 1
United States Filing_Original NDA | [7 empty] | 719 |  |  | 172 days | 2025-02-09 | 2025-02-11 | 2025-07-31 |  | In Progress | Awaiting final source document | 700727 | QC review | Sam Brooks | L. Bennett |  |  |  | Local | 720
|  | Publishing Package | [5 empty] | 720 |  |  | 348 days | 2025-02-09 | 2025-02-10 | 2026-01-23 | 2026-01-24 | Completed |  | 700728 | Publishing QC | Taylor Chen | L. Bennett |  |  |  | Local | 721
|  |  | Submission Components for an Original Application |  |  |  | Submission Components for an Original Application | 721 |  |  | 6 days | 2025-02-10 | 2025-02-13 | 2025-02-16 |  | In Progress | Regional review underway | 700729 | Authoring | Casey Rivera | N. Ortiz | PDF | Submission_Components_for_an_Original_Application_0729.pdf | Placeholder timeline for reporting test | Local | 722
[7 empty] | Module 1 Administrative Information | 722 |  |  | 270 days | 2025-02-10 | 2025-02-16 | 2025-11-07 |  | In Progress | Metadata check in progress | 700730 | Regional alignment | Alex Kim | A. Shah | PDF | Module_1_Administrative_Information_0730.pdf | Placeholder timeline for reporting test | Local | 723
[5 empty] | 1.1 |  | 1.1 Forms | 723 |  |  | 68 days | 2025-02-11 | 2025-02-09 | 2025-04-20 | 2025-04-19 | Completed | QC completed | 700731 | Archive release | Jordan Patel | R. Gupta | PDF | Forms_0731.pdf | Dummy data added for planning demo | Local | 724
[5 empty] | 1.1.2 |  | 1.1.2 Application form: FDA form 356h | 724 |  |  | 64 days | 2025-02-11 | 2025-02-13 | 2025-04-16 | 2025-04-15 | Completed | Released to archive | 700732 |  | Jamie Carter | R. Gupta | PDF | Application_form_FDA_form_356h_0732.pdf | Dummy data added for planning demo | Local | 725
[5 empty] | 1.1.2 |  | 1.1.2 Attachment to Application form: FDA form 356h | 725 |  |  | 38 days | 2025-02-12 | 2025-02-18 | 2025-03-22 |  | In Progress | Awaiting final source document | 700733 | Authoring | Taylor Chen | R. Gupta | PDF | Attachment_to_Application_form_FDA_form_356h_0733.pdf | Sample entry for dashboard validation | Local | 726
[5 empty] | 1.1.2 |  | 1.1.2 Establishment Information | 726 |  |  | 40 days | 2025-02-13 | 2025-02-14 | 2025-03-25 |  | In Progress | Awaiting final source document | 700734 | Authoring | Jamie Carter | L. Bennett | DOCX | Establishment_Information_0734.docx | Dummy data added for planning demo | Local | 727
[5 empty] | 1.1.3 |  | 1.1.3 User fee cover sheet: FDA form 3397 | 727 |  |  | 46 days | 2025-02-11 | 2025-02-15 | 2025-03-29 | 2025-03-27 | Completed |  | 700735 | Archive release | Taylor Chen | L. Bennett | PDF | User_fee_cover_sheet_FDA_form_3397_0735.pdf | Dummy data added for planning demo | Local | 728
[5 empty] | 1.1.7 |  | 1.1.7 Form FDA 3674: Certification of Compliance | 728 |  |  | 21 days | 2025-02-12 | 2025-02-10 | 2025-03-05 |  | In Progress | Publishing build in progress | 700736 | Publishing prep | Jordan Patel | L. Bennett | PDF | Form_FDA_3674_Certification_of_Compliance_0736.pdf | Dummy data added for planning demo | Local | 729
[5 empty] | 1.2 |  | 1.2 Cover letters | 729 |  |  | 127 days | 2025-02-14 | 2025-02-18 | 2025-06-21 | 2025-06-18 | Completed | Released to archive | 700737 | Archive release | Morgan Lee | R. Gupta | DOCX | Cover_letters_0737.docx | Sample entry for dashboard validation | Local | 730
[5 empty] | 1.2 |  | 1.2 Cover Letter | 730 |  |  | 116 days | 2025-02-10 | 2025-02-15 | 2025-06-06 |  | In Progress | Pending cross-functional signoff | 700738 | Authoring | Casey Rivera | R. Gupta | DOCX | Cover_Letter_0738.docx | Sample entry for dashboard validation | Local | 731
[5 empty] | 1.2 |  | 1.2 Reviewer's Guide | 731 |  |  | 92 days | 2025-02-11 |  | 2025-05-14 |  | Not Started | Planned for upcoming wave | 700739 |  | Alex Kim | N. Ortiz | PDF | Reviewer_s_Guide_0739.pdf | Dummy data added for planning demo | Local | 732
[5 empty] | 1.2 |  | 1.2 Regulatory History | 732 |  |  | 58 days | 2025-02-12 |  | 2025-04-11 |  | Not Started | On hold pending document availability | 700740 |  | Sam Brooks | L. Bennett | PDF | Regulatory_History_0740.pdf | Timing estimate is illustrative | Local | 733
[5 empty] | 1.3 |  | 1.3 Administrative information | 733 |  |  | 69 days | 2025-02-12 | 2025-02-15 | 2025-04-22 |  | In Progress | Pending cross-functional signoff | 700741 | Authoring | Sam Brooks | A. Shah | DOCX | Administrative_information_0741.docx | Dummy data added for planning demo | Local | 734
[5 empty] | 1.3.2 |  | 1.3.2 Field copy Certification | 734 |  |  | 23 days | 2025-02-13 |  | 2025-03-08 |  | Not Started | Planned for upcoming wave | 700742 |  | Morgan Lee | R. Gupta | XLSX | Field_copy_Certification_0742.xlsx | Sample entry for dashboard validation | Local | 735
[5 empty] | 1.3.3 |  | 1.3.3 Debarment certification | 735 |  |  | 64 days | 2025-02-16 | 2025-02-15 | 2025-04-21 | 2025-04-26 | Completed | Released to archive | 700743 | Publishing QC | Jordan Patel | R. Gupta | PDF | Debarment_certification_0743.pdf | Sample entry for dashboard validation | Local | 736
[5 empty] | 1.3.4 |  | 1.3.4 Financial certification and disclosure | 736 |  |  | 62 days | 2025-02-20 | 2025-02-25 | 2025-04-23 | 2025-04-22 | Completed |  | 700744 |  | Sam Brooks | L. Bennett | DOCX | Financial_certification_and_disclosure_0744.docx | Placeholder timeline for reporting test | Local | 737
[5 empty] | 1.3.4 |  | 1.3.4 Financial Disclosure Summary Document | 737 |  |  | 34 days | 2025-02-20 | 2025-02-21 | 2025-03-26 | 2025-04-02 | Completed | Completed as planned | 700745 | Archive release | Taylor Chen | N. Ortiz | PDF | Financial_Disclosure_Summary_Document_0745.pdf | Dummy data added for planning demo | Local | 738
[5 empty] | 1.3.4 |  | 1.3.4 Form 3454 | 738 |  |  | 51 days | 2025-02-15 | 2025-02-12 | 2025-04-07 | 2025-04-13 | Completed | Filed in baseline wave | 700746 |  | Jamie Carter | L. Bennett | PDF | Form_3454_0746.pdf | Sample entry for dashboard validation | Local | 739
[5 empty] | 1.3.4 |  | 1.3.4 Form 3455 | 739 |  |  | 41 days | 2025-02-16 | 2025-02-21 | 2025-03-29 | 2025-04-02 | Completed | QC completed | 700747 | Archive release | Sam Brooks | L. Bennett | PDF | Form_3455_0747.pdf | Dummy data added for planning demo | Local | 740
[5 empty] | 1.3.5 |  | 1.3.5 Patent and exclusivity | 740 |  |  | 34 days | 2025-02-17 |  | 2025-03-23 |  | Not Started | Scheduled after current milestone | 700748 |  | Casey Rivera | M. Sullivan | XLSX | Patent_and_exclusivity_0748.xlsx | Timing estimate is illustrative | Local | 741
[5 empty] | 1.3.5.1 |  | 1.3.5.1 Patent Exclusivity | 741 |  |  | 13 days | 2025-02-22 | 2025-02-25 | 2025-03-07 | 2025-03-05 | Completed | QC completed | 700749 |  | Sam Brooks | A. Shah | PDF | Patent_Exclusivity_0749.pdf | Sample entry for dashboard validation | Local | 742
[5 empty] | 1.3.5.1 |  | 1.3.5.1 Patent Information Submitted Upon and After Approval of an NDA or Supplement | 742 |  |  | 30 days | 2025-02-17 | 2025-02-14 | 2025-03-19 | 2025-03-22 | Completed | Filed in baseline wave | 700750 | Archive release | Alex Kim | L. Bennett | DOCX | Patent_Information_Submitted_Upon_and_After_Approval_of_an_N_0750.docx | Placeholder timeline for reporting test | Local | 743
[5 empty] | 1.3.5.1 |  | 1.3.5.1 Patent information | 743 |  |  | 10 days | 2025-02-21 |  | 2025-03-03 |  | Not Started | Planned for upcoming wave | 700751 |  | Morgan Lee | L. Bennett | PDF | Patent_information_0751.pdf | Timing estimate is illustrative | Local | 744
[5 empty] | 1.3.5.3 |  | 1.3.5.3 Exclusivity request | 744 |  |  | 23 days | 2025-02-24 | 2025-02-26 | 2025-03-19 | 2025-03-15 | Completed | Released to archive | 700752 | Archive release | Morgan Lee | A. Shah | PDF | Exclusivity_request_0752.pdf | Sample entry for dashboard validation | Local | 746
[5 empty] | 1.4 |  | 1.4 Information about the Expert | 745 |  |  | 69 days | 2025-02-24 | 2025-02-27 | 2025-05-04 | 2025-05-02 | Completed |  | 700753 | Archive release | Taylor Chen | M. Sullivan | DOCX | Information_about_the_Expert_0753.docx | Sample entry for dashboard validation | Central | 747
[5 empty] | 1.4.1 |  | 1.4.1 Information about the Expert - Quality CV | 746 |  |  | 63 days | 2025-02-20 | 2025-02-20 | 2025-04-24 | 2025-04-21 | Completed | Filed in baseline wave | 700754 | Publishing QC | Alex Kim | A. Shah | DOCX | Information_about_the_Expert_Quality_CV_0754.docx | Timing estimate is illustrative | Central | 748
[5 empty] | 1.4.1 |  | 1.4.1 Information about the Expert - Quality Declaration | 747 |  |  | 54 days | 2025-02-20 | 2025-02-20 | 2025-04-15 | 2025-04-20 | Completed | Released to archive | 700755 |  | Casey Rivera | A. Shah | PDF | Information_about_the_Expert_Quality_Declaration_0755.pdf | Placeholder timeline for reporting test | Central | 749
[5 empty] | 1.4.2 |  | 1.4.2 Information about the Expert - Nonclinical CV | 748 |  |  | 33 days | 2025-02-27 | 2025-02-27 | 2025-04-01 | 2025-04-02 | Completed | QC completed | 700756 |  | Morgan Lee | A. Shah | PDF | Information_about_the_Expert_Nonclinical_CV_0756.pdf | Timing estimate is illustrative | Central | 750
[5 empty] | 1.4.2 |  | 1.4.2 Information about the Expert - Nonclinical Declaration | 749 |  |  | 64 days | 2025-03-01 | 2025-03-03 | 2025-05-04 |  | In Progress | Regional review underway | 700757 | QC review | Jordan Patel | R. Gupta | PDF | Information_about_the_Expert_Nonclinical_Declaration_0757.pdf | Timing estimate is illustrative | Central | 751
[5 empty] | 1.4.3 |  | 1.4.3 Information about the Expert - Clinical CV | 750 |  |  | 41 days | 2025-02-23 | 2025-02-23 | 2025-04-05 |  | In Progress | Draft in QC review | 700758 | Regional alignment | Casey Rivera | R. Gupta | PDF | Information_about_the_Expert_Clinical_CV_0758.pdf | Timing estimate is illustrative | Central | 752
[5 empty] | 1.4.3 |  | 1.4.3 Information about the Expert - Clinical Declaration | 751 |  |  | 24 days | 2025-02-26 | 2025-02-23 | 2025-03-22 | 2025-03-27 | Completed | QC completed | 700759 |  | Taylor Chen | A. Shah | DOCX | Information_about_the_Expert_Clinical_Declaration_0759.docx | Timing estimate is illustrative | Central | 753
[5 empty] | 1.6 |  | 1.6 Meetings | 752 |  |  | 59 days | 2025-03-02 | 2025-02-27 | 2025-04-30 | 2025-05-05 | Completed | QC completed | 700760 | Submission build | Taylor Chen | M. Sullivan | PDF | Meetings_0760.pdf | Timing estimate is illustrative | Central | 754
[5 empty] | 1.6.3 |  | 1.6.3 Correspondence regarding meetings | 753 |  |  | 26 days | 2025-02-24 | 2025-02-26 | 2025-03-22 | 2025-03-25 | Completed | Released to archive | 700761 | Archive release | Taylor Chen | R. Gupta | XLSX | Correspondence_regarding_meetings_0761.xlsx | Sample entry for dashboard validation | Central | 755
[5 empty] | 1.9 |  | 1.9 Pediatric administrative information | 754 |  |  | 91 days | 2025-02-28 | 2025-03-02 | 2025-05-30 | 2025-05-30 | Completed | QC completed | 700762 |  | Jamie Carter | M. Sullivan | DOCX | Pediatric_administrative_information_0762.docx | Dummy data added for planning demo | Central | 756
[5 empty] | 1.9.6 |  | 1.9.6 Agreed – Initial Pediatric Study Plan | 755 |  |  | 63 days | 2025-02-28 | 2025-02-25 | 2025-05-02 | 2025-04-30 | Completed | Released to archive | 700763 | Submission build | Sam Brooks | N. Ortiz | PDF | Agreed_Initial_Pediatric_Study_Plan_0763.pdf | Sample entry for dashboard validation | Central | 757
[5 empty] | 1.12 |  | 1.12 Other correspondence | 756 |  |  | 76 days | 2025-02-25 | 2025-03-01 | 2025-05-12 |  | In Progress | Metadata check in progress | 700764 | QC review | Sam Brooks | A. Shah | PDF | Other_correspondence_0764.pdf | Sample entry for dashboard validation | Central | 760
[5 empty] | 1.12.14 |  | 1.12.14 Request for Categorical Exclusion | 757 |  |  | 37 days | 2025-02-27 | 2025-03-05 | 2025-04-05 |  | In Progress | Publishing build in progress | 700765 |  | Jordan Patel | R. Gupta | XLSX | Request_for_Categorical_Exclusion_0765.xlsx | Placeholder timeline for reporting test | Central | 762
[5 empty] | 1.14 |  | 1.14 Labeling | 758 |  |  | 95 days | 2025-03-03 | 2025-03-05 | 2025-06-06 |  | In Progress | Metadata check in progress | 700766 | QC review | Alex Kim | M. Sullivan | DOCX | Labeling_0766.docx | Dummy data added for planning demo | Central | 763
[5 empty] | 1.14.1 |  | 1.14.1 Draft labeling | 759 |  |  | 70 days | 2025-03-05 | 2025-03-07 | 2025-05-14 | 2025-05-14 | Completed | Completed as planned | 700767 | Publishing QC | Casey Rivera | N. Ortiz | DOCX | Draft_labeling_0767.docx | Timing estimate is illustrative | Central | 764
[5 empty] | 1.14.1.1 |  | 1.14.1.1 Draft carton and container labels | 760 |  |  | 16 days | 2025-03-07 | 2025-03-07 | 2025-03-23 |  | In Progress | Metadata check in progress | 700768 | Regional alignment | Morgan Lee | A. Shah | DOCX | Draft_carton_and_container_labels_0768.docx | Dummy data added for planning demo | Central | 765
[5 empty] | 1.14.1.2 |  | 1.14.1.2 Annotated draft labeling text | 761 |  |  | 8 days | 2025-03-07 | 2025-03-05 | 2025-03-15 | 2025-03-11 | Completed | Released to archive | 700769 | Archive release | Alex Kim | L. Bennett | DOCX | Annotated_draft_labeling_text_0769.docx | Dummy data added for planning demo | Central | 766
[5 empty] | 1.14.1.3 |  | 1.14.1.3 Draft labeling text | 762 |  |  | 15 days | 2025-03-01 | 2025-03-02 | 2025-03-16 | 2025-03-20 | Completed |  | 700770 | Submission build | Alex Kim | R. Gupta | PDF | Draft_labeling_text_0770.pdf | Timing estimate is illustrative | Central | 767
[5 empty] | 1.14.1.4 |  | 1.14.1.4 Label comprehension studies | 763 |  |  | 25 days | 2025-03-07 |  | 2025-04-01 |  | Not Started | Waiting on dependency from Module 3 | 700771 |  | Jordan Patel | A. Shah | DOCX | Label_comprehension_studies_0771.docx | Placeholder timeline for reporting test | Central | 768
[5 empty] | 1.18 |  | 1.18 Proprietary names | 764 |  |  | 131 days | 2025-03-05 | 2025-03-09 | 2025-07-14 |  | In Progress | Publishing build in progress | 700772 | Authoring | Morgan Lee | R. Gupta | XLSX | Proprietary_names_0772.xlsx | Placeholder timeline for reporting test | Central | 777
[5 empty] | 1.20 |  | 1.20 Study Data Standardization Plan | 765 |  |  | 117 days | 2025-03-04 | 2025-03-06 | 2025-06-29 | 2025-07-04 | Completed | Filed in baseline wave | 700773 | Submission build | Morgan Lee | N. Ortiz | PDF | Study_Data_Standardization_Plan_0773.pdf | Timing estimate is illustrative | Central | 778
[5 empty] | 2 |  | Module 2 Summaries | 766 |  |  | 168 days | 2025-03-07 | 2025-03-11 | 2025-08-22 | 2025-08-26 | Completed | Filed in baseline wave | 700774 |  | Jamie Carter | L. Bennett | PDF | Module_2_Summaries_0774.pdf | Timing estimate is illustrative | Central | 779
[5 empty] | 2.2 |  | 2.2 Introduction [hypercholest] | 767 |  |  | 101 days | 2025-03-12 | 2025-03-18 | 2025-06-21 |  | In Progress | Regional review underway | 700775 | Publishing prep | Casey Rivera | R. Gupta | DOCX | Introduction_hypercholest_0775.docx | Sample entry for dashboard validation | Central | 780
[5 empty] | 2.3 |  | Module 2.3 Quality Overall Summary (VDOC) | 768 |  |  | 97 days | 2025-03-10 | 2025-03-15 | 2025-06-15 | 2025-06-11 | Completed | Released to archive | 700776 | Publishing QC | Jamie Carter | N. Ortiz | DOCX | Module_2_3_Quality_Overall_Summary_VDOC_0776.docx | Timing estimate is illustrative | Central | 781
[5 empty] | 2.4 |  | 2.4 Nonclinical overview | 769 |  |  | 92 days | 2025-03-13 | 2025-03-18 | 2025-06-13 | 2025-06-18 | Completed | QC completed | 700777 | Publishing QC | Jamie Carter | L. Bennett | PDF | Nonclinical_overview_0777.pdf | Sample entry for dashboard validation | Central | 782
[5 empty] | 2.5 |  | 2.5 Clinical overview [hypercholest] | 770 |  |  | 104 days | 2025-03-05 | 2025-03-11 | 2025-06-17 |  | In Progress | Publishing build in progress | 700778 | Authoring | Alex Kim | A. Shah | DOCX | Clinical_overview_hypercholest_0778.docx | Dummy data added for planning demo | Central | 783
[5 empty] | 2.6 |  | 2.6 Nonclinical written and tabulated summaries | 771 |  |  | 121 days | 2025-03-11 | 2025-03-12 | 2025-07-10 | 2025-07-15 | Completed | Released to archive | 700779 | Archive release | Jamie Carter | A. Shah | PDF | Nonclinical_written_and_tabulated_summaries_0779.pdf | Dummy data added for planning demo | Central | 784
[5 empty] | 2.6.1 |  | 2.6.1 Introduction | 772 |  |  | 53 days | 2025-03-10 | 2025-03-14 | 2025-05-02 | 2025-04-30 | Completed | Filed in baseline wave | 700780 | Submission build | Morgan Lee | R. Gupta | XLSX | Introduction_0780.xlsx | Dummy data added for planning demo | Central | 785
[5 empty] | 2.6.2 |  | 2.6.2 Pharmacology written summary | 773 |  |  | 59 days | 2025-03-14 | 2025-03-13 | 2025-05-12 |  | In Progress | Draft in QC review | 700781 | Authoring | Jordan Patel | M. Sullivan | PDF | Pharmacology_written_summary_0781.pdf | Dummy data added for planning demo | Central | 786
[5 empty] | 2.6.3 |  | 2.6.3 Pharmacology tabulated summary | 774 |  |  | 33 days | 2025-03-11 | 2025-03-08 | 2025-04-13 | 2025-04-17 | Completed | Released to archive | 700782 |  | Alex Kim | A. Shah | DOCX | Pharmacology_tabulated_summary_0782.docx | Sample entry for dashboard validation | Central | 787
[5 empty] | 2.6.4 |  | 2.6.4 Pharmacokinetic written summary | 775 |  |  | 31 days | 2025-03-15 | 2025-03-21 | 2025-04-15 |  | In Progress | Metadata check in progress | 700783 |  | Sam Brooks | L. Bennett | PDF | Pharmacokinetic_written_summary_0783.pdf | Sample entry for dashboard validation | Central | 788
[5 empty] | 2.6.5 |  | 2.6.5 Pharmacokinetic tabulated summary | 776 |  |  | 60 days | 2025-03-11 | 2025-03-10 | 2025-05-10 | 2025-05-17 | Completed | Filed in baseline wave | 700784 | Submission build | Taylor Chen | M. Sullivan | PDF | Pharmacokinetic_tabulated_summary_0784.pdf | Sample entry for dashboard validation | Central | 789
[5 empty] | 2.6.6 |  | 2.6.6 Toxicology written summary | 777 |  |  | 38 days | 2025-03-17 | 2025-03-15 | 2025-04-24 | 2025-04-29 | Completed | Released to archive | 700785 | Archive release | Sam Brooks | R. Gupta | DOCX | Toxicology_written_summary_0785.docx | Sample entry for dashboard validation | Central | 790
[5 empty] | 2.6.7 |  | 2.6.7 Toxicology tabulated summary | 778 |  |  | 49 days | 2025-03-11 | 2025-03-14 | 2025-04-29 | 2025-04-27 | Completed | Completed as planned | 700786 | Archive release | Casey Rivera | A. Shah | DOCX | Toxicology_tabulated_summary_0786.docx | Dummy data added for planning demo | Central | 791
[5 empty] | 2.7 |  | 2.7 Clinical summary | 779 |  |  | 49 days | 2025-03-15 | 2025-03-20 | 2025-05-03 |  | In Progress | Draft in QC review | 700787 | Publishing prep | Jordan Patel | L. Bennett | DOCX | Clinical_summary_0787.docx | Placeholder timeline for reporting test | Central | 792
[5 empty] | 2.7.1 |  | 2.7.1 Summary of Biopharmaceutic Studies and Associated Analytical Methods | 780 |  |  | 30 days | 2025-03-11 | 2025-03-16 | 2025-04-10 | 2025-04-09 | Completed | QC completed | 700788 |  | Casey Rivera | M. Sullivan | PDF | Summary_of_Biopharmaceutic_Studies_and_Associated_Analytical_0788.pdf | Timing estimate is illustrative | Central | 793
[5 empty] | 2.7.2 |  | 2.7.2 Summary of Clinical Pharmacology studies [Indication Suffix] | 781 |  |  | 42 days | 2025-03-14 | 2025-03-17 | 2025-04-25 |  | In Progress | Publishing build in progress | 700789 | QC review | Morgan Lee | R. Gupta | DOCX | Summary_of_Clinical_Pharmacology_studies_Indication_Suffix_0789.docx | Dummy data added for planning demo | Central | 794
[5 empty] | 2.7.3 |  | 2.7.3 Summary of Clinical Efficacy [Indication Suffix] | 782 |  |  | 44 days | 2025-03-20 |  | 2025-05-03 |  | Not Started | Resource assignment not yet confirmed | 700790 |  | Sam Brooks | N. Ortiz | DOCX | Summary_of_Clinical_Efficacy_Indication_Suffix_0790.docx | Timing estimate is illustrative | Central | 795
[5 empty] | 2.7.4 |  | 2.7.4 Summary of Clinical Safety [Indication Suffix] | 783 |  |  | 57 days | 2025-03-18 |  | 2025-05-14 |  | Not Started | Waiting on dependency from Module 3 | 700791 |  | Taylor Chen | M. Sullivan | DOCX | Summary_of_Clinical_Safety_Indication_Suffix_0791.docx | Dummy data added for planning demo | Central | 796
[5 empty] | 2.7.5 |  | 2.7.5 References | 784 |  |  | 21 days | 2025-03-14 | 2025-03-14 | 2025-04-04 |  | In Progress | Awaiting final source document | 700792 | Authoring | Sam Brooks | A. Shah | DOCX | References_0792.docx | Sample entry for dashboard validation | Central | 797
[5 empty] | 2.7.6 |  | 2.7.6 Synopses of individual studies | 785 |  |  | 68 days | 2025-03-20 | 2025-03-20 | 2025-05-27 | 2025-05-24 | Completed | Filed in baseline wave | 700793 |  | Jamie Carter | L. Bennett | PDF | Synopses_of_individual_studies_0793.pdf | Dummy data added for planning demo | Central | 798
[7 empty] | Module 3 Quality | 786 |  |  | 178 days | 2025-03-19 | 2025-03-17 | 2025-09-13 | 2025-09-16 | Completed | QC completed | 700794 |  | Sam Brooks | A. Shah | PDF | Module_3_Quality_0794.pdf | Placeholder timeline for reporting test | Central | 800
[5 empty] | 3.0 |  | US Module 3 (VDOC) | 787 |  |  | 134 days | 2025-03-17 | 2025-03-16 | 2025-07-29 | 2025-08-04 | Completed |  | 700795 |  | Jordan Patel | N. Ortiz | DOCX | US_Module_3_VDOC_0795.docx | Sample entry for dashboard validation | Central | 801
[5 empty] | 4 |  | Module 4 Nonclinical Study Reports | 788 |  |  | 163 days | 2025-03-23 | 2025-03-22 | 2025-09-02 | 2025-09-04 | Completed |  | 700796 | Submission build | Alex Kim | M. Sullivan | PDF | Module_4_Nonclinical_Study_Reports_0796.pdf | Dummy data added for planning demo | Central | 802
[5 empty] | 4.2 |  | 4.2 Study reports | 789 |  |  | 49 days | 2025-03-20 | 2025-03-18 | 2025-05-08 |  | In Progress | Metadata check in progress | 700797 | Regional alignment | Taylor Chen | M. Sullivan | PDF | Study_reports_0797.pdf | Placeholder timeline for reporting test | Central | 803
[5 empty] | 4.2.1 |  | 4.2.1 Pharmacology | 790 |  |  | 63 days | 2025-03-20 | 2025-03-26 | 2025-05-22 |  | In Progress | Publishing build in progress | 700798 | QC review | Jamie Carter | N. Ortiz | XLSX | Pharmacology_0798.xlsx | Sample entry for dashboard validation | Central | 804
[5 empty] | 4.2.1.1 |  | 4.2.1.1 Primary pharmacodynamics | 791 |  |  | 18 days | 2025-03-26 | 2025-03-31 | 2025-04-13 | 2025-04-11 | Completed | Completed as planned | 700799 |  | Casey Rivera | L. Bennett | PDF | Primary_pharmacodynamics_0799.pdf | Dummy data added for planning demo | Central | 805
[5 empty] | 4.2.1.1 |  | Study report [pd001mk0001] and related information | 792 |  |  | 32 days | 2025-03-21 | 2025-03-19 | 2025-04-22 | 2025-04-19 | Completed | Released to archive | 700800 | Submission build | Alex Kim | M. Sullivan | DOCX | Study_report_pd001mk0001_and_related_information_0800.docx | Dummy data added for planning demo | Central | 806
[5 empty] | 4.2.1.1 |  | Study report [pd002mk0001] and related information | 793 |  |  | 33 days | 2025-03-22 |  | 2025-04-24 |  | Not Started | Waiting on dependency from Module 3 | 700801 |  | Casey Rivera | R. Gupta | PDF | Study_report_pd002mk0001_and_related_information_0801.pdf | Timing estimate is illustrative | Central | 807
[5 empty] | 4.2.1.1 |  | Study report [pd004mk0001] and related information | 794 |  |  | 9 days | 2025-03-24 | 2025-03-24 | 2025-04-02 | 2025-04-06 | Completed |  | 700802 |  | Morgan Lee | L. Bennett | PDF | Study_report_pd004mk0001_and_related_information_0802.pdf | Dummy data added for planning demo | Central | 808
[5 empty] | 4.2.1.1 |  | Study report [pd005mk0001] and related information | 795 |  |  | 15 days | 2025-03-28 | 2025-03-26 | 2025-04-12 |  | In Progress | Metadata check in progress | 700803 | Regional alignment | Morgan Lee | N. Ortiz | DOCX | Study_report_pd005mk0001_and_related_information_0803.docx | Dummy data added for planning demo | Central | 809
[5 empty] | 4.2.1.2 |  | 4.2.1.2 Secondary pharmacodynamics | 796 |  |  | 13 days | 2025-03-23 | 2025-03-25 | 2025-04-05 | 2025-04-11 | Completed | Completed as planned | 700804 | Submission build | Casey Rivera | A. Shah | XLSX | Secondary_pharmacodynamics_0804.xlsx | Dummy data added for planning demo | Central | 810
[5 empty] | 4.2.1.2 |  | Study report [pd003mk0001] and related information | 797 |  |  | 9 days | 2025-03-27 |  | 2025-04-05 |  | Not Started | Resource assignment not yet confirmed | 700805 |  | Sam Brooks | M. Sullivan | PDF | Study_report_pd003mk0001_and_related_information_0805.pdf | Sample entry for dashboard validation | Central | 811
[5 empty] | 4.2.1.2 |  | Study report [tt175072fin] and related information | 798 |  |  | 15 days | 2025-03-24 | 2025-03-23 | 2025-04-08 |  | In Progress | Draft in QC review | 700806 | Regional alignment | Taylor Chen | N. Ortiz | DOCX | Study_report_tt175072fin_and_related_information_0806.docx | Sample entry for dashboard validation | Central | 812
[5 empty] | 4.2.1.3 |  | 4.2.1.3 Safety pharmacology | 799 |  |  | 16 days | 2025-03-30 | 2025-03-31 | 2025-04-15 |  | In Progress | Draft in QC review | 700807 | Authoring | Alex Kim | N. Ortiz | XLSX | Safety_pharmacology_0807.xlsx | Sample entry for dashboard validation | Central | 813
[5 empty] | 4.2.1.3 |  | Study report [tt172962fin] and related information | 800 |  |  | 24 days | 2025-03-24 | 2025-03-27 | 2025-04-17 | 2025-04-19 | Completed | Filed in baseline wave | 700808 |  | Sam Brooks | L. Bennett | PDF | Study_report_tt172962fin_and_related_information_0808.pdf | Dummy data added for planning demo | Central | 814
[5 empty] | 4.2.1.3 |  | Study report [tt184703fin] and related information | 801 |  |  | 10 days | 2025-03-31 | 2025-04-03 | 2025-04-10 |  | In Progress | Metadata check in progress | 700809 | QC review | Morgan Lee | L. Bennett | PDF | Study_report_tt184703fin_and_related_information_0809.pdf | Timing estimate is illustrative | Central | 815
[5 empty] | 4.2.1.3 |  | Study report [tt185801fin] and related information | 802 |  |  | 9 days | 2025-03-28 | 2025-03-29 | 2025-04-06 |  | In Progress | Publishing build in progress | 700810 |  | Taylor Chen | A. Shah | PDF | Study_report_tt185801fin_and_related_information_0810.pdf | Timing estimate is illustrative | Central | 816
[5 empty] | 4.2.1.3 |  | Study report [tt185803fin] and related information | 803 |  |  | 9 days | 2025-03-25 | 2025-03-29 | 2025-04-03 | 2025-04-01 | Completed | QC completed | 700811 | Publishing QC | Morgan Lee | R. Gupta | PDF | Study_report_tt185803fin_and_related_information_0811.pdf | Placeholder timeline for reporting test | Central | 817
[5 empty] | 4.2.1.3 |  | Study report [tt185900fin] and related information | 804 |  |  | 26 days | 2025-03-28 | 2025-03-26 | 2025-04-23 | 2025-04-29 | Completed | Completed as planned | 700812 | Publishing QC | Morgan Lee | M. Sullivan | PDF | Study_report_tt185900fin_and_related_information_0812.pdf | Sample entry for dashboard validation | Central | 818
[5 empty] | 4.2.1.3 |  | Study report [tt195900fin] and related information | 805 |  |  | 35 days | 2025-04-01 |  | 2025-05-06 |  | Not Started | Pending authoring start | 700813 |  | Casey Rivera | R. Gupta | DOCX | Study_report_tt195900fin_and_related_information_0813.docx | Placeholder timeline for reporting test | Central | 819
[5 empty] | 4.2.2 |  | 4.2.2 Pharmacokinetics | 806 |  |  | 53 days | 2025-03-30 | 2025-04-02 | 2025-05-22 |  | In Progress | Regional review underway | 700814 |  | Taylor Chen | A. Shah | PDF | Pharmacokinetics_0814.pdf | Placeholder timeline for reporting test | Central | 820
[5 empty] | 4.2.2.1 |  | 4.2.2.1 Analytical methods and validation reports | 807 |  |  | 29 days | 2025-04-03 |  | 2025-05-02 |  | Not Started | Scheduled after current milestone | 700815 |  | Morgan Lee | A. Shah | PDF | Analytical_methods_and_validation_reports_0815.pdf | Timing estimate is illustrative | Central | 821
[5 empty] | 4.2.2.1 |  | Study report [055DG9] and related information | 808 |  |  | 14 days | 2025-04-05 | 2025-04-10 | 2025-04-19 | 2025-04-18 | Completed | Completed as planned | 700816 | Archive release | Sam Brooks | N. Ortiz | PDF | Study_report_055DG9_and_related_information_0816.pdf | Timing estimate is illustrative | Central | 822
[5 empty] | 4.2.2.1 |  | Study report [05FRC2] and related information | 809 |  |  | 27 days | 2025-04-05 | 2025-04-04 | 2025-05-02 |  | In Progress | Draft in QC review | 700817 | Regional alignment | Jamie Carter | A. Shah | DOCX | Study_report_05FRC2_and_related_information_0817.docx | Placeholder timeline for reporting test | Central | 823
[5 empty] | 4.2.2.1 |  | Study report [07XM2X] and related information | 810 |  |  | 16 days | 2025-04-05 | 2025-04-04 | 2025-04-21 |  | In Progress | Draft in QC review | 700818 | Publishing prep | Jamie Carter | M. Sullivan | DOCX | Study_report_07XM2X_and_related_information_0818.docx | Sample entry for dashboard validation | Central | 824
[5 empty] | 4.2.2.1 |  | Study report [08WH66] and related information | 811 |  |  | 34 days | 2025-03-30 | 2025-04-03 | 2025-05-03 | 2025-04-29 | Completed | Filed in baseline wave | 700819 | Submission build | Casey Rivera | N. Ortiz | DOCX | Study_report_08WH66_and_related_information_0819.docx | Dummy data added for planning demo | Central | 825
[5 empty] | 4.2.2.1 |  | Study report [08WQR8] and related information | 812 |  |  | 8 days | 2025-04-04 | 2025-04-06 | 2025-04-12 | 2025-04-08 | Completed |  | 700820 | Archive release | Jamie Carter | R. Gupta | PDF | Study_report_08WQR8_and_related_information_0820.pdf | Dummy data added for planning demo | Central | 826
[5 empty] | 4.2.2.1 |  | Study report [08WQRR] and related information | 813 |  |  | 30 days | 2025-04-06 | 2025-04-10 | 2025-05-06 |  | In Progress | Publishing build in progress | 700821 | Authoring | Jamie Carter | A. Shah | DOCX | Study_report_08WQRR_and_related_information_0821.docx | Placeholder timeline for reporting test | Central | 827
[5 empty] | 4.2.2.1 |  | Study report [08WQSF] and related information | 814 |  |  | 21 days | 2025-04-09 | 2025-04-14 | 2025-04-30 | 2025-04-30 | Completed | Filed in baseline wave | 700822 |  | Casey Rivera | N. Ortiz | PDF | Study_report_08WQSF_and_related_information_0822.pdf | Dummy data added for planning demo | Central | 828
[5 empty] | 4.2.2.2 |  | 4.2.2.2 Absorption | 815 |  |  | 32 days | 2025-04-06 | 2025-04-08 | 2025-05-08 |  | In Progress | Draft in QC review | 700823 | QC review | Jamie Carter | M. Sullivan | DOCX | Absorption_0823.docx | Placeholder timeline for reporting test | Central | 829
[5 empty] | 4.2.2.2 |  | Study report [pk001mk0001] and related information | 816 |  |  | 8 days | 2025-04-08 | 2025-04-11 | 2025-04-16 |  | In Progress | Metadata check in progress | 700824 | Publishing prep | Jamie Carter | M. Sullivan | PDF | Study_report_pk001mk0001_and_related_information_0824.pdf | Dummy data added for planning demo | Central | 830
[5 empty] | 4.2.2.3 |  | 4.2.2.3 Distribution | 817 |  |  | 25 days | 2025-04-07 | 2025-04-09 | 2025-05-02 |  | In Progress | Awaiting final source document | 700825 | Regional alignment | Casey Rivera | A. Shah | DOCX | Distribution_0825.docx | Dummy data added for planning demo | Central | 831
[5 empty] | 4.2.2.3 |  | Study report [PK002mk0001] and related information | 818 |  |  | 8 days | 2025-04-11 |  | 2025-04-19 |  | Not Started | Scheduled after current milestone | 700826 |  | Sam Brooks | M. Sullivan | PDF | Study_report_PK002mk0001_and_related_information_0826.pdf | Sample entry for dashboard validation | Central | 832
[5 empty] | 4.2.2.3 |  | Study report [pk014mk0001] and related information | 819 |  |  | 25 days | 2025-04-04 |  | 2025-04-29 |  | Not Started | Waiting on dependency from Module 3 | 700827 |  | Taylor Chen | M. Sullivan | DOCX | Study_report_pk014mk0001_and_related_information_0827.docx | Dummy data added for planning demo | Central | 833
[5 empty] | 4.2.2.3 |  | Study report [pk015mk0001] and related information | 820 |  |  | 12 days | 2025-04-12 | 2025-04-13 | 2025-04-24 | 2025-04-24 | Completed | Released to archive | 700828 | Submission build | Jordan Patel | N. Ortiz | PDF | Study_report_pk015mk0001_and_related_information_0828.pdf | Dummy data added for planning demo | Central | 834
[5 empty] | 4.2.2.3 |  | Study report [tt247090] and related information | 821 |  |  | 10 days | 2025-04-08 | 2025-04-08 | 2025-04-18 |  | In Progress | Regional review underway | 700829 |  | Jamie Carter | L. Bennett | DOCX | Study_report_tt247090_and_related_information_0829.docx | Dummy data added for planning demo | Central | 835
[5 empty] | 4.2.2.4 |  | 4.2.2.4 Metabolism | 822 |  |  | 29 days | 2025-04-14 | 2025-04-15 | 2025-05-13 | 2025-05-13 | Completed | Completed as planned | 700830 | Archive release | Taylor Chen | A. Shah | XLSX | Metabolism_0830.xlsx | Timing estimate is illustrative | Central | 836
[5 empty] | 4.2.2.4 |  | Study report [PK018mk0001] and related information | 823 |  |  | 10 days | 2025-04-12 | 2025-04-16 | 2025-04-22 | 2025-04-19 | Completed |  | 700831 | Publishing QC | Jordan Patel | N. Ortiz | DOCX | Study_report_PK018mk0001_and_related_information_0831.docx | Placeholder timeline for reporting test | Central | 837
[5 empty] | 4.2.2.5 |  | 4.2.2.5 Excretion | 824 |  |  | 9 days | 2025-04-13 | 2025-04-15 | 2025-04-22 |  | In Progress | Awaiting final source document | 700832 | Authoring | Morgan Lee | M. Sullivan | DOCX | Excretion_0832.docx | Placeholder timeline for reporting test | Central | 838
[5 empty] | 4.2.2.5 |  | Study report [pk003mk0001] and related information | 825 |  |  | 35 days | 2025-04-14 | 2025-04-19 | 2025-05-19 |  | In Progress | Metadata check in progress | 700833 |  | Alex Kim | N. Ortiz | DOCX | Study_report_pk003mk0001_and_related_information_0833.docx | Dummy data added for planning demo | Central | 839
[5 empty] | 4.2.2.5 |  | Study report [pk009mk0001] and related information | 826 |  |  | 11 days | 2025-04-12 |  | 2025-04-23 |  | Not Started | Planned for upcoming wave | 700834 |  | Alex Kim | M. Sullivan | PDF | Study_report_pk009mk0001_and_related_information_0834.pdf | Placeholder timeline for reporting test | Central | 840
[5 empty] | 4.2.2.5 |  | Study report [pk010mk0001] and related information | 827 |  |  | 29 days | 2025-04-17 | 2025-04-23 | 2025-05-16 |  | In Progress | Pending cross-functional signoff | 700835 | Publishing prep | Jordan Patel | L. Bennett | PDF | Study_report_pk010mk0001_and_related_information_0835.pdf | Timing estimate is illustrative | Central | 841
[5 empty] | 4.2.2.5 |  | Study report [pk013mk0001] and related information | 828 |  |  | 31 days | 2025-04-16 |  | 2025-05-17 |  | Not Started | Planned for upcoming wave | 700836 |  | Alex Kim | N. Ortiz | DOCX | Study_report_pk013mk0001_and_related_information_0836.docx | Dummy data added for planning demo | Central | 842
[5 empty] | 4.2.2.6 |  | 4.2.2.6 Pharmacokinetic drug interactions | 829 |  |  | 32 days | 2025-04-18 | 2025-04-22 | 2025-05-20 | 2025-05-26 | Completed |  | 700837 |  | Casey Rivera | R. Gupta | DOCX | Pharmacokinetic_drug_interactions_0837.docx | Timing estimate is illustrative | Central | 843
[5 empty] | 4.2.2.6 |  | Study report [pk004mk0001] and related information | 830 |  |  | 14 days | 2025-04-15 | 2025-04-17 | 2025-04-29 | 2025-04-28 | Completed | Released to archive | 700838 | Archive release | Sam Brooks | A. Shah | PDF | Study_report_pk004mk0001_and_related_information_0838.pdf | Sample entry for dashboard validation | Central | 844
[5 empty] | 4.2.2.6 |  | Study report [pk005mk0001] and related information | 831 |  |  | 18 days | 2025-04-17 | 2025-04-22 | 2025-05-05 | 2025-05-09 | Completed | Completed as planned | 700839 | Archive release | Sam Brooks | L. Bennett | PDF | Study_report_pk005mk0001_and_related_information_0839.pdf | Sample entry for dashboard validation | Central | 845
[5 empty] | 4.2.2.6 |  | Study report [pk006mk0001] and related information | 832 |  |  | 14 days | 2025-04-18 | 2025-04-18 | 2025-05-02 |  | In Progress | Pending cross-functional signoff | 700840 | QC review | Jamie Carter | L. Bennett | PDF | Study_report_pk006mk0001_and_related_information_0840.pdf | Placeholder timeline for reporting test | Central | 846
[5 empty] | 4.2.2.6 |  | Study report [pk007mk0001] and related information | 833 |  |  | 17 days | 2025-04-17 | 2025-04-15 | 2025-05-04 | 2025-05-06 | Completed | Released to archive | 700841 |  | Jordan Patel | M. Sullivan | DOCX | Study_report_pk007mk0001_and_related_information_0841.docx | Timing estimate is illustrative | Central | 847
[5 empty] | 4.2.2.6 |  | Study report [pk008mk0001] and related information | 834 |  |  | 35 days | 2025-04-15 | 2025-04-14 | 2025-05-20 | 2025-05-17 | Completed | Released to archive | 700842 | Archive release | Jamie Carter | M. Sullivan | DOCX | Study_report_pk008mk0001_and_related_information_0842.docx | Dummy data added for planning demo | Central | 848
[5 empty] | 4.2.2.6 |  | Study report [pk016mk0001] and related information | 835 |  |  | 34 days | 2025-04-16 | 2025-04-19 | 2025-05-20 | 2025-05-16 | Completed | Filed in baseline wave | 700843 | Publishing QC | Jordan Patel | M. Sullivan | DOCX | Study_report_pk016mk0001_and_related_information_0843.docx | Sample entry for dashboard validation | Central | 849
[5 empty] | 4.2.2.6 |  | Study report [pk017mk0001] and related information | 836 |  |  | 11 days | 2025-04-19 | 2025-04-24 | 2025-04-30 | 2025-04-29 | Completed | QC completed | 700844 | Publishing QC | Morgan Lee | R. Gupta | PDF | Study_report_pk017mk0001_and_related_information_0844.pdf | Dummy data added for planning demo | Central | 850
[5 empty] | 4.2.2.6 |  | Study report [PK020mk0001] and related information | 837 |  |  | 30 days | 2025-04-16 |  | 2025-05-16 |  | Not Started | Scheduled after current milestone | 700845 |  | Casey Rivera | L. Bennett | DOCX | Study_report_PK020mk0001_and_related_information_0845.docx | Placeholder timeline for reporting test | Central | 851
[5 empty] | 4.2.2.7 |  | 4.2.2.7 Other pharmacokinetic studies | 838 |  |  | 29 days | 2025-04-23 | 2025-04-22 | 2025-05-22 | 2025-05-29 | Completed |  | 700846 |  | Alex Kim | N. Ortiz | PDF | Other_pharmacokinetic_studies_0846.pdf | Placeholder timeline for reporting test | Central | 852
[5 empty] | 4.2.2.7 |  | Study report [PK012mk0001] and related information | 839 |  |  | 19 days | 2025-04-23 | 2025-04-22 | 2025-05-12 | 2025-05-16 | Completed |  | 700847 | Archive release | Jamie Carter | A. Shah | PDF | Study_report_PK012mk0001_and_related_information_0847.pdf | Placeholder timeline for reporting test | Central | 853
[5 empty] | 4.2.3 |  | 4.2.3 Toxicology | 840 |  |  | 41 days | 2025-04-24 | 2025-04-29 | 2025-06-04 | 2025-06-08 | Completed |  | 700848 |  | Jamie Carter | L. Bennett | DOCX | Toxicology_0848.docx | Placeholder timeline for reporting test | Central | 854
[5 empty] | 4.2.3.2 |  | 4.2.3.2 Repeat dose toxicity [Species, route, duration] | 841 |  |  | 17 days | 2025-04-23 | 2025-04-23 | 2025-05-10 |  | In Progress | Draft in QC review | 700849 | QC review | Casey Rivera | M. Sullivan | DOCX | Repeat_dose_toxicity_Species_route_duration_0849.docx | Placeholder timeline for reporting test | Central | 855
[5 empty] | 4.2.3.2 |  | Study report [tt181034fin] and related information | 842 |  |  | 18 days | 2025-04-19 | 2025-04-17 | 2025-05-07 | 2025-05-07 | Completed | QC completed | 700850 |  | Casey Rivera | N. Ortiz | PDF | Study_report_tt181034fin_and_related_information_0850.pdf | Placeholder timeline for reporting test | Central | 856
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt181034 | 843 |  |  | 26 days | 2025-04-23 | 2025-04-24 | 2025-05-19 |  | In Progress | Regional review underway | 700851 | Publishing prep | Jordan Patel | A. Shah | XLSX | NonClinical_SEND_Datasets_tt181034_0851.xlsx | Timing estimate is illustrative | Central | 857
[5 empty] | 4.2.3.2 |  | Study report [tt181035fin] and related information | 844 |  |  | 26 days | 2025-04-19 |  | 2025-05-15 |  | Not Started | Resource assignment not yet confirmed | 700852 |  | Taylor Chen | N. Ortiz | PDF | Study_report_tt181035fin_and_related_information_0852.pdf | Sample entry for dashboard validation | Central | 858
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt181035 | 845 |  |  | 18 days | 2025-04-20 | 2025-04-23 | 2025-05-08 | 2025-05-15 | Completed | Released to archive | 700853 |  | Jordan Patel | L. Bennett | CSV | NonClinical_SEND_Datasets_tt181035_0853.csv | Dummy data added for planning demo | Central | 859
[5 empty] | 4.2.3.2 |  | Study report [tt182515fin] and related information | 846 |  |  | 21 days | 2025-04-22 | 2025-04-27 | 2025-05-13 |  | In Progress | Metadata check in progress | 700854 | Authoring | Jamie Carter | N. Ortiz | DOCX | Study_report_tt182515fin_and_related_information_0854.docx | Dummy data added for planning demo | Central | 860
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt182515 | 847 |  |  | 32 days | 2025-04-26 | 2025-04-26 | 2025-05-28 | 2025-06-04 | Completed | Completed as planned | 700855 | Archive release | Jordan Patel | M. Sullivan | CSV | NonClinical_SEND_Datasets_tt182515_0855.csv | Placeholder timeline for reporting test | Central | 861
[5 empty] | 4.2.3.2 |  | Study report [tt182516fin] and related information | 848 |  |  | 27 days | 2025-04-29 | 2025-04-28 | 2025-05-26 |  | In Progress | Regional review underway | 700856 | Publishing prep | Alex Kim | L. Bennett | PDF | Study_report_tt182516fin_and_related_information_0856.pdf | Placeholder timeline for reporting test | Central | 862
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt182516 | 849 |  |  | 33 days | 2025-04-25 | 2025-04-23 | 2025-05-28 |  | In Progress | Regional review underway | 700857 | Authoring | Jordan Patel | N. Ortiz | ZIP | NonClinical_SEND_Datasets_tt182516_0857.zip | Sample entry for dashboard validation | Central | 863
[5 empty] | 4.2.3.2 |  | Study report [tt201020fin] and related information | 850 |  |  | 28 days | 2025-04-26 | 2025-04-30 | 2025-05-24 | 2025-05-22 | Completed | Released to archive | 700858 | Submission build | Sam Brooks | L. Bennett | DOCX | Study_report_tt201020fin_and_related_information_0858.docx | Timing estimate is illustrative | Central | 864
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt201020 | 851 |  |  | 27 days | 2025-04-27 | 2025-05-03 | 2025-05-24 |  | In Progress | Regional review underway | 700859 | QC review | Alex Kim | L. Bennett | XLSX | NonClinical_SEND_Datasets_tt201020_0859.xlsx | Sample entry for dashboard validation | Central | 865
[5 empty] | 4.2.3.2 |  | Study report [tt201021fin] and related information | 852 |  |  | 26 days | 2025-05-02 | 2025-05-01 | 2025-05-28 | 2025-05-24 | Completed | Released to archive | 700860 | Archive release | Taylor Chen | L. Bennett | PDF | Study_report_tt201021fin_and_related_information_0860.pdf | Placeholder timeline for reporting test | Central | 866
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt201021 | 853 |  |  | 23 days | 2025-05-02 | 2025-05-02 | 2025-05-25 |  | In Progress | Metadata check in progress | 700861 | QC review | Morgan Lee | L. Bennett | CSV | NonClinical_SEND_Datasets_tt201021_0861.csv | Sample entry for dashboard validation | Central | 867
[5 empty] | 4.2.3.2 |  | Study report [tt221002fin] and related information | 854 |  |  | 24 days | 2025-04-30 | 2025-04-28 | 2025-05-24 | 2025-05-23 | Completed | Completed as planned | 700862 | Archive release | Casey Rivera | L. Bennett | DOCX | Study_report_tt221002fin_and_related_information_0862.docx | Timing estimate is illustrative | Central | 868
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt221002 | 855 |  |  | 10 days | 2025-05-02 | 2025-05-04 | 2025-05-12 | 2025-05-18 | Completed | Completed as planned | 700863 | Archive release | Sam Brooks | L. Bennett | ZIP | NonClinical_SEND_Datasets_tt221002_0863.zip | Timing estimate is illustrative | Central | 869
[5 empty] | 4.2.3.2 |  | Study report [tt229000fin] and related information | 856 |  |  | 33 days | 2025-05-04 | 2025-05-09 | 2025-06-06 |  | In Progress | Pending cross-functional signoff | 700864 | Regional alignment | Sam Brooks | N. Ortiz | PDF | Study_report_tt229000fin_and_related_information_0864.pdf | Placeholder timeline for reporting test | Central | 870
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt229000 | 857 |  |  | 23 days | 2025-05-01 | 2025-05-04 | 2025-05-24 | 2025-05-20 | Completed |  | 700865 | Archive release | Morgan Lee | R. Gupta | CSV | NonClinical_SEND_Datasets_tt229000_0865.csv | Sample entry for dashboard validation | Central | 871
[5 empty] | 4.2.3.2 |  | Study report [tt176024fin] and related information | 858 |  |  | 20 days | 2025-05-05 | 2025-05-02 | 2025-05-25 | 2025-05-25 | Completed | Released to archive | 700866 | Submission build | Morgan Lee | A. Shah | DOCX | Study_report_tt176024fin_and_related_information_0866.docx | Sample entry for dashboard validation | Central | 872
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt176024 | 859 |  |  | 14 days | 2025-05-04 | 2025-05-04 | 2025-05-18 |  | In Progress | Pending cross-functional signoff | 700867 | QC review | Jamie Carter | A. Shah | ZIP | NonClinical_SEND_Datasets_tt176024_0867.zip | Placeholder timeline for reporting test | Central | 873
[5 empty] | 4.2.3.2 |  | Study report [tt176045fin] and related information | 860 |  |  | 26 days | 2025-05-01 | 2025-04-28 | 2025-05-27 | 2025-05-29 | Completed | Completed as planned | 700868 | Archive release | Morgan Lee | M. Sullivan | PDF | Study_report_tt176045fin_and_related_information_0868.pdf | Dummy data added for planning demo | Central | 874
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt176045 | 861 |  |  | 13 days | 2025-05-08 | 2025-05-08 | 2025-05-21 | 2025-05-19 | Completed |  | 700869 |  | Jamie Carter | N. Ortiz | CSV | NonClinical_SEND_Datasets_tt176045_0869.csv | Timing estimate is illustrative | Central | 875
[5 empty] | 4.2.3.2 |  | Study report [tt181033fin] and related information | 862 |  |  | 17 days | 2025-05-05 | 2025-05-10 | 2025-05-22 | 2025-05-29 | Completed | Filed in baseline wave | 700870 | Publishing QC | Alex Kim | A. Shah | PDF | Study_report_tt181033fin_and_related_information_0870.pdf | Sample entry for dashboard validation | Central | 876
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt181033 | 863 |  |  | 8 days | 2025-05-08 | 2025-05-09 | 2025-05-16 | 2025-05-12 | Completed | Filed in baseline wave | 700871 | Submission build | Alex Kim | R. Gupta | ZIP | NonClinical_SEND_Datasets_tt181033_0871.zip | Dummy data added for planning demo | Central | 877
[5 empty] | 4.2.3.2 |  | Study report [tt182506fin] and related information | 864 |  |  | 27 days | 2025-05-07 | 2025-05-08 | 2025-06-03 | 2025-05-31 | Completed | Completed as planned | 700872 | Publishing QC | Taylor Chen | L. Bennett | PDF | Study_report_tt182506fin_and_related_information_0872.pdf | Dummy data added for planning demo | Central | 878
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt182506 | 865 |  |  | 26 days | 2025-05-10 |  | 2025-06-05 |  | Not Started | Planned for upcoming wave | 700873 |  | Sam Brooks | M. Sullivan | CSV | NonClinical_SEND_Datasets_tt182506_0873.csv | Timing estimate is illustrative | Central | 879
[5 empty] | 4.2.3.2 |  | Study report [tt186041fin] and related information | 866 |  |  | 32 days | 2025-05-07 | 2025-05-12 | 2025-06-08 | 2025-06-15 | Completed | Completed as planned | 700874 | Archive release | Morgan Lee | L. Bennett | PDF | Study_report_tt186041fin_and_related_information_0874.pdf | Dummy data added for planning demo | Central | 880
[5 empty] | 4.2.3.2 |  | NonClinical SEND Datasets tt186041 | 867 |  |  | 27 days | 2025-05-07 | 2025-05-11 | 2025-06-03 |  | In Progress | Metadata check in progress | 700875 | Regional alignment | Alex Kim | N. Ortiz | CSV | NonClinical_SEND_Datasets_tt186041_0875.csv | Placeholder timeline for reporting test | Central | 881
[5 empty] | 4.2.3.3 |  | 4.2.3.3 Genotoxicity | 868 |  |  | 16 days | 2025-05-11 |  | 2025-05-27 |  | Not Started | Resource assignment not yet confirmed | 700876 |  | Taylor Chen | N. Ortiz | DOCX | Genotoxicity_0876.docx | Dummy data added for planning demo | Central | 882
[5 empty] | 4.2.3.3.1 |  | 4.2.3.3.1 In vitro | 869 |  |  | 30 days | 2025-05-11 | 2025-05-13 | 2025-06-10 | 2025-06-14 | Completed | Completed as planned | 700877 |  | Jordan Patel | M. Sullivan | PDF | In_vitro_0877.pdf | Sample entry for dashboard validation | Central | 883
[5 empty] | 4.2.3.3.1 |  | Study report [tt178133fin] and related information | 870 |  |  | 21 days | 2025-05-08 | 2025-05-06 | 2025-05-29 | 2025-06-04 | Completed | QC completed | 700878 | Archive release | Jordan Patel | A. Shah | PDF | Study_report_tt178133fin_and_related_information_0878.pdf | Timing estimate is illustrative | Central | 884
[5 empty] | 4.2.3.3.1 |  | Study report [tt188042fin] and related information | 871 |  |  | 34 days | 2025-05-09 |  | 2025-06-12 |  | Not Started | Resource assignment not yet confirmed | 700879 |  | Jordan Patel | A. Shah | PDF | Study_report_tt188042fin_and_related_information_0879.pdf | Sample entry for dashboard validation | Central | 886
[5 empty] | 4.2.3.3.1 |  | Study report [tt188699fin] and related information | 872 |  |  | 23 days | 2025-05-13 | 2025-05-14 | 2025-06-05 |  | In Progress | Draft in QC review | 700880 | Regional alignment | Morgan Lee | L. Bennett | DOCX | Study_report_tt188699fin_and_related_information_0880.docx | Placeholder timeline for reporting test | Central | 888
[5 empty] | 4.2.3.4 |  | 4.2.3.4 Carcinogenicity | 873 |  |  | 8 days | 2025-05-09 | 2025-05-12 | 2025-05-17 | 2025-05-13 | Completed | QC completed | 700881 | Submission build | Jamie Carter | M. Sullivan | DOCX | Carcinogenicity_0881.docx | Sample entry for dashboard validation | Central | 890
[5 empty] | 4.2.3.4.1 |  | 4.2.3.4.1 Long term studies [Species] | 874 |  |  | 27 days | 2025-05-13 | 2025-05-17 | 2025-06-09 | 2025-06-16 | Completed | Released to archive | 700882 |  | Taylor Chen | A. Shah | PDF | Long_term_studies_Species_0882.pdf | Sample entry for dashboard validation | Central | 891
[5 empty] | 4.2.3.4.1 |  | Study report [WOE001mk0001] and related information | 875 |  |  | 19 days | 2025-05-09 | 2025-05-06 | 2025-05-28 | 2025-05-26 | Completed |  | 700883 | Publishing QC | Jordan Patel | N. Ortiz | DOCX | Study_report_WOE001mk0001_and_related_information_0883.docx | Dummy data added for planning demo | Central | 892
[5 empty] | 4.2.3.4.1 |  | NonClinical SEND Datasets WOE001mk0001 | 876 |  |  | 35 days | 2025-05-09 | 2025-05-08 | 2025-06-13 | 2025-06-19 | Completed |  | 700884 |  | Jordan Patel | M. Sullivan | CSV | NonClinical_SEND_Datasets_WOE001mk0001_0884.csv | Sample entry for dashboard validation | Central | 893
[5 empty] | 4.2.3.4.1 |  | Study report [WOE001CAPRATE] and related information | 877 |  |  | 16 days | 2025-05-09 | 2025-05-10 | 2025-05-25 | 2025-06-01 | Completed | QC completed | 700885 |  | Morgan Lee | M. Sullivan | DOCX | Study_report_WOE001CAPRATE_and_related_information_0885.docx | Timing estimate is illustrative | Central | 894
[5 empty] | 4.2.3.4.1 |  | NonClinical SEND Datasets WOE001CAPRATE | 878 |  |  | 16 days | 2025-05-12 | 2025-05-12 | 2025-05-28 | 2025-06-02 | Completed | QC completed | 700886 |  | Taylor Chen | R. Gupta | CSV | NonClinical_SEND_Datasets_WOE001CAPRATE_0886.csv | Sample entry for dashboard validation | Central | 895
[5 empty] | 4.2.3.4.2 |  | 4.2.3.4.2 Short or medium term studies | 879 |  |  | 17 days | 2025-05-14 |  | 2025-05-31 |  | Not Started | On hold pending document availability | 700887 |  | Jamie Carter | N. Ortiz | PDF | Short_or_medium_term_studies_0887.pdf | Sample entry for dashboard validation | Central | 896
[5 empty] | 4.2.3.4.2 |  | Study report [tt249005fin] and related information | 880 |  |  | 17 days | 2025-05-11 | 2025-05-10 | 2025-05-28 | 2025-05-31 | Completed | Completed as planned | 700888 | Publishing QC | Morgan Lee | N. Ortiz | PDF | Study_report_tt249005fin_and_related_information_0888.pdf | Dummy data added for planning demo | Central | 897
[5 empty] | 4.2.3.4.2 |  | NonClinical Datasets tt249005 | 881 |  |  | 21 days | 2025-05-20 | 2025-05-17 | 2025-06-10 | 2025-06-15 | Completed | Released to archive | 700889 |  | Jordan Patel | A. Shah | CSV | NonClinical_Datasets_tt249005_0889.csv | Timing estimate is illustrative | Central | 898
[5 empty] | 4.2.3.5 |  | 4.2.3.5 Reproductive and developmental toxicity | 882 |  |  | 27 days | 2025-05-17 | 2025-05-17 | 2025-06-13 | 2025-06-13 | Completed | QC completed | 700890 |  | Taylor Chen | R. Gupta | DOCX | Reproductive_and_developmental_toxicity_0890.docx | Sample entry for dashboard validation | Central | 899
[5 empty] | 4.2.3.5.1 |  | 4.2.3.5.1 Fertility and early embryonic development | 883 |  |  | 24 days | 2025-05-17 | 2025-05-17 | 2025-06-10 | 2025-06-07 | Completed |  | 700891 | Submission build | Alex Kim | N. Ortiz | DOCX | Fertility_and_early_embryonic_development_0891.docx | Timing estimate is illustrative | Central | 900
[5 empty] | 4.2.3.5.1 |  | Study report [tt217040fin] and related information | 884 |  |  | 25 days | 2025-05-18 | 2025-05-23 | 2025-06-12 | 2025-06-17 | Completed | Released to archive | 700892 | Archive release | Taylor Chen | M. Sullivan | DOCX | Study_report_tt217040fin_and_related_information_0892.docx | Sample entry for dashboard validation | Central | 901
[5 empty] | 4.2.3.5.1 |  | Study report [tt217050fin] and related information | 885 |  |  | 12 days | 2025-05-17 | 2025-05-17 | 2025-05-29 | 2025-05-28 | Completed | Completed as planned | 700893 |  | Jordan Patel | N. Ortiz | PDF | Study_report_tt217050fin_and_related_information_0893.pdf | Sample entry for dashboard validation | Central | 903
[5 empty] | 4.2.3.5.1 |  | Study report [tt217070fin] and related information | 886 |  |  | 17 days | 2025-05-15 | 2025-05-12 | 2025-06-01 | 2025-05-30 | Completed |  | 700894 |  | Casey Rivera | L. Bennett | DOCX | Study_report_tt217070fin_and_related_information_0894.docx | Placeholder timeline for reporting test | Central | 905
[5 empty] | 4.2.3.5.1 |  | Study report [tt217090fin] and related information | 887 |  |  | 31 days | 2025-05-23 | 2025-05-28 | 2025-06-23 | 2025-06-25 | Completed | Released to archive | 700895 |  | Sam Brooks | L. Bennett | DOCX | Study_report_tt217090fin_and_related_information_0895.docx | Placeholder timeline for reporting test | Central | 907
[5 empty] | 4.2.3.5.2 |  | 4.2.3.5.2 Embryofetal development | 888 |  |  | 17 days | 2025-05-24 | 2025-05-24 | 2025-06-10 | 2025-06-08 | Completed | QC completed | 700896 | Submission build | Jamie Carter | L. Bennett | XLSX | Embryofetal_development_0896.xlsx | Sample entry for dashboard validation | Central | 909
[5 empty] | 4.2.3.5.2 |  | Study report [tt217004fin] and related information | 889 |  |  | 29 days | 2025-05-24 | 2025-05-23 | 2025-06-22 |  | In Progress | Pending cross-functional signoff | 700897 | Regional alignment | Sam Brooks | R. Gupta | PDF | Study_report_tt217004fin_and_related_information_0897.pdf | Dummy data added for planning demo | Central | 910
[5 empty] | 4.2.3.5.2 |  | Study report [tt217014fin] and related information | 890 |  |  | 34 days | 2025-05-22 | 2025-05-24 | 2025-06-25 | 2025-07-02 | Completed | Released to archive | 700898 | Submission build | Taylor Chen | M. Sullivan | PDF | Study_report_tt217014fin_and_related_information_0898.pdf | Sample entry for dashboard validation | Central | 911
[5 empty] | 4.2.3.5.2 |  | Study report [tt217020fin] and related information | 891 |  |  | 12 days | 2025-05-23 |  | 2025-06-04 |  | Not Started | Planned for upcoming wave | 700899 |  | Jordan Patel | L. Bennett | DOCX | Study_report_tt217020fin_and_related_information_0899.docx | Timing estimate is illustrative | Central | 912
[5 empty] | 4.2.3.5.2 |  | Study report [tt217024fin] and related information | 892 |  |  | 25 days | 2025-05-18 | 2025-05-16 | 2025-06-12 | 2025-06-13 | Completed | QC completed | 700900 |  | Alex Kim | M. Sullivan | DOCX | Study_report_tt217024fin_and_related_information_0900.docx | Dummy data added for planning demo | Central | 913
[5 empty] | 4.2.3.5.2 |  | Study report [tt217030fin] and related information | 893 |  |  | 27 days | 2025-05-23 | 2025-05-20 | 2025-06-19 | 2025-06-26 | Completed | QC completed | 700901 | Archive release | Sam Brooks | A. Shah | PDF | Study_report_tt217030fin_and_related_information_0901.pdf | Sample entry for dashboard validation | Central | 914
[5 empty] | 4.2.3.5.2 |  | Study report [tt217034fin] and related information | 894 |  |  | 22 days | 2025-05-27 | 2025-06-01 | 2025-06-18 | 2025-06-15 | Completed | Completed as planned | 700902 | Archive release | Alex Kim | M. Sullivan | PDF | Study_report_tt217034fin_and_related_information_0902.pdf | Timing estimate is illustrative | Central | 915
[5 empty] | 4.2.3.5.2 |  | Study report [tt217060fin] and related information | 895 |  |  | 9 days | 2025-05-22 | 2025-05-20 | 2025-05-31 | 2025-05-27 | Completed | Released to archive | 700903 | Publishing QC | Morgan Lee | A. Shah | DOCX | Study_report_tt217060fin_and_related_information_0903.docx | Timing estimate is illustrative | Central | 916
[5 empty] | 4.2.3.5.2 |  | Study report [tt217080fin] and related information | 896 |  |  | 17 days | 2025-05-21 | 2025-05-24 | 2025-06-07 |  | In Progress | Regional review underway | 700904 | QC review | Taylor Chen | R. Gupta | PDF | Study_report_tt217080fin_and_related_information_0904.pdf | Sample entry for dashboard validation | Central | 917
[5 empty] | 4.2.3.5.3 |  | 4.2.3.5.3 Prenatal and postnatal development, including maternal function | 897 |  |  | 33 days | 2025-05-27 | 2025-05-25 | 2025-06-29 |  | In Progress | Draft in QC review | 700905 | QC review | Jamie Carter | M. Sullivan | PDF | Prenatal_and_postnatal_development_including_maternal_functi_0905.pdf | Placeholder timeline for reporting test | Central | 918
[5 empty] | 4.2.3.5.3 |  | Study report [tt249016fin] and related information | 898 |  |  | 12 days | 2025-05-23 | 2025-05-24 | 2025-06-04 | 2025-06-09 | Completed | Filed in baseline wave | 700906 |  | Casey Rivera | N. Ortiz | PDF | Study_report_tt249016fin_and_related_information_0906.pdf | Placeholder timeline for reporting test | Central | 919
[5 empty] | 4.2.3.5.3 |  | Study report [WOE001CAPRATEPPND] and related information | 899 |  |  | 24 days | 2025-05-27 | 2025-05-29 | 2025-06-20 | 2025-06-23 | Completed |  | 700907 | Publishing QC | Taylor Chen | L. Bennett | PDF | Study_report_WOE001CAPRATEPPND_and_related_information_0907.pdf | Dummy data added for planning demo | Central | 920
[5 empty] | 4.2.3.6 |  | 4.2.3.6 Local tolerance | 900 |  |  | 12 days | 2025-05-24 | 2025-05-24 | 2025-06-05 |  | In Progress | Metadata check in progress | 700908 |  | Sam Brooks | A. Shah | PDF | Local_tolerance_0908.pdf | Dummy data added for planning demo | Central | 924
[5 empty] | 4.2.3.6 |  | Study report [tt247832] and related information | 901 |  |  | 27 days | 2025-05-27 | 2025-05-25 | 2025-06-23 | 2025-06-30 | Completed | Filed in baseline wave | 700909 | Archive release | Jamie Carter | N. Ortiz | PDF | Study_report_tt247832_and_related_information_0909.pdf | Placeholder timeline for reporting test | Central | 925
[5 empty] | 4.2.3.6 |  | Study report [tt247833] and related information | 902 |  |  | 19 days | 2025-05-24 | 2025-05-24 | 2025-06-12 |  | In Progress | Metadata check in progress | 700910 | QC review | Taylor Chen | R. Gupta | DOCX | Study_report_tt247833_and_related_information_0910.docx | Timing estimate is illustrative | Central | 926
[5 empty] | 4.2.3.7 |  | 4.2.3.7 Other toxicity studies | 903 |  |  | 15 days | 2025-05-28 | 2025-05-28 | 2025-06-12 |  | In Progress | Metadata check in progress | 700911 | Publishing prep | Sam Brooks | L. Bennett | DOCX | Other_toxicity_studies_0911.docx | Dummy data added for planning demo | Central | 928
[5 empty] | 4.2.3.7.2 |  | 4.2.3.7.2 Immunotoxicity | 904 |  |  | 18 days | 2025-06-02 | 2025-06-05 | 2025-06-20 |  | In Progress | Regional review underway | 700912 |  | Casey Rivera | N. Ortiz | PDF | Immunotoxicity_0912.pdf | Sample entry for dashboard validation | Central | 929
[5 empty] | 4.2.3.7.2 |  | Study report [TT227826FIN] and related information | 905 |  |  | 24 days | 2025-05-28 | 2025-06-01 | 2025-06-21 |  | In Progress | Metadata check in progress | 700913 | Publishing prep | Jordan Patel | R. Gupta | DOCX | Study_report_TT227826FIN_and_related_information_0913.docx | Dummy data added for planning demo | Central | 930
[5 empty] | 4.2.3.7.6 |  | 4.2.3.7.6 Impurities | 906 |  |  | 31 days | 2025-06-04 | 2025-06-04 | 2025-07-05 | 2025-07-08 | Completed | QC completed | 700914 | Publishing QC | Alex Kim | M. Sullivan | XLSX | Impurities_0914.xlsx | Timing estimate is illustrative | Central | 931
[5 empty] | 4.2.3.7.6 |  | Study report [tt191030fin] and related information | 907 |  |  | 11 days | 2025-06-04 | 2025-06-06 | 2025-06-15 | 2025-06-16 | Completed |  | 700915 |  | Sam Brooks | M. Sullivan | PDF | Study_report_tt191030fin_and_related_information_0915.pdf | Placeholder timeline for reporting test | Central | 932
[5 empty] | 4.2.3.7.6 |  | Study report [tt251006fin] and related information | 908 |  |  | 27 days | 2025-05-29 | 2025-05-26 | 2025-06-25 | 2025-06-23 | Completed | Released to archive | 700916 |  | Morgan Lee | R. Gupta | PDF | Study_report_tt251006fin_and_related_information_0916.pdf | Timing estimate is illustrative | Central | 933
[5 empty] | 4.2.3.7.6 |  | Study report [pk002l006722648] and related information | 909 |  |  | 16 days | 2025-06-03 | 2025-06-08 | 2025-06-19 | 2025-06-17 | Completed | Completed as planned | 700917 |  | Jamie Carter | M. Sullivan | DOCX | Study_report_pk002l006722648_and_related_information_0917.docx | Sample entry for dashboard validation | Central | 934
[5 empty] | 4.2.3.7.6 |  | Study report [tt249052fin] and related information | 910 |  |  | 22 days | 2025-06-04 | 2025-06-06 | 2025-06-26 |  | In Progress | Regional review underway | 700918 | Publishing prep | Taylor Chen | R. Gupta | DOCX | Study_report_tt249052fin_and_related_information_0918.docx | Sample entry for dashboard validation | Central | 935
[5 empty] | 4.2.3.7.6 |  | Study report [tt258005fin] and related information | 911 |  |  | 8 days | 2025-06-03 |  | 2025-06-11 |  | Not Started | Pending authoring start | 700919 |  | Jamie Carter | M. Sullivan | PDF | Study_report_tt258005fin_and_related_information_0919.pdf | Sample entry for dashboard validation | Central | 936
[5 empty] | 4.2.3.7.6 |  | Study report [tt258025] and related information | 912 |  |  | 31 days | 2025-06-06 | 2025-06-09 | 2025-07-07 | 2025-07-12 | Completed | Completed as planned | 700920 | Submission build | Taylor Chen | N. Ortiz | DOCX | Study_report_tt258025_and_related_information_0920.docx | Timing estimate is illustrative | Central | 937
[5 empty] | 4.2.3.7.6 |  | Study report [TT248064FIN] and related information | 913 |  |  | 11 days | 2025-06-02 | 2025-05-31 | 2025-06-13 |  | In Progress | Draft in QC review | 700921 | Publishing prep | Jamie Carter | N. Ortiz | DOCX | Study_report_TT248064FIN_and_related_information_0921.docx | Sample entry for dashboard validation | Central | 938
[5 empty] | 4.2.3.7.6 |  | Study report [tt221032fin] and related information | 914 |  |  | 12 days | 2025-06-07 | 2025-06-06 | 2025-06-19 | 2025-06-18 | Completed | Filed in baseline wave | 700922 | Archive release | Morgan Lee | A. Shah | PDF | Study_report_tt221032fin_and_related_information_0922.pdf | Timing estimate is illustrative | Central | 939
[5 empty] | 4.2.3.7.6 |  | NonClinical Datasets tt221032 | 915 |  |  | 20 days | 2025-06-04 | 2025-06-04 | 2025-06-24 | 2025-06-22 | Completed |  | 700923 | Archive release | Alex Kim | L. Bennett | XLSX | NonClinical_Datasets_tt221032_0923.xlsx | Placeholder timeline for reporting test | Central | 940
[5 empty] | 4.2.3.7.6 |  | Study report [TT248090FIN] and related information | 916 |  |  | 22 days | 2025-06-03 | 2025-06-06 | 2025-06-25 | 2025-07-02 | Completed | Filed in baseline wave | 700924 |  | Sam Brooks | L. Bennett | DOCX | Study_report_TT248090FIN_and_related_information_0924.docx | Timing estimate is illustrative | Central | 941
[5 empty] | 4.2.3.7.6 |  | Study report [TT258026FIN] and related information | 917 |  |  | 19 days | 2025-06-04 | 2025-06-03 | 2025-06-23 | 2025-06-25 | Completed | QC completed | 700925 | Archive release | Jamie Carter | L. Bennett | DOCX | Study_report_TT258026FIN_and_related_information_0925.docx | Dummy data added for planning demo | Central | 942
[5 empty] | 4.2.3.7.6 |  | Study report [TT258085FIN] and related information | 918 |  |  | 22 days | 2025-06-08 | 2025-06-06 | 2025-06-30 |  | In Progress | Awaiting final source document | 700926 |  | Jordan Patel | N. Ortiz | DOCX | Study_report_TT258085FIN_and_related_information_0926.docx | Placeholder timeline for reporting test | Central | 943
[5 empty] | 4.2.3.7.6 |  | Study report [TT259042FIN] and related information | 919 |  |  | 23 days | 2025-06-09 | 2025-06-13 | 2025-07-02 |  | In Progress | Draft in QC review | 700927 | QC review | Jordan Patel | L. Bennett | PDF | Study_report_TT259042FIN_and_related_information_0927.pdf | Dummy data added for planning demo | Central | 944
[5 empty] | 4.2.3.7.6 |  | Study report [pk002l007006016] and related information | 920 |  |  | 16 days | 2025-06-07 | 2025-06-09 | 2025-06-23 | 2025-06-25 | Completed | Filed in baseline wave | 700928 |  | Jordan Patel | R. Gupta | DOCX | Study_report_pk002l007006016_and_related_information_0928.docx | Sample entry for dashboard validation | Central | 945
[5 empty] | 4.2.3.7.6 |  | Study report [TT258083FIN] and related information | 921 |  |  | 8 days | 2025-06-12 | 2025-06-15 | 2025-06-20 | 2025-06-18 | Completed | Filed in baseline wave | 700929 |  | Sam Brooks | M. Sullivan | PDF | Study_report_TT258083FIN_and_related_information_0929.pdf | Sample entry for dashboard validation | Central | 946
[5 empty] | 4.2.3.7.6 |  | Study report [TT258086FIN] and related information | 922 |  |  | 18 days | 2025-06-07 | 2025-06-06 | 2025-06-25 |  | In Progress | Regional review underway | 700930 | Regional alignment | Jamie Carter | A. Shah | PDF | Study_report_TT258086FIN_and_related_information_0930.pdf | Placeholder timeline for reporting test | Central | 947
[5 empty] | 4.2.3.7.6 |  | Study report [TT259036FIN] and related information | 923 |  |  | 25 days | 2025-06-08 | 2025-06-12 | 2025-07-03 | 2025-06-29 | Completed | Released to archive | 700931 |  | Casey Rivera | A. Shah | DOCX | Study_report_TT259036FIN_and_related_information_0931.docx | Sample entry for dashboard validation | Central | 948
[5 empty] | 4.2.3.7.6 |  | Study report [pk002l007006333] and related information | 924 |  |  | 30 days | 2025-06-11 | 2025-06-16 | 2025-07-11 |  | In Progress | Pending cross-functional signoff | 700932 | Publishing prep | Jamie Carter | L. Bennett | DOCX | Study_report_pk002l007006333_and_related_information_0932.docx | Placeholder timeline for reporting test | Central | 949
[5 empty] | 4.2.3.7.6 |  | Study report [TT258084FIN] and related information | 925 |  |  | 32 days | 2025-06-08 | 2025-06-11 | 2025-07-10 | 2025-07-14 | Completed | Released to archive | 700933 | Publishing QC | Jordan Patel | A. Shah | DOCX | Study_report_TT258084FIN_and_related_information_0933.docx | Placeholder timeline for reporting test | Central | 950
[5 empty] | 4.2.3.7.7 |  | 4.2.3.7.7 Other | 926 |  |  | 23 days | 2025-06-11 | 2025-06-16 | 2025-07-04 |  | In Progress | Publishing build in progress | 700934 | Authoring | Casey Rivera | R. Gupta | PDF | Other_0934.pdf | Dummy data added for planning demo | Central | 951
[5 empty] | 4.2.3.7.7 |  | Study report [tt176032fin] and related information | 927 |  |  | 21 days | 2025-06-16 | 2025-06-18 | 2025-07-07 | 2025-07-07 | Completed | Released to archive | 700935 | Archive release | Sam Brooks | R. Gupta | PDF | Study_report_tt176032fin_and_related_information_0935.pdf | Placeholder timeline for reporting test | Central | 952
[5 empty] | 4.2.3.7.7 |  | Study report [tt181401fin] and related information | 928 |  |  | 16 days | 2025-06-11 | 2025-06-08 | 2025-06-27 | 2025-06-30 | Completed | QC completed | 700936 | Archive release | Sam Brooks | A. Shah | PDF | Study_report_tt181401fin_and_related_information_0936.pdf | Placeholder timeline for reporting test | Central | 953
[5 empty] | 4.2.3.7.7 |  | Study report [tt184604fin] and related information | 929 |  |  | 24 days | 2025-06-10 | 2025-06-11 | 2025-07-04 |  | In Progress | Awaiting final source document | 700937 | Authoring | Taylor Chen | A. Shah | PDF | Study_report_tt184604fin_and_related_information_0937.pdf | Timing estimate is illustrative | Central | 954
[5 empty] | 4.2.3.7.7 |  | Study report [tt187801fin] and related information | 930 |  |  | 20 days | 2025-06-17 | 2025-06-20 | 2025-07-07 |  | In Progress | Publishing build in progress | 700938 |  | Jordan Patel | M. Sullivan | DOCX | Study_report_tt187801fin_and_related_information_0938.docx | Dummy data added for planning demo | Central | 955
[5 empty] | 4.2.3.7.7 |  | Study report [tt191009fin] and related information | 931 |  |  | 17 days | 2025-06-12 | 2025-06-11 | 2025-06-29 | 2025-07-04 | Completed | Completed as planned | 700939 |  | Taylor Chen | A. Shah | DOCX | Study_report_tt191009fin_and_related_information_0939.docx | Placeholder timeline for reporting test | Central | 956
[5 empty] | 4.2.3.7.7 |  | Study report [tt197888fin] and related information | 932 |  |  | 19 days | 2025-06-18 | 2025-06-19 | 2025-07-07 | 2025-07-14 | Completed | Completed as planned | 700940 |  | Alex Kim | N. Ortiz | DOCX | Study_report_tt197888fin_and_related_information_0940.docx | Placeholder timeline for reporting test | Central | 957
[5 empty] | 4.2.3.7.7 |  | Study report [tt197033fin] and related information | 933 |  |  | 24 days | 2025-06-20 | 2025-06-21 | 2025-07-14 |  | In Progress | Regional review underway | 700941 | Authoring | Morgan Lee | M. Sullivan | DOCX | Study_report_tt197033fin_and_related_information_0941.docx | Timing estimate is illustrative | Central | 958
[5 empty] | 4.2.3.7.7 |  | Study report [tt197043fin] and related information | 934 |  |  | 15 days | 2025-06-19 | 2025-06-19 | 2025-07-04 |  | In Progress | Metadata check in progress | 700942 |  | Sam Brooks | A. Shah | DOCX | Study_report_tt197043fin_and_related_information_0942.docx | Timing estimate is illustrative | Central | 959
[5 empty] | 4.2.3.7.7 |  | Study report [tt207063fin] and related information | 935 |  |  | 15 days | 2025-06-18 | 2025-06-18 | 2025-07-03 | 2025-06-29 | Completed | Released to archive | 700943 | Submission build | Morgan Lee | R. Gupta | DOCX | Study_report_tt207063fin_and_related_information_0943.docx | Placeholder timeline for reporting test | Central | 960
[5 empty] | 4.2.3.7.7 |  | Study report [tt211024fin] and related information | 936 |  |  | 14 days | 2025-06-15 | 2025-06-17 | 2025-06-29 | 2025-06-28 | Completed | Completed as planned | 700944 |  | Morgan Lee | M. Sullivan | DOCX | Study_report_tt211024fin_and_related_information_0944.docx | Sample entry for dashboard validation | Central | 961
[5 empty] | 4.2.3.7.7 |  | Study report [tt211025fin] and related information | 937 |  |  | 24 days | 2025-06-20 | 2025-06-25 | 2025-07-14 | 2025-07-10 | Completed | QC completed | 700945 | Archive release | Morgan Lee | R. Gupta | DOCX | Study_report_tt211025fin_and_related_information_0945.docx | Timing estimate is illustrative | Central | 962
[5 empty] | 4.2.3.7.7 |  | Study report [tt212560fin] and related information | 938 |  |  | 34 days | 2025-06-22 | 2025-06-23 | 2025-07-26 |  | In Progress | Pending cross-functional signoff | 700946 | QC review | Sam Brooks | L. Bennett | DOCX | Study_report_tt212560fin_and_related_information_0946.docx | Sample entry for dashboard validation | Central | 963
[5 empty] | 4.2.3.7.7 |  | Study report [tt231004fin] and related information | 939 |  |  | 28 days | 2025-06-16 | 2025-06-15 | 2025-07-14 |  | In Progress | Regional review underway | 700947 | Regional alignment | Taylor Chen | R. Gupta | PDF | Study_report_tt231004fin_and_related_information_0947.pdf | Timing estimate is illustrative | Central | 964
[5 empty] | 4.2.3.7.7 |  | Study report [TT179828188FIN] and related information | 940 |  |  | 18 days | 2025-06-25 | 2025-06-27 | 2025-07-13 | 2025-07-16 | Completed | Released to archive | 700948 | Publishing QC | Jordan Patel | M. Sullivan | PDF | Study_report_TT179828188FIN_and_related_information_0948.pdf | Placeholder timeline for reporting test | Central | 965
[5 empty] | 4.3 |  | 4.3 Literature references | 941 |  |  | 98 days | 2025-06-23 |  | 2025-09-29 |  | Not Started | Planned for upcoming wave | 700949 |  | Jamie Carter | R. Gupta | XLSX | Literature_references_0949.xlsx | Sample entry for dashboard validation | Central | 966
[5 empty] | 5 |  | Module 5 Clinical Study Reports | 942 |  |  | 186 days | 2025-06-21 |  | 2025-12-24 |  | Not Started | Pending authoring start | 700950 |  | Casey Rivera | M. Sullivan | PDF | Module_5_Clinical_Study_Reports_0950.pdf | Dummy data added for planning demo | Central | 967
[5 empty] | 5.2 |  | 5.2 Tabular listing of all clinical studies | 943 |  |  | 72 days | 2025-06-24 | 2025-06-22 | 2025-09-04 | 2025-09-09 | Completed | QC completed | 700951 | Submission build | Jamie Carter | N. Ortiz | ZIP | Tabular_listing_of_all_clinical_studies_0951.zip | Sample entry for dashboard validation | Central | 968
[5 empty] | 5.2 |  | 5.2 Table of all clinical studies (US) | 944 |  |  | 97 days | 2025-06-27 | 2025-06-27 | 2025-10-02 | 2025-10-04 | Completed |  | 700952 | Archive release | Morgan Lee | R. Gupta | ZIP | Table_of_all_clinical_studies_US_0952.zip | Dummy data added for planning demo | Central | 969
[5 empty] | 5.2 |  | 5.2 Summary Level Clinical Site Information (US) | 945 |  |  | 109 days | 2025-06-25 | 2025-06-28 | 2025-10-12 | 2025-10-11 | Completed | Released to archive | 700953 |  | Jamie Carter | L. Bennett | DOCX | Summary_Level_Clinical_Site_Information_US_0953.docx | Sample entry for dashboard validation | Central | 970
[5 empty] | 5.2 |  | 5.2 Study Administrative Structure Table (EU) | 946 |  |  | 67 days | 2025-06-22 | 2025-06-19 | 2025-08-28 | 2025-09-01 | Completed | QC completed | 700954 |  | Sam Brooks | N. Ortiz | ZIP | Study_Administrative_Structure_Table_EU_0954.zip | Dummy data added for planning demo | Central | 971
[5 empty] | 5.2 |  | 5.2 Subjects Recruited by Sites Table (EU) | 947 |  |  | 119 days | 2025-06-27 | 2025-07-01 | 2025-10-24 |  | In Progress | Publishing build in progress | 700955 | QC review | Sam Brooks | A. Shah | ZIP | Subjects_Recruited_by_Sites_Table_EU_0955.zip | Timing estimate is illustrative | Central | 972
[5 empty] | 5.3 |  | 5.3 Clinical study reports and related information | 948 |  |  | 123 days | 2025-06-23 | 2025-06-22 | 2025-10-24 |  | In Progress | Pending cross-functional signoff | 700956 |  | Sam Brooks | L. Bennett | PDF | Clinical_study_reports_and_related_information_0956.pdf | Placeholder timeline for reporting test | Central | 973
[5 empty] | 5.3.1 |  | 5.3.1 Reports of biopharmaceutic studies | 949 |  |  | 30 days | 2025-06-25 | 2025-06-30 | 2025-07-25 |  | In Progress | Regional review underway | 700957 | Authoring | Morgan Lee | A. Shah | XLSX | Reports_of_biopharmaceutic_studies_0957.xlsx | Sample entry for dashboard validation | Central | 974
[5 empty] | 5.3.1.1 |  | 5.3.1.1 p022mk0001 | 950 |  |  | 23 days | 2025-07-01 | 2025-07-01 | 2025-07-24 |  | In Progress | Publishing build in progress | 700958 | Publishing prep | Sam Brooks | N. Ortiz | PDF | p022mk0001_0958.pdf | Sample entry for dashboard validation | Central | 975
[5 empty] | 5.3.1.1 |  | Study report [p022mk0001] and related information | 951 |  |  | 17 days | 2025-06-26 | 2025-06-24 | 2025-07-13 | 2025-07-09 | Completed | Filed in baseline wave | 700959 |  | Casey Rivera | L. Bennett | PDF | Study_report_p022mk0001_and_related_information_0959.pdf | Sample entry for dashboard validation | Central | 976
[5 empty] | 5.3.1.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p022mk0001 | 952 |  |  | 32 days | 2025-06-27 | 2025-07-01 | 2025-07-29 | 2025-08-02 | Completed | Completed as planned | 700960 |  | Jamie Carter | R. Gupta | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_0960.xlsx | Timing estimate is illustrative | Central | 977
[5 empty] | 5.3.1.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 953 |  |  | 30 days | 2025-07-01 |  | 2025-07-31 |  | Not Started | Planned for upcoming wave | 700961 |  | Sam Brooks | A. Shah | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_0961.zip | Sample entry for dashboard validation | Central | 978
[5 empty] | 5.3.1.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 954 |  |  | 22 days | 2025-07-03 | 2025-07-02 | 2025-07-25 |  | In Progress | Publishing build in progress | 700962 | Publishing prep | Sam Brooks | M. Sullivan | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_0962.xlsx | Dummy data added for planning demo | Central | 979
[5 empty] | 5.3.1.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 955 |  |  | 22 days | 2025-07-03 | 2025-07-01 | 2025-07-25 |  | In Progress | Metadata check in progress | 700963 | Regional alignment | Jamie Carter | A. Shah | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0963.docx | Sample entry for dashboard validation | Central | 980
[5 empty] | 5.3.1.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p022mk0001 | 956 |  |  | 27 days | 2025-07-04 | 2025-07-08 | 2025-07-31 |  | In Progress | Draft in QC review | 700964 | Authoring | Jordan Patel | R. Gupta | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p022mk0001_0964.zip | Dummy data added for planning demo | Central | 981
[5 empty] | 5.3.1.1 |  | Analysis datasets - ADAM format | 957 |  |  | 18 days | 2025-06-29 | 2025-07-01 | 2025-07-17 | 2025-07-15 | Completed | Filed in baseline wave | 700965 |  | Jordan Patel | R. Gupta | XLSX | Analysis_datasets_ADAM_format_0965.xlsx | Placeholder timeline for reporting test | Central | 982
[5 empty] | 5.3.1.1 |  | Data definition for analysis datasets - ADAM format (define file) | 958 |  |  | 21 days | 2025-06-28 | 2025-07-03 | 2025-07-19 |  | In Progress | Awaiting final source document | 700966 | Publishing prep | Morgan Lee | R. Gupta | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0966.zip | Sample entry for dashboard validation | Central | 983
[5 empty] | 5.3.1.1 |  | Analysis Data Reviewers Guide | 959 |  |  | 32 days | 2025-07-03 | 2025-07-04 | 2025-08-04 | 2025-08-09 | Completed | QC completed | 700967 |  | Alex Kim | N. Ortiz | XLSX | Analysis_Data_Reviewers_Guide_0967.xlsx | Placeholder timeline for reporting test | Central | 984
[5 empty] | 5.3.1.1 |  | Analysis programs | 960 |  |  | 14 days | 2025-06-29 | 2025-07-02 | 2025-07-13 |  | In Progress | Regional review underway | 700968 | Publishing prep | Morgan Lee | N. Ortiz | TXT | Analysis_programs_0968.txt | Sample entry for dashboard validation | Central | 985
[5 empty] | 5.3.1.1 |  | 5.3.1.1 p033mk0001 | 961 |  |  | 28 days | 2025-07-06 | 2025-07-05 | 2025-08-03 | 2025-08-01 | Completed |  | 700969 | Archive release | Jamie Carter | L. Bennett | DOCX | p033mk0001_0969.docx | Timing estimate is illustrative | Central | 986
[5 empty] | 5.3.1.1 |  | Study report [p033mk0001] and related information | 962 |  |  | 34 days | 2025-06-30 | 2025-07-01 | 2025-08-03 | 2025-08-01 | Completed |  | 700970 | Publishing QC | Morgan Lee | R. Gupta | DOCX | Study_report_p033mk0001_and_related_information_0970.docx | Sample entry for dashboard validation | Central | 987
[5 empty] | 5.3.1.1 |  | Case Report Forms - CRF FOLDER p033mk0001 | 963 |  |  | 18 days | 2025-07-02 | 2025-07-08 | 2025-07-20 |  | In Progress | Metadata check in progress | 700971 |  | Morgan Lee | L. Bennett | DOCX | Case_Report_Forms_CRF_FOLDER_p033mk0001_0971.docx | Timing estimate is illustrative | Central | 988
[5 empty] | 5.3.1.1 |  | Listing of Case Report Forms (CRFs TOC) | 964 |  |  | 22 days | 2025-07-09 | 2025-07-12 | 2025-07-31 | 2025-07-27 | Completed | Completed as planned | 700972 | Archive release | Jordan Patel | R. Gupta | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_0972.xlsx | Timing estimate is illustrative | Central | 989
[5 empty] | 5.3.1.1 |  | Case Report Forms - eCRFs (by site) for US | 965 |  |  | 15 days | 2025-07-04 | 2025-07-03 | 2025-07-19 |  | In Progress | Regional review underway | 700973 | QC review | Morgan Lee | L. Bennett | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_0973.docx | Dummy data added for planning demo | Central | 990
[5 empty] | 5.3.1.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p033mk0001 | 966 |  |  | 35 days | 2025-07-10 | 2025-07-10 | 2025-08-14 | 2025-08-15 | Completed | Completed as planned | 700974 |  | Sam Brooks | A. Shah | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p03_0974.csv | Dummy data added for planning demo | Central | 991
[5 empty] | 5.3.1.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 967 |  |  | 24 days | 2025-07-07 |  | 2025-07-31 |  | Not Started | On hold pending document availability | 700975 |  | Taylor Chen | A. Shah | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_0975.xlsx | Sample entry for dashboard validation | Central | 992
[5 empty] | 5.3.1.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 968 |  |  | 14 days | 2025-07-12 | 2025-07-11 | 2025-07-26 | 2025-08-02 | Completed | Filed in baseline wave | 700976 | Submission build | Sam Brooks | L. Bennett | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_0976.xlsx | Dummy data added for planning demo | Central | 993
[5 empty] | 5.3.1.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 969 |  |  | 24 days | 2025-07-08 | 2025-07-09 | 2025-08-01 |  | In Progress | Regional review underway | 700977 | Authoring | Jordan Patel | M. Sullivan | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_0977.docx | Dummy data added for planning demo | Central | 994
[5 empty] | 5.3.1.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p033mk0001 | 970 |  |  | 14 days | 2025-07-08 | 2025-07-12 | 2025-07-22 | 2025-07-25 | Completed | Completed as planned | 700978 |  | Jamie Carter | A. Shah | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p033mk0001_0978.csv | Dummy data added for planning demo | Central | 995
[5 empty] | 5.3.1.1 |  | Analysis datasets - ADAM format | 971 |  |  | 22 days | 2025-07-08 | 2025-07-06 | 2025-07-30 | 2025-08-02 | Completed | Filed in baseline wave | 700979 | Publishing QC | Taylor Chen | M. Sullivan | XLSX | Analysis_datasets_ADAM_format_0979.xlsx | Sample entry for dashboard validation | Central | 996
[5 empty] | 5.3.1.1 |  | Data definition for analysis datasets - ADAM format (define file) | 972 |  |  | 25 days | 2025-07-10 | 2025-07-13 | 2025-08-04 | 2025-08-01 | Completed | Released to archive | 700980 | Submission build | Taylor Chen | M. Sullivan | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0980.csv | Dummy data added for planning demo | Central | 997
[5 empty] | 5.3.1.1 |  | Analysis Data Reviewers Guide | 973 |  |  | 31 days | 2025-07-11 | 2025-07-13 | 2025-08-11 |  | In Progress | Publishing build in progress | 700981 | QC review | Morgan Lee | M. Sullivan | CSV | Analysis_Data_Reviewers_Guide_0981.csv | Placeholder timeline for reporting test | Central | 998
[5 empty] | 5.3.1.1 |  | Analysis programs | 974 |  |  | 15 days | 2025-07-11 |  | 2025-07-26 |  | Not Started | Pending authoring start | 700982 |  | Morgan Lee | R. Gupta | TXT | Analysis_programs_0982.txt | Sample entry for dashboard validation | Central | 999
[5 empty] | 5.3.1.1 |  | 5.3.1.1 p040mk0001 | 975 |  |  | 31 days | 2025-07-09 |  | 2025-08-09 |  | Not Started | Scheduled after current milestone | 700983 |  | Alex Kim | R. Gupta | XLSX | p040mk0001_0983.xlsx | Sample entry for dashboard validation | Central | 1000
[5 empty] | 5.3.1.1 |  | Study report [p040mk0001] and related information | 976 |  |  | 12 days | 2025-07-15 | 2025-07-18 | 2025-07-27 | 2025-08-02 | Completed | QC completed | 700984 | Publishing QC | Jamie Carter | L. Bennett | DOCX | Study_report_p040mk0001_and_related_information_0984.docx | Timing estimate is illustrative | Central | 1001
[5 empty] | 5.3.1.1 |  | Case Report Forms - CRF FOLDER | 977 |  |  | 31 days | 2025-07-12 | 2025-07-12 | 2025-08-12 | 2025-08-11 | Completed | QC completed | 700985 |  | Morgan Lee | R. Gupta | DOCX | Case_Report_Forms_CRF_FOLDER_0985.docx | Dummy data added for planning demo | Central | 1002
[5 empty] | 5.3.1.1 |  | Listing of Case Report Forms (CRFs TOC) | 978 |  |  | 26 days | 2025-07-14 | 2025-07-13 | 2025-08-09 | 2025-08-10 | Completed | Filed in baseline wave | 700986 | Submission build | Jamie Carter | L. Bennett | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_0986.xlsx | Timing estimate is illustrative | Central | 1003
[5 empty] | 5.3.1.1 |  | Case Report Forms - eCRFs (by site) Category 1 and 2 for US | 979 |  |  | 17 days | 2025-07-12 |  | 2025-07-29 |  | Not Started | Scheduled after current milestone | 700987 |  | Sam Brooks | M. Sullivan | DOCX | Case_Report_Forms_eCRFs_by_site_Category_1_and_2_for_US_0987.docx | Placeholder timeline for reporting test | Central | 1004
[5 empty] | 5.3.1.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER | 980 |  |  | 15 days | 2025-07-14 | 2025-07-16 | 2025-07-29 |  | In Progress | Metadata check in progress | 700988 | QC review | Morgan Lee | R. Gupta | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_0988.zip | Placeholder timeline for reporting test | Central | 1005
[5 empty] | 5.3.1.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format SDTM or Legacy format( Choose the correct Data format with team) | 981 |  |  | 21 days | 2025-07-16 | 2025-07-20 | 2025-08-06 |  | In Progress | Publishing build in progress | 700989 | Authoring | Jamie Carter | L. Bennett | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_0989.xlsx | Sample entry for dashboard validation | Central | 1006
[5 empty] | 5.3.1.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format SDTM or Legacy format( Choose the correct Data format with team) (define file) | 982 |  |  | 27 days | 2025-07-17 |  | 2025-08-13 |  | Not Started | Scheduled after current milestone | 700990 |  | Jamie Carter | R. Gupta | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_0990.xlsx | Timing estimate is illustrative | Central | 1007
[5 empty] | 5.3.1.1 |  | Annotated Case Report Forms (CRFs) - SDTM format or Legacy format( Choose the correct Data format with team) | 983 |  |  | 28 days | 2025-07-16 | 2025-07-18 | 2025-08-13 |  | In Progress | Metadata check in progress | 700991 | Authoring | Morgan Lee | L. Bennett | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_or_Legacy_forma_0991.docx | Placeholder timeline for reporting test | Central | 1008
[5 empty] | 5.3.1.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER | 984 |  |  | 24 days | 2025-07-21 | 2025-07-22 | 2025-08-14 |  | In Progress | Pending cross-functional signoff | 700992 |  | Casey Rivera | R. Gupta | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_0992.xlsx | Dummy data added for planning demo | Central | 1009
[5 empty] | 5.3.1.1 |  | Analysis datasets - ADAM format | 985 |  |  | 12 days | 2025-07-17 | 2025-07-22 | 2025-07-29 |  | In Progress | Regional review underway | 700993 |  | Casey Rivera | A. Shah | ZIP | Analysis_datasets_ADAM_format_0993.zip | Sample entry for dashboard validation | Central | 1010
[5 empty] | 5.3.1.1 |  | Data definition for analysis datasets - ADAM format (define file) | 986 |  |  | 14 days | 2025-07-21 | 2025-07-25 | 2025-08-04 |  | In Progress | Draft in QC review | 700994 | Authoring | Alex Kim | R. Gupta | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_0994.csv | Placeholder timeline for reporting test | Central | 1011
[5 empty] | 5.3.1.1 |  | Analysis Data Reviewers Guide | 987 |  |  | 16 days | 2025-07-22 | 2025-07-21 | 2025-08-07 | 2025-08-14 | Completed | Completed as planned | 700995 | Archive release | Jamie Carter | L. Bennett | XLSX | Analysis_Data_Reviewers_Guide_0995.xlsx | Timing estimate is illustrative | Central | 1012
[5 empty] | 5.3.1.1 |  | Analysis programs | 988 |  |  | 25 days | 2025-07-20 | 2025-07-18 | 2025-08-14 | 2025-08-17 | Completed | Filed in baseline wave | 700996 | Archive release | Taylor Chen | M. Sullivan | TXT | Analysis_programs_0996.txt | Placeholder timeline for reporting test | Central | 1013
[5 empty] | 5.3.1.2 |  | 5.3.1.2 p004mk0001 | 989 |  |  | 11 days | 2025-07-16 | 2025-07-15 | 2025-07-27 |  | In Progress | Regional review underway | 700997 | Publishing prep | Jamie Carter | R. Gupta | DOCX | p004mk0001_0997.docx | Timing estimate is illustrative | Central | 1014
[5 empty] | 5.3.1.2 |  | Study report [p004mk0001] and related information | 990 |  |  | 17 days | 2025-07-19 | 2025-07-24 | 2025-08-05 |  | In Progress | Metadata check in progress | 700998 | Publishing prep | Jordan Patel | R. Gupta | DOCX | Study_report_p004mk0001_and_related_information_0998.docx | Dummy data added for planning demo | Central | 1015
[5 empty] | 5.3.1.2 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p004mk0001 | 991 |  |  | 10 days | 2025-07-19 | 2025-07-23 | 2025-07-29 |  | In Progress | Publishing build in progress | 700999 | Regional alignment | Jamie Carter | A. Shah | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_0999.zip | Dummy data added for planning demo | Central | 1016
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 992 |  |  | 18 days | 2025-07-26 | 2025-07-29 | 2025-08-13 | 2025-08-09 | Completed |  | 701000 | Archive release | Jamie Carter | M. Sullivan | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_1000.csv | Placeholder timeline for reporting test | Central | 1017
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 993 |  |  | 27 days | 2025-07-24 | 2025-07-22 | 2025-08-20 | 2025-08-25 | Completed | Completed as planned | 701001 |  | Jamie Carter | A. Shah | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_1001.zip | Timing estimate is illustrative | Central | 1018
[5 empty] | 5.3.1.2 |  | Annotated Case Report Forms (CRFs) - SDTM format | 994 |  |  | 34 days | 2025-07-27 |  | 2025-08-30 |  | Not Started | Resource assignment not yet confirmed | 701002 |  | Casey Rivera | M. Sullivan | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_1002.pdf | Dummy data added for planning demo | Central | 1019
[5 empty] | 5.3.1.2 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p004mk0001 | 995 |  |  | 33 days | 2025-07-26 | 2025-07-31 | 2025-08-28 |  | In Progress | Regional review underway | 701003 | QC review | Sam Brooks | R. Gupta | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p004mk0001_1003.xlsx | Timing estimate is illustrative | Central | 1020
[5 empty] | 5.3.1.2 |  | Analysis datasets - ADAM format | 996 |  |  | 21 days | 2025-07-25 | 2025-07-29 | 2025-08-15 |  | In Progress | Draft in QC review | 701004 | Regional alignment | Taylor Chen | R. Gupta | XLSX | Analysis_datasets_ADAM_format_1004.xlsx | Sample entry for dashboard validation | Central | 1021
[5 empty] | 5.3.1.2 |  | Data definition for analysis datasets - ADAM format (define file) | 997 |  |  | 7 days | 2025-07-21 | 2025-07-24 | 2025-07-28 | 2025-07-26 | Completed | QC completed | 701005 | Submission build | Taylor Chen | R. Gupta | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1005.zip | Sample entry for dashboard validation | Central | 1022
[5 empty] | 5.3.1.2 |  | Analysis Data Reviewers Guide | 998 |  |  | 31 days | 2025-07-25 |  | 2025-08-25 |  | Not Started | Waiting on dependency from Module 3 | 701006 |  | Sam Brooks | M. Sullivan | XLSX | Analysis_Data_Reviewers_Guide_1006.xlsx | Timing estimate is illustrative | Central | 1023
[5 empty] | 5.3.1.2 |  | Analysis programs | 999 |  |  | 13 days | 2025-07-24 | 2025-07-23 | 2025-08-06 |  | In Progress | Draft in QC review | 701007 |  | Taylor Chen | A. Shah | ZIP | Analysis_programs_1007.zip | Placeholder timeline for reporting test | Central | 1024
[5 empty] | 5.3.1.2 |  | 5.3.1.2 p005mk0001 | 1000 |  |  | 17 days | 2025-07-24 |  | 2025-08-10 |  | Not Started | Pending authoring start | 701008 |  | Sam Brooks | N. Ortiz | PDF | p005mk0001_1008.pdf | Placeholder timeline for reporting test | Central | 1025
[5 empty] | 5.3.1.2 |  | Study report [p005mk0001] and related information | 1001 |  |  | 20 days | 2025-07-26 |  | 2025-08-15 |  | Not Started | Pending authoring start | 701009 |  | Jordan Patel | R. Gupta | PDF | Study_report_p005mk0001_and_related_information_1009.pdf | Timing estimate is illustrative | Central | 1026
[5 empty] | 5.3.1.2 |  | Case Report Forms - CRF FOLDER p005mk0001 | 1002 |  |  | 10 days | 2025-07-31 |  | 2025-08-10 |  | Not Started | Scheduled after current milestone | 701010 |  | Alex Kim | L. Bennett | PDF | Case_Report_Forms_CRF_FOLDER_p005mk0001_1010.pdf | Sample entry for dashboard validation | Central | 1027
[5 empty] | 5.3.1.2 |  | Listing of Case Report Forms (CRFs TOC) | 1003 |  |  | 21 days | 2025-07-25 | 2025-07-26 | 2025-08-15 |  | In Progress | Awaiting final source document | 701011 | Regional alignment | Taylor Chen | A. Shah | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_1011.xlsx | Timing estimate is illustrative | Central | 1028
[5 empty] | 5.3.1.2 |  | Case Report Forms - eCRFs (by site) for US | 1004 |  |  | 25 days | 2025-08-02 | 2025-08-01 | 2025-08-27 |  | In Progress | Awaiting final source document | 701012 | QC review | Alex Kim | L. Bennett | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1012.docx | Placeholder timeline for reporting test | Central | 1029
[5 empty] | 5.3.1.2 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p005mk0001 | 1005 |  |  | 13 days | 2025-08-01 | 2025-07-30 | 2025-08-14 | 2025-08-18 | Completed | QC completed | 701013 |  | Morgan Lee | M. Sullivan | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_1013.xlsx | Sample entry for dashboard validation | Central | 1030
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1006 |  |  | 7 days | 2025-07-27 | 2025-07-31 | 2025-08-03 |  | In Progress | Publishing build in progress | 701014 | Authoring | Morgan Lee | R. Gupta | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_1014.csv | Dummy data added for planning demo | Central | 1031
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1007 |  |  | 34 days | 2025-08-02 | 2025-08-03 | 2025-09-05 |  | In Progress | Regional review underway | 701015 | Authoring | Sam Brooks | L. Bennett | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_1015.csv | Dummy data added for planning demo | Central | 1032
[5 empty] | 5.3.1.2 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1008 |  |  | 30 days | 2025-08-01 | 2025-08-04 | 2025-08-31 |  | In Progress | Draft in QC review | 701016 | QC review | Jamie Carter | N. Ortiz | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_1016.pdf | Dummy data added for planning demo | Central | 1033
[5 empty] | 5.3.1.2 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p005mk0001 | 1009 |  |  | 23 days | 2025-07-30 | 2025-08-03 | 2025-08-22 | 2025-08-18 | Completed | Completed as planned | 701017 |  | Jamie Carter | N. Ortiz | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p005mk0001_1017.zip | Placeholder timeline for reporting test | Central | 1034
[5 empty] | 5.3.1.2 |  | Analysis datasets - ADAM format | 1010 |  |  | 26 days | 2025-08-03 | 2025-08-03 | 2025-08-29 |  | In Progress | Publishing build in progress | 701018 | QC review | Jordan Patel | M. Sullivan | XLSX | Analysis_datasets_ADAM_format_1018.xlsx | Timing estimate is illustrative | Central | 1035
[5 empty] | 5.3.1.2 |  | Data definition for analysis datasets - ADAM format (define file) | 1011 |  |  | 35 days | 2025-08-04 |  | 2025-09-08 |  | Not Started | Pending authoring start | 701019 |  | Alex Kim | L. Bennett | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1019.xlsx | Placeholder timeline for reporting test | Central | 1036
[5 empty] | 5.3.1.2 |  | Analysis Data Reviewers Guide | 1012 |  |  | 27 days | 2025-08-05 | 2025-08-07 | 2025-09-01 |  | In Progress | Pending cross-functional signoff | 701020 | Publishing prep | Alex Kim | A. Shah | CSV | Analysis_Data_Reviewers_Guide_1020.csv | Dummy data added for planning demo | Central | 1037
[5 empty] | 5.3.1.2 |  | Analysis programs | 1013 |  |  | 8 days | 2025-08-07 | 2025-08-07 | 2025-08-15 |  | In Progress | Publishing build in progress | 701021 | Authoring | Taylor Chen | L. Bennett | ZIP | Analysis_programs_1021.zip | Timing estimate is illustrative | Central | 1038
[5 empty] | 5.3.1.2 |  | 5.3.1.2 p009mk0001 | 1014 |  |  | 7 days | 2025-08-01 | 2025-08-02 | 2025-08-08 |  | In Progress | Draft in QC review | 701022 | Regional alignment | Alex Kim | A. Shah | DOCX | p009mk0001_1022.docx | Sample entry for dashboard validation | Central | 1039
[5 empty] | 5.3.1.2 |  | Study report [p009mk0001] and related information | 1015 |  |  | 34 days | 2025-08-07 |  | 2025-09-10 |  | Not Started | Scheduled after current milestone | 701023 |  | Jordan Patel | M. Sullivan | PDF | Study_report_p009mk0001_and_related_information_1023.pdf | Placeholder timeline for reporting test | Central | 1040
[5 empty] | 5.3.1.2 |  | Case Report Forms - CRF FOLDER p009mk0001 | 1016 |  |  | 22 days | 2025-08-09 |  | 2025-08-31 |  | Not Started | Waiting on dependency from Module 3 | 701024 |  | Jordan Patel | R. Gupta | DOCX | Case_Report_Forms_CRF_FOLDER_p009mk0001_1024.docx | Dummy data added for planning demo | Central | 1041
[5 empty] | 5.3.1.2 |  | Listing of Case Report Forms (CRFs TOC) | 1017 |  |  | 22 days | 2025-08-09 | 2025-08-10 | 2025-08-31 |  | In Progress | Awaiting final source document | 701025 | QC review | Taylor Chen | N. Ortiz | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_1025.xlsx | Timing estimate is illustrative | Central | 1042
[5 empty] | 5.3.1.2 |  | Case Report Forms - eCRFs (by site) for US | 1018 |  |  | 30 days | 2025-08-04 | 2025-08-07 | 2025-09-03 | 2025-09-03 | Completed |  | 701026 | Publishing QC | Jordan Patel | N. Ortiz | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1026.docx | Timing estimate is illustrative | Central | 1043
[5 empty] | 5.3.1.2 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p009mk0001 | 1019 |  |  | 17 days | 2025-08-07 | 2025-08-12 | 2025-08-24 |  | In Progress | Regional review underway | 701027 |  | Taylor Chen | M. Sullivan | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_1027.zip | Placeholder timeline for reporting test | Central | 1044
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1020 |  |  | 17 days | 2025-08-06 | 2025-08-06 | 2025-08-23 |  | In Progress | Pending cross-functional signoff | 701028 | Authoring | Sam Brooks | L. Bennett | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_1028.zip | Dummy data added for planning demo | Central | 1045
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1021 |  |  | 12 days | 2025-08-08 | 2025-08-05 | 2025-08-20 | 2025-08-19 | Completed | Filed in baseline wave | 701029 |  | Morgan Lee | A. Shah | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_1029.zip | Sample entry for dashboard validation | Central | 1046
[5 empty] | 5.3.1.2 |  | Annotated Case Report Forms (CRFs) - SDTM format p009mk0001 | 1022 |  |  | 34 days | 2025-08-12 | 2025-08-16 | 2025-09-15 |  | In Progress | Publishing build in progress | 701030 | QC review | Casey Rivera | M. Sullivan | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_p009mk0001_1030.docx | Sample entry for dashboard validation | Central | 1047
[5 empty] | 5.3.1.2 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER | 1023 |  |  | 30 days | 2025-08-07 | 2025-08-13 | 2025-09-06 |  | In Progress | Metadata check in progress | 701031 | Publishing prep | Jordan Patel | R. Gupta | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_1031.csv | Sample entry for dashboard validation | Central | 1048
[5 empty] | 5.3.1.2 |  | Analysis datasets - ADAM format | 1024 |  |  | 21 days | 2025-08-14 | 2025-08-17 | 2025-09-04 |  | In Progress | Pending cross-functional signoff | 701032 | Publishing prep | Alex Kim | R. Gupta | CSV | Analysis_datasets_ADAM_format_1032.csv | Dummy data added for planning demo | Central | 1049
[5 empty] | 5.3.1.2 |  | Data definition for analysis datasets - ADAM format (define file) | 1025 |  |  | 11 days | 2025-08-15 | 2025-08-19 | 2025-08-26 | 2025-08-23 | Completed | Completed as planned | 701033 |  | Sam Brooks | R. Gupta | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1033.xlsx | Placeholder timeline for reporting test | Central | 1050
[5 empty] | 5.3.1.2 |  | Analysis Data Reviewers Guide | 1026 |  |  | 21 days | 2025-08-12 | 2025-08-11 | 2025-09-02 |  | In Progress | Pending cross-functional signoff | 701034 | QC review | Casey Rivera | M. Sullivan | XLSX | Analysis_Data_Reviewers_Guide_1034.xlsx | Timing estimate is illustrative | Central | 1051
[5 empty] | 5.3.1.2 |  | Analysis programs | 1027 |  |  | 31 days | 2025-08-11 | 2025-08-13 | 2025-09-11 | 2025-09-15 | Completed |  | 701035 | Submission build | Taylor Chen | M. Sullivan | ZIP | Analysis_programs_1035.zip | Placeholder timeline for reporting test | Central | 1052
[5 empty] | 5.3.1.2 |  | 5.3.1.2 p025mk0001 | 1028 |  |  | 14 days | 2025-08-17 | 2025-08-23 | 2025-08-31 |  | In Progress | Awaiting final source document | 701036 | Publishing prep | Jordan Patel | A. Shah | XLSX | p025mk0001_1036.xlsx | Timing estimate is illustrative | Central | 1053
[5 empty] | 5.3.1.2 |  | Study report [p025mk0001] and related information | 1029 |  |  | 33 days | 2025-08-13 |  | 2025-09-15 |  | Not Started | On hold pending document availability | 701037 |  | Jordan Patel | M. Sullivan | DOCX | Study_report_p025mk0001_and_related_information_1037.docx | Timing estimate is illustrative | Central | 1054
[5 empty] | 5.3.1.2 |  | Case Report Forms - CRF FOLDER p025mk0001 | 1030 |  |  | 8 days | 2025-08-14 |  | 2025-08-22 |  | Not Started | Scheduled after current milestone | 701038 |  | Morgan Lee | L. Bennett | DOCX | Case_Report_Forms_CRF_FOLDER_p025mk0001_1038.docx | Sample entry for dashboard validation | Central | 1055
[5 empty] | 5.3.1.2 |  | Listing of Case Report Forms (CRFs TOC) | 1031 |  |  | 17 days | 2025-08-18 | 2025-08-19 | 2025-09-04 | 2025-08-31 | Completed | Completed as planned | 701039 | Archive release | Sam Brooks | M. Sullivan | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_1039.zip | Placeholder timeline for reporting test | Central | 1056
[5 empty] | 5.3.1.2 |  | Case Report Forms - eCRFs (by site) for US | 1032 |  |  | 30 days | 2025-08-14 | 2025-08-13 | 2025-09-13 |  | In Progress | Draft in QC review | 701040 | Regional alignment | Jordan Patel | N. Ortiz | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1040.docx | Timing estimate is illustrative | Central | 1057
[5 empty] | 5.3.1.2 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p025mk0001 | 1033 |  |  | 19 days | 2025-08-15 | 2025-08-19 | 2025-09-03 |  | In Progress | Publishing build in progress | 701041 |  | Jordan Patel | N. Ortiz | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_1041.csv | Dummy data added for planning demo | Central | 1058
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1034 |  |  | 15 days | 2025-08-16 | 2025-08-19 | 2025-08-31 | 2025-08-28 | Completed |  | 701042 | Submission build | Jordan Patel | L. Bennett | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_1042.xlsx | Placeholder timeline for reporting test | Central | 1059
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1035 |  |  | 7 days | 2025-08-18 | 2025-08-24 | 2025-08-25 |  | In Progress | Metadata check in progress | 701043 |  | Alex Kim | M. Sullivan | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_1043.csv | Timing estimate is illustrative | Central | 1060
[5 empty] | 5.3.1.2 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1036 |  |  | 16 days | 2025-08-21 |  | 2025-09-06 |  | Not Started | Resource assignment not yet confirmed | 701044 |  | Sam Brooks | M. Sullivan | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_1044.docx | Timing estimate is illustrative | Central | 1061
[5 empty] | 5.3.1.2 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p025mk0001 | 1037 |  |  | 35 days | 2025-08-15 |  | 2025-09-19 |  | Not Started | On hold pending document availability | 701045 |  | Morgan Lee | R. Gupta | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p025mk0001_1045.xlsx | Sample entry for dashboard validation | Central | 1062
[5 empty] | 5.3.1.2 |  | Analysis datasets - ADAM format | 1038 |  |  | 10 days | 2025-08-19 | 2025-08-23 | 2025-08-29 |  | In Progress | Pending cross-functional signoff | 701046 | QC review | Sam Brooks | L. Bennett | CSV | Analysis_datasets_ADAM_format_1046.csv | Timing estimate is illustrative | Central | 1063
[5 empty] | 5.3.1.2 |  | Data definition for analysis datasets - ADAM format (define file) | 1039 |  |  | 10 days | 2025-08-24 | 2025-08-26 | 2025-09-03 | 2025-09-02 | Completed | Released to archive | 701047 |  | Casey Rivera | A. Shah | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1047.zip | Dummy data added for planning demo | Central | 1064
[5 empty] | 5.3.1.2 |  | Analysis Data Reviewers Guide | 1040 |  |  | 33 days | 2025-08-20 | 2025-08-22 | 2025-09-22 |  | In Progress | Metadata check in progress | 701048 |  | Morgan Lee | L. Bennett | ZIP | Analysis_Data_Reviewers_Guide_1048.zip | Placeholder timeline for reporting test | Central | 1065
[5 empty] | 5.3.1.2 |  | Analysis programs | 1041 |  |  | 9 days | 2025-08-22 | 2025-08-26 | 2025-08-31 | 2025-08-30 | Completed |  | 701049 |  | Jordan Patel | M. Sullivan | TXT | Analysis_programs_1049.txt | Placeholder timeline for reporting test | Central | 1066
[5 empty] | 5.3.1.2 |  | 5.3.1.2 p035mk0001 | 1042 |  |  | 31 days | 2025-08-18 |  | 2025-09-18 |  | Not Started | Scheduled after current milestone | 701050 |  | Taylor Chen | M. Sullivan | XLSX | p035mk0001_1050.xlsx | Sample entry for dashboard validation | Central | 1067
[5 empty] | 5.3.1.2 |  | Study report [p035mk0001] and related information | 1043 |  |  | 34 days | 2025-08-26 |  | 2025-09-29 |  | Not Started | Scheduled after current milestone | 701051 |  | Alex Kim | M. Sullivan | PDF | Study_report_p035mk0001_and_related_information_1051.pdf | Dummy data added for planning demo | Central | 1068
[5 empty] | 5.3.1.2 |  | Case Report Forms - CRF FOLDER p035mk0001 | 1044 |  |  | 10 days | 2025-08-20 |  | 2025-08-30 |  | Not Started | Pending authoring start | 701052 |  | Morgan Lee | M. Sullivan | DOCX | Case_Report_Forms_CRF_FOLDER_p035mk0001_1052.docx | Sample entry for dashboard validation | Central | 1069
[5 empty] | 5.3.1.2 |  | Listing of Case Report Forms (CRFs TOC) | 1045 |  |  | 18 days | 2025-08-19 | 2025-08-24 | 2025-09-06 |  | In Progress | Publishing build in progress | 701053 |  | Jamie Carter | M. Sullivan | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_1053.xlsx | Sample entry for dashboard validation | Central | 1070
[5 empty] | 5.3.1.2 |  | Case Report Forms - eCRFs (by site) for US | 1046 |  |  | 28 days | 2025-08-26 |  | 2025-09-23 |  | Not Started | Pending authoring start | 701054 |  | Taylor Chen | N. Ortiz | PDF | Case_Report_Forms_eCRFs_by_site_for_US_1054.pdf | Placeholder timeline for reporting test | Central | 1071
[5 empty] | 5.3.1.2 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p035mk0001 | 1047 |  |  | 16 days | 2025-08-21 |  | 2025-09-06 |  | Not Started | Planned for upcoming wave | 701055 |  | Sam Brooks | L. Bennett | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p03_1055.csv | Placeholder timeline for reporting test | Central | 1072
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1048 |  |  | 18 days | 2025-08-26 |  | 2025-09-13 |  | Not Started | Pending authoring start | 701056 |  | Morgan Lee | L. Bennett | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_1056.xlsx | Placeholder timeline for reporting test | Central | 1073
[5 empty] | 5.3.1.2 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1049 |  |  | 29 days | 2025-08-29 |  | 2025-09-27 |  | Not Started | Waiting on dependency from Module 3 | 701057 |  | Jamie Carter | N. Ortiz | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_1057.xlsx | Placeholder timeline for reporting test | Central | 1074
[5 empty] | 5.3.1.2 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1050 |  |  | 31 days | 2025-08-28 | 2025-08-28 | 2025-09-28 |  | In Progress | Publishing build in progress | 701058 | Authoring | Morgan Lee | R. Gupta | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_1058.pdf | Placeholder timeline for reporting test | Central | 1075
[5 empty] | 5.3.1.2 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p035mk0001 | 1051 |  |  | 10 days | 2025-08-27 |  | 2025-09-06 |  | Not Started | Planned for upcoming wave | 701059 |  | Sam Brooks | L. Bennett | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p035mk0001_1059.csv | Sample entry for dashboard validation | Central | 1076
[5 empty] | 5.3.1.2 |  | Analysis datasets - ADAM format | 1052 |  |  | 31 days | 2025-08-25 | 2025-08-27 | 2025-09-25 |  | In Progress | Regional review underway | 701060 | Regional alignment | Morgan Lee | R. Gupta | CSV | Analysis_datasets_ADAM_format_1060.csv | Placeholder timeline for reporting test | Central | 1077
[5 empty] | 5.3.1.2 |  | Data definition for analysis datasets - ADAM format (define file) | 1053 |  |  | 12 days | 2025-08-26 | 2025-08-25 | 2025-09-07 |  | In Progress | Awaiting final source document | 701061 |  | Morgan Lee | M. Sullivan | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1061.zip | Placeholder timeline for reporting test | Central | 1078
[5 empty] | 5.3.1.2 |  | Analysis Data Reviewers Guide | 1054 |  |  | 24 days | 2025-09-02 | 2025-08-31 | 2025-09-26 | 2025-09-25 | Completed | Completed as planned | 701062 | Publishing QC | Sam Brooks | M. Sullivan | ZIP | Analysis_Data_Reviewers_Guide_1062.zip | Sample entry for dashboard validation | Central | 1079
[5 empty] | 5.3.1.2 |  | Analysis programs | 1055 |  |  | 11 days | 2025-08-29 | 2025-09-04 | 2025-09-09 |  | In Progress | Metadata check in progress | 701063 | Regional alignment | Jordan Patel | L. Bennett | ZIP | Analysis_programs_1063.zip | Placeholder timeline for reporting test | Central | 1080
[5 empty] | 5.3.3 |  | 5.3.3 Reports of human pharmacokinetic (PK) studies | 1056 |  |  | 40 days | 2025-08-27 |  | 2025-10-06 |  | Not Started | Scheduled after current milestone | 701064 |  | Jamie Carter | A. Shah | PDF | Reports_of_human_pharmacokinetic_PK_studies_1064.pdf | Timing estimate is illustrative | Central | 1081
[5 empty] | 5.3.3.1 |  | 5.3.3.1 p001mk0001 | 1057 |  |  | 7 days | 2025-08-30 | 2025-08-31 | 2025-09-06 |  | In Progress | Awaiting final source document | 701065 | QC review | Casey Rivera | N. Ortiz | PDF | p001mk0001_1065.pdf | Dummy data added for planning demo | Central | 1082
[5 empty] | 5.3.3.1 |  | Study report [p001mk0001] and related information | 1058 |  |  | 14 days | 2025-08-31 |  | 2025-09-14 |  | Not Started | Resource assignment not yet confirmed | 701066 |  | Casey Rivera | L. Bennett | DOCX | Study_report_p001mk0001_and_related_information_1066.docx | Timing estimate is illustrative | Central | 1083
[5 empty] | 5.3.3.1 |  | Case Report Forms - CRF FOLDER p001mk0001 | 1059 |  |  | 12 days | 2025-09-03 |  | 2025-09-15 |  | Not Started | Resource assignment not yet confirmed | 701067 |  | Casey Rivera | M. Sullivan | DOCX | Case_Report_Forms_CRF_FOLDER_p001mk0001_1067.docx | Placeholder timeline for reporting test | Central | 1084
[5 empty] | 5.3.3.1 |  | Listing of Case Report Forms (CRFs TOC) | 1060 |  |  | 32 days | 2025-09-02 |  | 2025-10-04 |  | Not Started | Scheduled after current milestone | 701068 |  | Morgan Lee | R. Gupta | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_1068.xlsx | Placeholder timeline for reporting test | Central | 1085
[5 empty] | 5.3.3.1 |  | Case Report Forms - eCRFs (by site) for US | 1061 |  |  | 18 days | 2025-09-06 | 2025-09-05 | 2025-09-24 | 2025-09-25 | Completed | Filed in baseline wave | 701069 |  | Taylor Chen | N. Ortiz | PDF | Case_Report_Forms_eCRFs_by_site_for_US_1069.pdf | Sample entry for dashboard validation | Central | 1086
[5 empty] | 5.3.3.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p001mk0001 | 1062 |  |  | 17 days | 2025-09-07 | 2025-09-07 | 2025-09-24 | 2025-10-01 | Completed | QC completed | 701070 |  | Jamie Carter | N. Ortiz | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_1070.csv | Placeholder timeline for reporting test | Central | 1087
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1063 |  |  | 21 days | 2025-08-30 | 2025-09-04 | 2025-09-20 |  | In Progress | Pending cross-functional signoff | 701071 | Regional alignment | Alex Kim | N. Ortiz | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_1071.xlsx | Sample entry for dashboard validation | Central | 1088
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1064 |  |  | 27 days | 2025-09-08 | 2025-09-10 | 2025-10-05 | 2025-10-08 | Completed | Filed in baseline wave | 701072 | Publishing QC | Sam Brooks | R. Gupta | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_1072.xlsx | Placeholder timeline for reporting test | Central | 1089
[5 empty] | 5.3.3.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1065 |  |  | 35 days | 2025-09-04 | 2025-09-09 | 2025-10-09 |  | In Progress | Publishing build in progress | 701073 | QC review | Casey Rivera | N. Ortiz | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_1073.docx | Placeholder timeline for reporting test | Central | 1090
[5 empty] | 5.3.3.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p001mk0001 | 1066 |  |  | 29 days | 2025-09-09 | 2025-09-12 | 2025-10-08 |  | In Progress | Awaiting final source document | 701074 |  | Jamie Carter | M. Sullivan | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p001mk0001_1074.csv | Timing estimate is illustrative | Central | 1091
[5 empty] | 5.3.3.1 |  | Analysis datasets - ADAM format | 1067 |  |  | 28 days | 2025-09-10 | 2025-09-08 | 2025-10-08 |  | In Progress | Pending cross-functional signoff | 701075 | Authoring | Sam Brooks | R. Gupta | ZIP | Analysis_datasets_ADAM_format_1075.zip | Dummy data added for planning demo | Central | 1092
[5 empty] | 5.3.3.1 |  | Data definition for analysis datasets - ADAM format (define file) | 1068 |  |  | 26 days | 2025-09-03 | 2025-09-06 | 2025-09-29 | 2025-10-06 | Completed | Filed in baseline wave | 701076 | Submission build | Jordan Patel | M. Sullivan | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1076.xlsx | Timing estimate is illustrative | Central | 1093
[5 empty] | 5.3.3.1 |  | Analysis Data Reviewers Guide | 1069 |  |  | 27 days | 2025-09-03 |  | 2025-09-30 |  | Not Started | On hold pending document availability | 701077 |  | Alex Kim | R. Gupta | XLSX | Analysis_Data_Reviewers_Guide_1077.xlsx | Dummy data added for planning demo | Central | 1094
[5 empty] | 5.3.3.1 |  | Analysis programs | 1070 |  |  | 25 days | 2025-09-09 | 2025-09-13 | 2025-10-04 |  | In Progress | Publishing build in progress | 701078 | Regional alignment | Sam Brooks | L. Bennett | ZIP | Analysis_programs_1078.zip | Placeholder timeline for reporting test | Central | 1095
[5 empty] | 5.3.3.1 |  | 5.3.3.1 p003mk0001 | 1071 |  |  | 10 days | 2025-09-06 | 2025-09-06 | 2025-09-16 |  | In Progress | Regional review underway | 701079 | Regional alignment | Morgan Lee | L. Bennett | PDF | p003mk0001_1079.pdf | Timing estimate is illustrative | Central | 1096
[5 empty] | 5.3.3.1 |  | Study report [p003mk0001] and related information | 1072 |  |  | 19 days | 2025-09-09 | 2025-09-11 | 2025-09-28 | 2025-10-04 | Completed | Completed as planned | 701080 | Archive release | Casey Rivera | A. Shah | DOCX | Study_report_p003mk0001_and_related_information_1080.docx | Dummy data added for planning demo | Central | 1097
[5 empty] | 5.3.3.1 |  | Case Report Forms - CRF FOLDER | 1073 |  |  | 24 days | 2025-09-05 | 2025-09-07 | 2025-09-29 | 2025-09-26 | Completed | Filed in baseline wave | 701081 | Publishing QC | Taylor Chen | A. Shah | PDF | Case_Report_Forms_CRF_FOLDER_1081.pdf | Placeholder timeline for reporting test | Central | 1098
[5 empty] | 5.3.3.1 |  | Listing of Case Report Forms (CRFs TOC) | 1074 |  |  | 16 days | 2025-09-12 | 2025-09-14 | 2025-09-28 | 2025-09-25 | Completed | Filed in baseline wave | 701082 | Submission build | Sam Brooks | M. Sullivan | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_1082.csv | Timing estimate is illustrative | Central | 1099
[5 empty] | 5.3.3.1 |  | Case Report Forms - eCRFs (by site) Category 1 and 2 for US | 1075 |  |  | 13 days | 2025-09-14 |  | 2025-09-27 |  | Not Started | Planned for upcoming wave | 701083 |  | Jamie Carter | N. Ortiz | DOCX | Case_Report_Forms_eCRFs_by_site_Category_1_and_2_for_US_1083.docx | Timing estimate is illustrative | Central | 1100
[5 empty] | 5.3.3.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER | 1076 |  |  | 29 days | 2025-09-14 |  | 2025-10-13 |  | Not Started | Pending authoring start | 701084 |  | Taylor Chen | N. Ortiz | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_1084.csv | Dummy data added for planning demo | Central | 1101
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data tabulation datasets - SDTM or Legacy format( Choose the correct Data format with team) | 1077 |  |  | 24 days | 2025-09-08 |  | 2025-10-02 |  | Not Started | Planned for upcoming wave | 701085 |  | Jamie Carter | R. Gupta | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_1085.csv | Dummy data added for planning demo | Central | 1102
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM or Legacy format (define file)( Choose the correct Data format with team) | 1078 |  |  | 28 days | 2025-09-13 | 2025-09-18 | 2025-10-11 | 2025-10-09 | Completed | Completed as planned | 701086 |  | Jordan Patel | M. Sullivan | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_1086.xlsx | Placeholder timeline for reporting test | Central | 1103
[5 empty] | 5.3.3.1 |  | Annotated Case Report Forms (CRFs) - SDTM or Legacy format ( Choose the correct Data format with team) | 1079 |  |  | 28 days | 2025-09-16 | 2025-09-20 | 2025-10-14 |  | In Progress | Publishing build in progress | 701087 | Authoring | Sam Brooks | M. Sullivan | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_or_Legacy_format_Choos_1087.pdf | Placeholder timeline for reporting test | Central | 1104
[5 empty] | 5.3.3.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER | 1080 |  |  | 18 days | 2025-09-12 | 2025-09-16 | 2025-09-30 | 2025-09-29 | Completed | Released to archive | 701088 | Publishing QC | Morgan Lee | A. Shah | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_1088.csv | Dummy data added for planning demo | Central | 1105
[5 empty] | 5.3.3.1 |  | Analysis datasets - ADAM format | 1081 |  |  | 9 days | 2025-09-18 | 2025-09-21 | 2025-09-27 |  | In Progress | Pending cross-functional signoff | 701089 |  | Taylor Chen | M. Sullivan | ZIP | Analysis_datasets_ADAM_format_1089.zip | Sample entry for dashboard validation | Central | 1106
[5 empty] | 5.3.3.1 |  | Data definition for analysis datasets - ADAM format (define file) | 1082 |  |  | 27 days | 2025-09-19 | 2025-09-21 | 2025-10-16 | 2025-10-14 | Completed | Released to archive | 701090 | Submission build | Morgan Lee | L. Bennett | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1090.csv | Sample entry for dashboard validation | Central | 1107
[5 empty] | 5.3.3.1 |  | Analysis Data Reviewers Guide | 1083 |  |  | 9 days | 2025-09-17 | 2025-09-22 | 2025-09-26 |  | In Progress | Draft in QC review | 701091 | Publishing prep | Taylor Chen | L. Bennett | ZIP | Analysis_Data_Reviewers_Guide_1091.zip | Sample entry for dashboard validation | Central | 1108
[5 empty] | 5.3.3.1 |  | Analysis programs | 1084 |  |  | 22 days | 2025-09-16 |  | 2025-10-08 |  | Not Started | Waiting on dependency from Module 3 | 701092 |  | Jamie Carter | A. Shah | ZIP | Analysis_programs_1092.zip | Timing estimate is illustrative | Central | 1109
[5 empty] | 5.3.3.1 |  | 5.3.3.1 p006mk0001 | 1085 |  |  | 16 days | 2025-09-13 |  | 2025-09-29 |  | Not Started | On hold pending document availability | 701093 |  | Taylor Chen | M. Sullivan | PDF | p006mk0001_1093.pdf | Placeholder timeline for reporting test | Central | 1110
[5 empty] | 5.3.3.1 |  | Study report [p006mk0001] and related information | 1086 |  |  | 24 days | 2025-09-13 | 2025-09-14 | 2025-10-07 | 2025-10-09 | Completed | Filed in baseline wave | 701094 | Archive release | Taylor Chen | A. Shah | DOCX | Study_report_p006mk0001_and_related_information_1094.docx | Timing estimate is illustrative | Central | 1111
[5 empty] | 5.3.3.1 |  | Case Report Forms - CRF FOLDER p006mk0001 | 1087 |  |  | 18 days | 2025-09-22 | 2025-09-20 | 2025-10-10 |  | In Progress | Awaiting final source document | 701095 | Authoring | Casey Rivera | N. Ortiz | PDF | Case_Report_Forms_CRF_FOLDER_p006mk0001_1095.pdf | Placeholder timeline for reporting test | Central | 1112
[5 empty] | 5.3.3.1 |  | Listing of Case Report Forms (CRFs TOC) | 1088 |  |  | 29 days | 2025-09-15 | 2025-09-15 | 2025-10-14 | 2025-10-19 | Completed |  | 701096 | Publishing QC | Alex Kim | L. Bennett | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_1096.xlsx | Dummy data added for planning demo | Central | 1113
[5 empty] | 5.3.3.1 |  | Case Report Forms - eCRFs (by site) for US | 1089 |  |  | 7 days | 2025-09-19 |  | 2025-09-26 |  | Not Started | On hold pending document availability | 701097 |  | Jamie Carter | R. Gupta | PDF | Case_Report_Forms_eCRFs_by_site_for_US_1097.pdf | Sample entry for dashboard validation | Central | 1114
[5 empty] | 5.3.3.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p006mk0001 | 1090 |  |  | 18 days | 2025-09-19 |  | 2025-10-07 |  | Not Started | Scheduled after current milestone | 701098 |  | Alex Kim | N. Ortiz | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_1098.xlsx | Timing estimate is illustrative | Central | 1115
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1091 |  |  | 35 days | 2025-09-20 |  | 2025-10-25 |  | Not Started | On hold pending document availability | 701099 |  | Taylor Chen | R. Gupta | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_1099.xlsx | Placeholder timeline for reporting test | Central | 1116
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1092 |  |  | 29 days | 2025-09-23 | 2025-09-26 | 2025-10-22 | 2025-10-24 | Completed | QC completed | 701100 | Submission build | Jamie Carter | L. Bennett | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_1100.csv | Dummy data added for planning demo | Central | 1117
[5 empty] | 5.3.3.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1093 |  |  | 8 days | 2025-09-23 | 2025-09-28 | 2025-10-01 |  | In Progress | Awaiting final source document | 701101 | QC review | Alex Kim | A. Shah | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_1101.pdf | Timing estimate is illustrative | Central | 1118
[5 empty] | 5.3.3.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p006mk0001 | 1094 |  |  | 9 days | 2025-09-25 | 2025-09-27 | 2025-10-04 | 2025-10-02 | Completed | QC completed | 701102 |  | Morgan Lee | M. Sullivan | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p006mk0001_1102.csv | Placeholder timeline for reporting test | Central | 1119
[5 empty] | 5.3.3.1 |  | Analysis datasets - ADAM format | 1095 |  |  | 10 days | 2025-09-23 | 2025-09-27 | 2025-10-03 |  | In Progress | Awaiting final source document | 701103 | Authoring | Taylor Chen | L. Bennett | XLSX | Analysis_datasets_ADAM_format_1103.xlsx | Timing estimate is illustrative | Central | 1120
[5 empty] | 5.3.3.1 |  | Data definition for analysis datasets - ADAM format (define file) | 1096 |  |  | 8 days | 2025-09-27 | 2025-09-26 | 2025-10-05 |  | In Progress | Draft in QC review | 701104 | QC review | Alex Kim | L. Bennett | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1104.xlsx | Dummy data added for planning demo | Central | 1121
[5 empty] | 5.3.3.1 |  | Analysis Data Reviewers Guide | 1097 |  |  | 14 days | 2025-09-21 | 2025-09-24 | 2025-10-05 |  | In Progress | Publishing build in progress | 701105 | QC review | Casey Rivera | M. Sullivan | XLSX | Analysis_Data_Reviewers_Guide_1105.xlsx | Timing estimate is illustrative | Central | 1122
[5 empty] | 5.3.3.1 |  | Analysis programs | 1098 |  |  | 30 days | 2025-09-23 | 2025-09-21 | 2025-10-23 |  | In Progress | Awaiting final source document | 701106 | Publishing prep | Jamie Carter | R. Gupta | ZIP | Analysis_programs_1106.zip | Placeholder timeline for reporting test | Central | 1123
[5 empty] | 5.3.3.1 |  | 5.3.3.1 p010mk0001 | 1099 |  |  | 13 days | 2025-09-28 |  | 2025-10-11 |  | Not Started | Planned for upcoming wave | 701107 |  | Casey Rivera | L. Bennett | PDF | p010mk0001_1107.pdf | Placeholder timeline for reporting test | Central | 1124
[5 empty] | 5.3.3.1 |  | Study report [p010mk0001] and related information | 1100 |  |  | 9 days | 2025-09-30 | 2025-09-30 | 2025-10-09 | 2025-10-10 | Completed | Released to archive | 701108 | Publishing QC | Jamie Carter | L. Bennett | PDF | Study_report_p010mk0001_and_related_information_1108.pdf | Timing estimate is illustrative | Central | 1125
[5 empty] | 5.3.3.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p010mk0001 | 1101 |  |  | 16 days | 2025-09-30 | 2025-09-30 | 2025-10-16 |  | In Progress | Pending cross-functional signoff | 701109 | Publishing prep | Alex Kim | A. Shah | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_1109.zip | Dummy data added for planning demo | Central | 1126
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1102 |  |  | 23 days | 2025-09-29 | 2025-09-29 | 2025-10-22 |  | In Progress | Regional review underway | 701110 | Publishing prep | Morgan Lee | A. Shah | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_1110.xlsx | Dummy data added for planning demo | Central | 1127
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1103 |  |  | 7 days | 2025-09-26 | 2025-09-24 | 2025-10-03 |  | In Progress | Publishing build in progress | 701111 |  | Alex Kim | N. Ortiz | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_1111.zip | Dummy data added for planning demo | Central | 1128
[5 empty] | 5.3.3.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1104 |  |  | 9 days | 2025-10-02 | 2025-10-06 | 2025-10-11 | 2025-10-16 | Completed | Released to archive | 701112 | Archive release | Sam Brooks | M. Sullivan | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_1112.docx | Sample entry for dashboard validation | Central | 1129
[5 empty] | 5.3.3.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p010mk0001 | 1105 |  |  | 28 days | 2025-09-28 | 2025-09-30 | 2025-10-26 |  | In Progress | Metadata check in progress | 701113 | Regional alignment | Casey Rivera | N. Ortiz | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p010mk0001_1113.csv | Placeholder timeline for reporting test | Central | 1130
[5 empty] | 5.3.3.1 |  | Analysis datasets - ADAM format | 1106 |  |  | 11 days | 2025-09-28 | 2025-09-28 | 2025-10-09 |  | In Progress | Publishing build in progress | 701114 | Publishing prep | Jordan Patel | R. Gupta | ZIP | Analysis_datasets_ADAM_format_1114.zip | Dummy data added for planning demo | Central | 1131
[5 empty] | 5.3.3.1 |  | Data definition for analysis datasets - ADAM format (define file) | 1107 |  |  | 32 days | 2025-10-02 | 2025-09-30 | 2025-11-03 |  | In Progress | Publishing build in progress | 701115 | Regional alignment | Sam Brooks | M. Sullivan | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1115.xlsx | Sample entry for dashboard validation | Central | 1132
[5 empty] | 5.3.3.1 |  | Analysis Data Reviewers Guide | 1108 |  |  | 33 days | 2025-09-28 | 2025-09-29 | 2025-10-31 |  | In Progress | Publishing build in progress | 701116 | Regional alignment | Casey Rivera | L. Bennett | ZIP | Analysis_Data_Reviewers_Guide_1116.zip | Sample entry for dashboard validation | Central | 1133
[5 empty] | 5.3.3.1 |  | Analysis programs | 1109 |  |  | 19 days | 2025-10-04 | 2025-10-07 | 2025-10-23 |  | In Progress | Metadata check in progress | 701117 | Regional alignment | Jordan Patel | M. Sullivan | ZIP | Analysis_programs_1117.zip | Timing estimate is illustrative | Central | 1134
[5 empty] | 5.3.3.1 |  | 5.3.3.1 p012mk0001 | 1110 |  |  | 29 days | 2025-10-01 | 2025-10-01 | 2025-10-30 | 2025-11-06 | Completed |  | 701118 | Archive release | Casey Rivera | M. Sullivan | DOCX | p012mk0001_1118.docx | Placeholder timeline for reporting test | Central | 1135
[5 empty] | 5.3.3.1 |  | Study report [p012mk0001 ] and related information | 1111 |  |  | 13 days | 2025-10-02 | 2025-10-07 | 2025-10-15 |  | In Progress | Draft in QC review | 701119 |  | Sam Brooks | L. Bennett | DOCX | Study_report_p012mk0001_and_related_information_1119.docx | Sample entry for dashboard validation | Central | 1136
[5 empty] | 5.3.3.1 |  | Case Report Forms - CRF FOLDER p012mk0001 | 1112 |  |  | 13 days | 2025-09-29 | 2025-10-04 | 2025-10-12 | 2025-10-10 | Completed | Released to archive | 701120 |  | Casey Rivera | N. Ortiz | DOCX | Case_Report_Forms_CRF_FOLDER_p012mk0001_1120.docx | Dummy data added for planning demo | Central | 1137
[5 empty] | 5.3.3.1 |  | Listing of Case Report Forms (CRFs TOC) | 1113 |  |  | 19 days | 2025-10-02 | 2025-10-02 | 2025-10-21 |  | In Progress | Metadata check in progress | 701121 |  | Jamie Carter | N. Ortiz | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_1121.zip | Sample entry for dashboard validation | Central | 1138
[5 empty] | 5.3.3.1 |  | Case Report Forms - eCRFs (by site) for US | 1114 |  |  | 11 days | 2025-10-03 | 2025-10-08 | 2025-10-14 |  | In Progress | Awaiting final source document | 701122 | QC review | Jamie Carter | L. Bennett | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1122.docx | Dummy data added for planning demo | Central | 1139
[5 empty] | 5.3.3.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p012mk0001 | 1115 |  |  | 32 days | 2025-10-02 | 2025-09-29 | 2025-11-03 | 2025-10-30 | Completed | Completed as planned | 701123 | Archive release | Jamie Carter | A. Shah | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_1123.csv | Placeholder timeline for reporting test | Central | 1140
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1116 |  |  | 30 days | 2025-10-04 | 2025-10-04 | 2025-11-03 | 2025-11-03 | Completed | Completed as planned | 701124 | Archive release | Taylor Chen | R. Gupta | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_1124.zip | Sample entry for dashboard validation | Central | 1141
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1117 |  |  | 17 days | 2025-10-09 | 2025-10-11 | 2025-10-26 |  | In Progress | Metadata check in progress | 701125 | Authoring | Jamie Carter | M. Sullivan | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_1125.xlsx | Timing estimate is illustrative | Central | 1142
[5 empty] | 5.3.3.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1118 |  |  | 20 days | 2025-10-04 | 2025-10-07 | 2025-10-24 | 2025-10-22 | Completed |  | 701126 |  | Sam Brooks | L. Bennett | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_1126.docx | Timing estimate is illustrative | Central | 1143
[5 empty] | 5.3.3.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p012mk0001 | 1119 |  |  | 28 days | 2025-10-04 |  | 2025-11-01 |  | Not Started | Scheduled after current milestone | 701127 |  | Alex Kim | A. Shah | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p012mk0001_1127.xlsx | Sample entry for dashboard validation | Central | 1144
[5 empty] | 5.3.3.1 |  | Analysis datasets - ADAM format | 1120 |  |  | 19 days | 2025-10-11 | 2025-10-09 | 2025-10-30 |  | In Progress | Pending cross-functional signoff | 701128 | Publishing prep | Casey Rivera | M. Sullivan | ZIP | Analysis_datasets_ADAM_format_1128.zip | Timing estimate is illustrative | Central | 1145
[5 empty] | 5.3.3.1 |  | Data definition for analysis datasets - ADAM format (define file) | 1121 |  |  | 35 days | 2025-10-11 | 2025-10-15 | 2025-11-15 | 2025-11-21 | Completed |  | 701129 | Archive release | Morgan Lee | A. Shah | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1129.csv | Dummy data added for planning demo | Central | 1146
[5 empty] | 5.3.3.1 |  | Analysis Data Reviewers Guide | 1122 |  |  | 11 days | 2025-10-07 | 2025-10-11 | 2025-10-18 |  | In Progress | Awaiting final source document | 701130 | Authoring | Jamie Carter | N. Ortiz | ZIP | Analysis_Data_Reviewers_Guide_1130.zip | Placeholder timeline for reporting test | Central | 1147
[5 empty] | 5.3.3.1 |  | Analysis programs | 1123 |  |  | 29 days | 2025-10-10 | 2025-10-09 | 2025-11-08 |  | In Progress | Metadata check in progress | 701131 |  | Jamie Carter | L. Bennett | ZIP | Analysis_programs_1131.zip | Sample entry for dashboard validation | Central | 1148
[5 empty] | 5.3.3.1 |  | 5.3.3.1 p016mk0001 | 1124 |  |  | 18 days | 2025-10-08 |  | 2025-10-26 |  | Not Started | Pending authoring start | 701132 |  | Taylor Chen | R. Gupta | XLSX | p016mk0001_1132.xlsx | Dummy data added for planning demo | Central | 1149
[5 empty] | 5.3.3.1 |  | Study report [p016mk0001] and related information | 1125 |  |  | 17 days | 2025-10-14 |  | 2025-10-31 |  | Not Started | Planned for upcoming wave | 701133 |  | Sam Brooks | N. Ortiz | DOCX | Study_report_p016mk0001_and_related_information_1133.docx | Placeholder timeline for reporting test | Central | 1150
[5 empty] | 5.3.3.1 |  | Case Report Forms - CRF FOLDER p016mk0001 | 1126 |  |  | 20 days | 2025-10-14 | 2025-10-16 | 2025-11-03 |  | In Progress | Regional review underway | 701134 | Regional alignment | Sam Brooks | A. Shah | DOCX | Case_Report_Forms_CRF_FOLDER_p016mk0001_1134.docx | Dummy data added for planning demo | Central | 1151
[5 empty] | 5.3.3.1 |  | Listing of Case Report Forms (CRFs TOC) | 1127 |  |  | 34 days | 2025-10-10 |  | 2025-11-13 |  | Not Started | Resource assignment not yet confirmed | 701135 |  | Alex Kim | M. Sullivan | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_1135.xlsx | Placeholder timeline for reporting test | Central | 1152
[5 empty] | 5.3.3.1 |  | Case Report Forms - eCRFs (by site) for US | 1128 |  |  | 13 days | 2025-10-15 |  | 2025-10-28 |  | Not Started | Scheduled after current milestone | 701136 |  | Casey Rivera | A. Shah | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1136.docx | Sample entry for dashboard validation | Central | 1153
[5 empty] | 5.3.3.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p016mk0001 | 1129 |  |  | 18 days | 2025-10-14 |  | 2025-11-01 |  | Not Started | Scheduled after current milestone | 701137 |  | Casey Rivera | R. Gupta | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_1137.xlsx | Placeholder timeline for reporting test | Central | 1154
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1130 |  |  | 24 days | 2025-10-14 | 2025-10-15 | 2025-11-07 | 2025-11-07 | Completed | Completed as planned | 701138 |  | Sam Brooks | A. Shah | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_1138.zip | Placeholder timeline for reporting test | Central | 1155
[5 empty] | 5.3.3.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1131 |  |  | 35 days | 2025-10-18 | 2025-10-17 | 2025-11-22 | 2025-11-19 | Completed | Filed in baseline wave | 701139 | Publishing QC | Jordan Patel | R. Gupta | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_1139.xlsx | Timing estimate is illustrative | Central | 1156
[5 empty] | 5.3.3.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1132 |  |  | 31 days | 2025-10-14 | 2025-10-12 | 2025-11-14 | 2025-11-10 | Completed | Completed as planned | 701140 | Archive release | Jamie Carter | M. Sullivan | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_1140.pdf | Timing estimate is illustrative | Central | 1157
[5 empty] | 5.3.3.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p016mk0001 | 1133 |  |  | 27 days | 2025-10-19 |  | 2025-11-15 |  | Not Started | On hold pending document availability | 701141 |  | Alex Kim | M. Sullivan | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p016mk0001_1141.xlsx | Dummy data added for planning demo | Central | 1158
[5 empty] | 5.3.3.1 |  | Analysis datasets - ADAM format | 1134 |  |  | 13 days | 2025-10-14 |  | 2025-10-27 |  | Not Started | Planned for upcoming wave | 701142 |  | Jordan Patel | A. Shah | ZIP | Analysis_datasets_ADAM_format_1142.zip | Dummy data added for planning demo | Central | 1159
[5 empty] | 5.3.3.1 |  | Data definition for analysis datasets - ADAM format (define file) | 1135 |  |  | 20 days | 2025-10-13 | 2025-10-14 | 2025-11-02 |  | In Progress | Awaiting final source document | 701143 | Authoring | Sam Brooks | A. Shah | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1143.csv | Placeholder timeline for reporting test | Central | 1160
[5 empty] | 5.3.3.1 |  | Analysis Data Reviewers Guide | 1136 |  |  | 13 days | 2025-10-21 | 2025-10-22 | 2025-11-03 |  | In Progress | Regional review underway | 701144 | Regional alignment | Taylor Chen | N. Ortiz | CSV | Analysis_Data_Reviewers_Guide_1144.csv | Placeholder timeline for reporting test | Central | 1161
[5 empty] | 5.3.3.1 |  | Analysis programs | 1137 |  |  | 21 days | 2025-10-14 | 2025-10-11 | 2025-11-04 | 2025-11-01 | Completed | Filed in baseline wave | 701145 | Submission build | Morgan Lee | N. Ortiz | ZIP | Analysis_programs_1145.zip | Dummy data added for planning demo | Central | 1162
[5 empty] | 5.3.3.3 |  | 5.3.3.3 p007mk0001 | 1138 |  |  | 13 days | 2025-10-16 | 2025-10-18 | 2025-10-29 | 2025-10-28 | Completed | Filed in baseline wave | 701146 |  | Sam Brooks | M. Sullivan | DOCX | p007mk0001_1146.docx | Sample entry for dashboard validation | Central | 1191
[5 empty] | 5.3.3.3 |  | Study report [p007mk0001] and related information | 1139 |  |  | 27 days | 2025-10-23 | 2025-10-27 | 2025-11-19 |  | In Progress | Metadata check in progress | 701147 | Publishing prep | Sam Brooks | N. Ortiz | PDF | Study_report_p007mk0001_and_related_information_1147.pdf | Placeholder timeline for reporting test | Central | 1192
[5 empty] | 5.3.3.3 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p007mk0001 | 1140 |  |  | 31 days | 2025-10-20 | 2025-10-17 | 2025-11-20 | 2025-11-17 | Completed | Released to archive | 701148 | Archive release | Sam Brooks | A. Shah | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_1148.zip | Sample entry for dashboard validation | Central | 1193
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1141 |  |  | 28 days | 2025-10-17 | 2025-10-22 | 2025-11-14 |  | In Progress | Draft in QC review | 701149 | Authoring | Morgan Lee | M. Sullivan | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_1149.csv | Dummy data added for planning demo | Central | 1194
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1142 |  |  | 30 days | 2025-10-21 |  | 2025-11-20 |  | Not Started | Scheduled after current milestone | 701150 |  | Morgan Lee | L. Bennett | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_1150.csv | Sample entry for dashboard validation | Central | 1195
[5 empty] | 5.3.3.3 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1143 |  |  | 31 days | 2025-10-22 | 2025-10-28 | 2025-11-22 |  | In Progress | Regional review underway | 701151 | QC review | Jordan Patel | M. Sullivan | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_1151.pdf | Dummy data added for planning demo | Central | 1196
[5 empty] | 5.3.3.3 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p007mk0001 | 1144 |  |  | 20 days | 2025-10-23 | 2025-10-28 | 2025-11-12 |  | In Progress | Metadata check in progress | 701152 | Regional alignment | Casey Rivera | L. Bennett | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p007mk0001_1152.csv | Timing estimate is illustrative | Central | 1197
[5 empty] | 5.3.3.3 |  | Analysis datasets - ADAM format | 1145 |  |  | 30 days | 2025-10-21 | 2025-10-25 | 2025-11-20 |  | In Progress | Draft in QC review | 701153 | QC review | Jamie Carter | R. Gupta | CSV | Analysis_datasets_ADAM_format_1153.csv | Timing estimate is illustrative | Central | 1198
[5 empty] | 5.3.3.3 |  | Data definition for analysis datasets - ADAM format (define file) | 1146 |  |  | 18 days | 2025-10-25 | 2025-10-24 | 2025-11-12 | 2025-11-10 | Completed |  | 701154 | Submission build | Jordan Patel | A. Shah | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1154.xlsx | Sample entry for dashboard validation | Central | 1199
[5 empty] | 5.3.3.3 |  | Analysis Data Reviewers Guide | 1147 |  |  | 11 days | 2025-10-27 | 2025-10-28 | 2025-11-07 |  | In Progress | Draft in QC review | 701155 | Regional alignment | Casey Rivera | N. Ortiz | CSV | Analysis_Data_Reviewers_Guide_1155.csv | Placeholder timeline for reporting test | Central | 1200
[5 empty] | 5.3.3.3 |  | Analysis programs | 1148 |  |  | 13 days | 2025-10-24 | 2025-10-29 | 2025-11-06 |  | In Progress | Publishing build in progress | 701156 | Regional alignment | Jamie Carter | N. Ortiz | TXT | Analysis_programs_1156.txt | Dummy data added for planning demo | Central | 1201
[5 empty] | 5.3.3.3 |  | 5.3.3.3 p011mk0001 | 1149 |  |  | 10 days | 2025-10-26 | 2025-10-28 | 2025-11-05 | 2025-11-12 | Completed | Released to archive | 701157 |  | Morgan Lee | N. Ortiz | PDF | p011mk0001_1157.pdf | Sample entry for dashboard validation | Central | 1202
[5 empty] | 5.3.3.3 |  | Study report [p011mk0001] and related information | 1150 |  |  | 20 days | 2025-10-25 | 2025-10-27 | 2025-11-14 |  | In Progress | Regional review underway | 701158 | QC review | Morgan Lee | R. Gupta | DOCX | Study_report_p011mk0001_and_related_information_1158.docx | Dummy data added for planning demo | Central | 1203
[5 empty] | 5.3.3.3 |  | Case Report Forms - CRF FOLDER p011mk0001 | 1151 |  |  | 23 days | 2025-10-25 | 2025-10-28 | 2025-11-17 |  | In Progress | Regional review underway | 701159 | QC review | Morgan Lee | M. Sullivan | DOCX | Case_Report_Forms_CRF_FOLDER_p011mk0001_1159.docx | Dummy data added for planning demo | Central | 1204
[5 empty] | 5.3.3.3 |  | Listing of Case Report Forms (CRFs TOC) | 1152 |  |  | 21 days | 2025-10-23 | 2025-10-24 | 2025-11-13 |  | In Progress | Awaiting final source document | 701160 | Publishing prep | Sam Brooks | N. Ortiz | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_1160.csv | Sample entry for dashboard validation | Central | 1205
[5 empty] | 5.3.3.3 |  | Case Report Forms - eCRFs (by site) for US | 1153 |  |  | 24 days | 2025-10-28 | 2025-10-31 | 2025-11-21 |  | In Progress | Regional review underway | 701161 | QC review | Jordan Patel | R. Gupta | PDF | Case_Report_Forms_eCRFs_by_site_for_US_1161.pdf | Timing estimate is illustrative | Central | 1206
[5 empty] | 5.3.3.3 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p011mk0001 | 1154 |  |  | 22 days | 2025-10-27 | 2025-10-25 | 2025-11-18 |  | In Progress | Metadata check in progress | 701162 |  | Alex Kim | L. Bennett | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_1162.xlsx | Placeholder timeline for reporting test | Central | 1207
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1155 |  |  | 23 days | 2025-10-26 | 2025-10-28 | 2025-11-18 |  | In Progress | Draft in QC review | 701163 | Regional alignment | Casey Rivera | N. Ortiz | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_1163.csv | Timing estimate is illustrative | Central | 1208
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1156 |  |  | 34 days | 2025-10-31 | 2025-11-05 | 2025-12-04 |  | In Progress | Awaiting final source document | 701164 | QC review | Sam Brooks | A. Shah | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_1164.csv | Placeholder timeline for reporting test | Central | 1209
[5 empty] | 5.3.3.3 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1157 |  |  | 24 days | 2025-11-02 | 2025-11-03 | 2025-11-26 | 2025-11-27 | Completed | Released to archive | 701165 | Archive release | Taylor Chen | M. Sullivan | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_1165.pdf | Timing estimate is illustrative | Central | 1210
[5 empty] | 5.3.3.3 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p011mk0001 | 1158 |  |  | 16 days | 2025-10-28 | 2025-10-29 | 2025-11-13 |  | In Progress | Pending cross-functional signoff | 701166 |  | Morgan Lee | N. Ortiz | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p011mk0001_1166.csv | Sample entry for dashboard validation | Central | 1211
[5 empty] | 5.3.3.3 |  | Analysis datasets - ADAM format | 1159 |  |  | 16 days | 2025-10-27 | 2025-10-27 | 2025-11-12 |  | In Progress | Metadata check in progress | 701167 | Authoring | Alex Kim | L. Bennett | XLSX | Analysis_datasets_ADAM_format_1167.xlsx | Placeholder timeline for reporting test | Central | 1212
[5 empty] | 5.3.3.3 |  | Data definition for analysis datasets - ADAM format (define file) | 1160 |  |  | 31 days | 2025-11-04 |  | 2025-12-05 |  | Not Started | Pending authoring start | 701168 |  | Casey Rivera | L. Bennett | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1168.zip | Timing estimate is illustrative | Central | 1213
[5 empty] | 5.3.3.3 |  | Analysis Data Reviewers Guide | 1161 |  |  | 31 days | 2025-11-05 | 2025-11-07 | 2025-12-06 |  | In Progress | Publishing build in progress | 701169 | Publishing prep | Jordan Patel | M. Sullivan | CSV | Analysis_Data_Reviewers_Guide_1169.csv | Placeholder timeline for reporting test | Central | 1214
[5 empty] | 5.3.3.3 |  | Analysis programs | 1162 |  |  | 25 days | 2025-10-31 | 2025-10-28 | 2025-11-25 | 2025-11-22 | Completed | Completed as planned | 701170 | Archive release | Taylor Chen | L. Bennett | TXT | Analysis_programs_1170.txt | Timing estimate is illustrative | Central | 1215
[5 empty] | 5.3.3.3 |  | 5.3.3.3 p020mk0001 | 1163 |  |  | 33 days | 2025-11-04 | 2025-11-10 | 2025-12-07 |  | In Progress | Draft in QC review | 701171 | Regional alignment | Sam Brooks | R. Gupta | DOCX | p020mk0001_1171.docx | Timing estimate is illustrative | Central | 1216
[5 empty] | 5.3.3.3 |  | Study report [p020mk0001] and related information | 1164 |  |  | 26 days | 2025-11-04 |  | 2025-11-30 |  | Not Started | Planned for upcoming wave | 701172 |  | Sam Brooks | R. Gupta | DOCX | Study_report_p020mk0001_and_related_information_1172.docx | Dummy data added for planning demo | Central | 1217
[5 empty] | 5.3.3.3 |  | Case Report Forms - CRF FOLDER p020mk0001 | 1165 |  |  | 8 days | 2025-11-08 | 2025-11-08 | 2025-11-16 |  | In Progress | Publishing build in progress | 701173 | Authoring | Alex Kim | N. Ortiz | PDF | Case_Report_Forms_CRF_FOLDER_p020mk0001_1173.pdf | Dummy data added for planning demo | Central | 1218
[5 empty] | 5.3.3.3 |  | Listing of Case Report Forms (CRFs TOC) | 1166 |  |  | 12 days | 2025-11-09 |  | 2025-11-21 |  | Not Started | Pending authoring start | 701174 |  | Alex Kim | R. Gupta | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_1174.csv | Placeholder timeline for reporting test | Central | 1219
[5 empty] | 5.3.3.3 |  | Case Report Forms - eCRFs (by site) for US | 1167 |  |  | 20 days | 2025-11-02 | 2025-11-01 | 2025-11-22 |  | In Progress | Publishing build in progress | 701175 | Regional alignment | Taylor Chen | A. Shah | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1175.docx | Sample entry for dashboard validation | Central | 1220
[5 empty] | 5.3.3.3 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p020mk0001 | 1168 |  |  | 24 days | 2025-11-04 |  | 2025-11-28 |  | Not Started | Pending authoring start | 701176 |  | Casey Rivera | N. Ortiz | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_1176.xlsx | Placeholder timeline for reporting test | Central | 1221
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1169 |  |  | 14 days | 2025-11-05 | 2025-11-10 | 2025-11-19 | 2025-11-15 | Completed | Completed as planned | 701177 | Submission build | Casey Rivera | A. Shah | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_1177.xlsx | Timing estimate is illustrative | Central | 1222
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1170 |  |  | 11 days | 2025-11-06 |  | 2025-11-17 |  | Not Started | Pending authoring start | 701178 |  | Taylor Chen | R. Gupta | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_1178.csv | Sample entry for dashboard validation | Central | 1223
[5 empty] | 5.3.3.3 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1171 |  |  | 7 days | 2025-11-10 | 2025-11-12 | 2025-11-17 |  | In Progress | Publishing build in progress | 701179 | Authoring | Sam Brooks | L. Bennett | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_1179.pdf | Dummy data added for planning demo | Central | 1224
[5 empty] | 5.3.3.3 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p020mk0001 | 1172 |  |  | 25 days | 2025-11-07 | 2025-11-07 | 2025-12-02 | 2025-12-07 | Completed | Released to archive | 701180 | Publishing QC | Morgan Lee | A. Shah | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p020mk0001_1180.zip | Placeholder timeline for reporting test | Central | 1225
[5 empty] | 5.3.3.3 |  | Analysis datasets - ADAM format | 1173 |  |  | 35 days | 2025-11-13 |  | 2025-12-18 |  | Not Started | Scheduled after current milestone | 701181 |  | Jordan Patel | N. Ortiz | ZIP | Analysis_datasets_ADAM_format_1181.zip | Dummy data added for planning demo | Central | 1226
[5 empty] | 5.3.3.3 |  | Data definition for analysis datasets - ADAM format (define file) | 1174 |  |  | 15 days | 2025-11-09 | 2025-11-15 | 2025-11-24 |  | In Progress | Publishing build in progress | 701182 | QC review | Jamie Carter | N. Ortiz | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1182.zip | Placeholder timeline for reporting test | Central | 1227
[5 empty] | 5.3.3.3 |  | Analysis Data Reviewers Guide | 1175 |  |  | 13 days | 2025-11-11 | 2025-11-13 | 2025-11-24 |  | In Progress | Publishing build in progress | 701183 | Authoring | Sam Brooks | R. Gupta | CSV | Analysis_Data_Reviewers_Guide_1183.csv | Dummy data added for planning demo | Central | 1228
[5 empty] | 5.3.3.3 |  | Analysis programs | 1176 |  |  | 26 days | 2025-11-14 |  | 2025-12-10 |  | Not Started | On hold pending document availability | 701184 |  | Taylor Chen | L. Bennett | ZIP | Analysis_programs_1184.zip | Timing estimate is illustrative | Central | 1229
[5 empty] | 5.3.3.3 |  | 5.3.3.3 p030mk0001 | 1177 |  |  | 8 days | 2025-11-08 | 2025-11-07 | 2025-11-16 |  | In Progress | Regional review underway | 701185 | QC review | Jordan Patel | M. Sullivan | XLSX | p030mk0001_1185.xlsx | Placeholder timeline for reporting test | Central | 1230
[5 empty] | 5.3.3.3 |  | Study report [p030mk0001] and related information | 1178 |  |  | 35 days | 2025-11-11 | 2025-11-13 | 2025-12-16 |  | In Progress | Metadata check in progress | 701186 | Regional alignment | Alex Kim | N. Ortiz | DOCX | Study_report_p030mk0001_and_related_information_1186.docx | Timing estimate is illustrative | Central | 1231
[5 empty] | 5.3.3.3 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p030mk0001 | 1179 |  |  | 7 days | 2025-11-16 | 2025-11-17 | 2025-11-23 |  | In Progress | Awaiting final source document | 701187 | Publishing prep | Jordan Patel | L. Bennett | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p03_1187.zip | Sample entry for dashboard validation | Central | 1232
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1180 |  |  | 21 days | 2025-11-14 |  | 2025-12-05 |  | Not Started | Resource assignment not yet confirmed | 701188 |  | Jamie Carter | N. Ortiz | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_1188.csv | Sample entry for dashboard validation | Central | 1233
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1181 |  |  | 26 days | 2025-11-18 | 2025-11-19 | 2025-12-14 |  | In Progress | Draft in QC review | 701189 |  | Alex Kim | A. Shah | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_1189.xlsx | Dummy data added for planning demo | Central | 1234
[5 empty] | 5.3.3.3 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1182 |  |  | 15 days | 2025-11-10 |  | 2025-11-25 |  | Not Started | Waiting on dependency from Module 3 | 701190 |  | Casey Rivera | L. Bennett | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_1190.pdf | Dummy data added for planning demo | Central | 1235
[5 empty] | 5.3.3.3 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p030mk0001 | 1183 |  |  | 18 days | 2025-11-11 | 2025-11-11 | 2025-11-29 | 2025-12-01 | Completed | QC completed | 701191 | Publishing QC | Morgan Lee | L. Bennett | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p030mk0001_1191.zip | Dummy data added for planning demo | Central | 1236
[5 empty] | 5.3.3.3 |  | Analysis datasets - ADAM format | 1184 |  |  | 31 days | 2025-11-16 | 2025-11-14 | 2025-12-17 | 2025-12-17 | Completed | Filed in baseline wave | 701192 | Archive release | Casey Rivera | N. Ortiz | XLSX | Analysis_datasets_ADAM_format_1192.xlsx | Dummy data added for planning demo | Central | 1237
[5 empty] | 5.3.3.3 |  | Data definition for analysis datasets - ADAM format (define file) | 1185 |  |  | 12 days | 2025-11-19 | 2025-11-17 | 2025-12-01 | 2025-12-08 | Completed | Filed in baseline wave | 701193 |  | Jamie Carter | M. Sullivan | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1193.zip | Placeholder timeline for reporting test | Central | 1238
[5 empty] | 5.3.3.3 |  | Analysis Data Reviewers Guide | 1186 |  |  | 7 days | 2025-11-17 | 2025-11-22 | 2025-11-24 |  | In Progress | Draft in QC review | 701194 | QC review | Jordan Patel | A. Shah | CSV | Analysis_Data_Reviewers_Guide_1194.csv | Sample entry for dashboard validation | Central | 1239
[5 empty] | 5.3.3.3 |  | Analysis programs | 1187 |  |  | 8 days | 2025-11-13 | 2025-11-18 | 2025-11-21 |  | In Progress | Publishing build in progress | 701195 | QC review | Alex Kim | M. Sullivan | ZIP | Analysis_programs_1195.zip | Dummy data added for planning demo | Central | 1240
[5 empty] | 5.3.3.3 |  | 5.3.3.3 p032mk0001 | 1188 |  |  | 29 days | 2025-11-18 | 2025-11-23 | 2025-12-17 |  | In Progress | Awaiting final source document | 701196 | Publishing prep | Alex Kim | R. Gupta | PDF | p032mk0001_1196.pdf | Timing estimate is illustrative | Central | 1241
[5 empty] | 5.3.3.3 |  | Study report [p032mk0001] and related information | 1189 |  |  | 32 days | 2025-11-22 | 2025-11-19 | 2025-12-24 | 2025-12-29 | Completed | Released to archive | 701197 |  | Sam Brooks | L. Bennett | PDF | Study_report_p032mk0001_and_related_information_1197.pdf | Dummy data added for planning demo | Central | 1242
[5 empty] | 5.3.3.3 |  | Case Report Forms - CRF FOLDER p032mk0001 | 1190 |  |  | 18 days | 2025-11-19 | 2025-11-21 | 2025-12-07 | 2025-12-10 | Completed | Released to archive | 701198 |  | Jordan Patel | R. Gupta | DOCX | Case_Report_Forms_CRF_FOLDER_p032mk0001_1198.docx | Timing estimate is illustrative | Central | 1243
[5 empty] | 5.3.3.3 |  | Listing of Case Report Forms (CRFs TOC) | 1191 |  |  | 30 days | 2025-11-21 | 2025-11-25 | 2025-12-21 |  | In Progress | Awaiting final source document | 701199 |  | Casey Rivera | R. Gupta | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_1199.csv | Placeholder timeline for reporting test | Central | 1244
[5 empty] | 5.3.3.3 |  | Case Report Forms - eCRFs (by site) for US | 1192 |  |  | 11 days | 2025-11-20 |  | 2025-12-01 |  | Not Started | Scheduled after current milestone | 701200 |  | Sam Brooks | M. Sullivan | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1200.docx | Placeholder timeline for reporting test | Central | 1245
[5 empty] | 5.3.3.3 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p032mk0001 | 1193 |  |  | 9 days | 2025-11-23 | 2025-11-23 | 2025-12-02 |  | In Progress | Metadata check in progress | 701201 | Publishing prep | Sam Brooks | L. Bennett | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p03_1201.csv | Timing estimate is illustrative | Central | 1246
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1194 |  |  | 17 days | 2025-11-18 | 2025-11-18 | 2025-12-05 |  | In Progress | Pending cross-functional signoff | 701202 | Publishing prep | Taylor Chen | N. Ortiz | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_1202.zip | Timing estimate is illustrative | Central | 1247
[5 empty] | 5.3.3.3 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1195 |  |  | 33 days | 2025-11-21 | 2025-11-20 | 2025-12-24 |  | In Progress | Publishing build in progress | 701203 | Authoring | Taylor Chen | M. Sullivan | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_1203.xlsx | Dummy data added for planning demo | Central | 1248
[5 empty] | 5.3.3.3 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1196 |  |  | 15 days | 2025-11-19 |  | 2025-12-04 |  | Not Started | On hold pending document availability | 701204 |  | Jordan Patel | N. Ortiz | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_1204.docx | Sample entry for dashboard validation | Central | 1249
[5 empty] | 5.3.3.3 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p032mk0001 | 1197 |  |  | 17 days | 2025-11-20 | 2025-11-23 | 2025-12-07 |  | In Progress | Pending cross-functional signoff | 701205 | Regional alignment | Taylor Chen | L. Bennett | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p032mk0001_1205.xlsx | Placeholder timeline for reporting test | Central | 1250
[5 empty] | 5.3.3.3 |  | Analysis datasets - ADAM format | 1198 |  |  | 29 days | 2025-11-26 | 2025-11-25 | 2025-12-25 |  | In Progress | Awaiting final source document | 701206 | Regional alignment | Jordan Patel | N. Ortiz | ZIP | Analysis_datasets_ADAM_format_1206.zip | Dummy data added for planning demo | Central | 1251
[5 empty] | 5.3.3.3 |  | Data definition for analysis datasets - ADAM format (define file) | 1199 |  |  | 32 days | 2025-11-29 | 2025-11-28 | 2025-12-31 | 2025-12-28 | Completed | QC completed | 701207 | Submission build | Jamie Carter | L. Bennett | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1207.csv | Timing estimate is illustrative | Central | 1252
[5 empty] | 5.3.3.3 |  | Analysis Data Reviewers Guide | 1200 |  |  | 27 days | 2025-11-29 | 2025-11-29 | 2025-12-26 | 2025-12-22 | Completed | Completed as planned | 701208 | Publishing QC | Morgan Lee | A. Shah | XLSX | Analysis_Data_Reviewers_Guide_1208.xlsx | Timing estimate is illustrative | Central | 1253
[5 empty] | 5.3.3.3 |  | Analysis programs | 1201 |  |  | 9 days | 2025-11-23 | 2025-11-22 | 2025-12-02 |  | In Progress | Publishing build in progress | 701209 | Publishing prep | Sam Brooks | L. Bennett | ZIP | Analysis_programs_1209.zip | Placeholder timeline for reporting test | Central | 1254
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p023mk0001 | 1202 |  |  | 19 days | 2025-11-27 | 2025-11-29 | 2025-12-16 |  | In Progress | Publishing build in progress | 701210 |  | Taylor Chen | L. Bennett | XLSX | p023mk0001_1210.xlsx | Dummy data added for planning demo | Central | 1255
[5 empty] | 5.3.3.4 |  | Study report [p023mk0001] and related information | 1203 |  |  | 8 days | 2025-11-30 | 2025-12-03 | 2025-12-08 |  | In Progress | Draft in QC review | 701211 | Publishing prep | Sam Brooks | L. Bennett | DOCX | Study_report_p023mk0001_and_related_information_1211.docx | Dummy data added for planning demo | Central | 1256
[5 empty] | 5.3.3.4 |  | Case Report Forms - CRF FOLDER p023mk0001 | 1204 |  |  | 29 days | 2025-11-30 | 2025-12-03 | 2025-12-29 |  | In Progress | Regional review underway | 701212 | Regional alignment | Alex Kim | L. Bennett | PDF | Case_Report_Forms_CRF_FOLDER_p023mk0001_1212.pdf | Sample entry for dashboard validation | Central | 1257
[5 empty] | 5.3.3.4 |  | Listing of Case Report Forms (CRFs TOC) | 1205 |  |  | 22 days | 2025-11-25 | 2025-11-24 | 2025-12-17 |  | In Progress | Draft in QC review | 701213 | QC review | Sam Brooks | A. Shah | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_1213.csv | Sample entry for dashboard validation | Central | 1258
[5 empty] | 5.3.3.4 |  | Case Report Forms - eCRFs (by site) for US | 1206 |  |  | 14 days | 2025-11-30 | 2025-12-05 | 2025-12-14 |  | In Progress | Draft in QC review | 701214 | Publishing prep | Morgan Lee | M. Sullivan | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1214.docx | Timing estimate is illustrative | Central | 1259
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p023mk0001 | 1207 |  |  | 10 days | 2025-12-01 | 2025-11-30 | 2025-12-11 | 2025-12-16 | Completed | Completed as planned | 701215 |  | Casey Rivera | A. Shah | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_1215.zip | Timing estimate is illustrative | Central | 1260
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1208 |  |  | 15 days | 2025-12-03 | 2025-12-07 | 2025-12-18 |  | In Progress | Pending cross-functional signoff | 701216 | Authoring | Morgan Lee | M. Sullivan | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_1216.xlsx | Sample entry for dashboard validation | Central | 1261
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1209 |  |  | 35 days | 2025-11-29 | 2025-11-29 | 2026-01-03 |  | In Progress | Draft in QC review | 701217 | Publishing prep | Taylor Chen | R. Gupta | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_1217.csv | Dummy data added for planning demo | Central | 1262
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1210 |  |  | 33 days | 2025-11-29 | 2025-12-03 | 2026-01-01 | 2026-01-04 | Completed | Filed in baseline wave | 701218 | Publishing QC | Casey Rivera | N. Ortiz | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_1218.docx | Dummy data added for planning demo | Central | 1263
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p023mk0001 | 1211 |  |  | 12 days | 2025-12-02 | 2025-12-06 | 2025-12-14 | 2025-12-13 | Completed | Released to archive | 701219 | Publishing QC | Alex Kim | N. Ortiz | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p023mk0001_1219.xlsx | Timing estimate is illustrative | Central | 1264
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 1212 |  |  | 21 days | 2025-11-28 | 2025-12-02 | 2025-12-19 |  | In Progress | Draft in QC review | 701220 |  | Sam Brooks | R. Gupta | ZIP | Analysis_datasets_ADAM_format_1220.zip | Dummy data added for planning demo | Central | 1265
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 1213 |  |  | 22 days | 2025-12-05 | 2025-12-08 | 2025-12-27 | 2025-12-31 | Completed | Released to archive | 701221 | Publishing QC | Alex Kim | A. Shah | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1221.csv | Placeholder timeline for reporting test | Central | 1266
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 1214 |  |  | 19 days | 2025-12-07 | 2025-12-08 | 2025-12-26 |  | In Progress | Awaiting final source document | 701222 | Authoring | Alex Kim | N. Ortiz | XLSX | Analysis_Data_Reviewers_Guide_1222.xlsx | Timing estimate is illustrative | Central | 1267
[5 empty] | 5.3.3.4 |  | Analysis programs | 1215 |  |  | 21 days | 2025-12-03 | 2025-12-09 | 2025-12-24 |  | In Progress | Metadata check in progress | 701223 |  | Morgan Lee | L. Bennett | ZIP | Analysis_programs_1223.zip | Timing estimate is illustrative | Central | 1268
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p024mk0001 | 1216 |  |  | 10 days | 2025-12-07 | 2025-12-08 | 2025-12-17 |  | In Progress | Awaiting final source document | 701224 | QC review | Morgan Lee | N. Ortiz | XLSX | p024mk0001_1224.xlsx | Sample entry for dashboard validation | Central | 1269
[5 empty] | 5.3.3.4 |  | Study report [p024mk0001 ] and related information | 1217 |  |  | 18 days | 2025-12-02 | 2025-11-29 | 2025-12-20 | 2025-12-17 | Completed |  | 701225 | Archive release | Taylor Chen | M. Sullivan | PDF | Study_report_p024mk0001_and_related_information_1225.pdf | Placeholder timeline for reporting test | Central | 1270
[5 empty] | 5.3.3.4 |  | Case Report Forms - CRF FOLDER p024mk0001 | 1218 |  |  | 17 days | 2025-12-04 |  | 2025-12-21 |  | Not Started | Scheduled after current milestone | 701226 |  | Jamie Carter | N. Ortiz | PDF | Case_Report_Forms_CRF_FOLDER_p024mk0001_1226.pdf | Sample entry for dashboard validation | Central | 1271
[5 empty] | 5.3.3.4 |  | Listing of Case Report Forms (CRFs TOC) | 1219 |  |  | 22 days | 2025-12-10 | 2025-12-09 | 2026-01-01 | 2026-01-03 | Completed |  | 701227 |  | Jamie Carter | A. Shah | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_1227.xlsx | Timing estimate is illustrative | Central | 1272
[5 empty] | 5.3.3.4 |  | Case Report Forms - eCRFs (by site) for US | 1220 |  |  | 11 days | 2025-12-11 |  | 2025-12-22 |  | Not Started | Planned for upcoming wave | 701228 |  | Casey Rivera | M. Sullivan | PDF | Case_Report_Forms_eCRFs_by_site_for_US_1228.pdf | Timing estimate is illustrative | Central | 1273
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p024mk0001 | 1221 |  |  | 27 days | 2025-12-07 | 2025-12-10 | 2026-01-03 |  | In Progress | Awaiting final source document | 701229 | Publishing prep | Casey Rivera | A. Shah | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_1229.csv | Dummy data added for planning demo | Central | 1274
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1222 |  |  | 31 days | 2025-12-10 | 2025-12-11 | 2026-01-10 |  | In Progress | Regional review underway | 701230 | Publishing prep | Casey Rivera | L. Bennett | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_1230.zip | Timing estimate is illustrative | Central | 1275
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1223 |  |  | 22 days | 2025-12-07 | 2025-12-13 | 2025-12-29 |  | In Progress | Publishing build in progress | 701231 | QC review | Jordan Patel | M. Sullivan | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_1231.zip | Placeholder timeline for reporting test | Central | 1276
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1224 |  |  | 31 days | 2025-12-13 | 2025-12-10 | 2026-01-13 | 2026-01-15 | Completed | Completed as planned | 701232 |  | Alex Kim | N. Ortiz | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_1232.pdf | Placeholder timeline for reporting test | Central | 1277
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p024mk0001 | 1225 |  |  | 19 days | 2025-12-10 | 2025-12-13 | 2025-12-29 |  | In Progress | Metadata check in progress | 701233 |  | Taylor Chen | R. Gupta | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p024mk0001_1233.csv | Sample entry for dashboard validation | Central | 1278
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 1226 |  |  | 22 days | 2025-12-15 | 2025-12-21 | 2026-01-06 |  | In Progress | Regional review underway | 701234 |  | Taylor Chen | M. Sullivan | XLSX | Analysis_datasets_ADAM_format_1234.xlsx | Sample entry for dashboard validation | Central | 1279
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 1227 |  |  | 9 days | 2025-12-13 | 2025-12-16 | 2025-12-22 |  | In Progress | Pending cross-functional signoff | 701235 |  | Taylor Chen | A. Shah | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1235.csv | Placeholder timeline for reporting test | Central | 1280
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 1228 |  |  | 34 days | 2025-12-12 | 2025-12-18 | 2026-01-15 |  | In Progress | Awaiting final source document | 701236 | Publishing prep | Morgan Lee | N. Ortiz | ZIP | Analysis_Data_Reviewers_Guide_1236.zip | Timing estimate is illustrative | Central | 1281
[5 empty] | 5.3.3.4 |  | Analysis programs | 1229 |  |  | 16 days | 2025-12-14 | 2025-12-16 | 2025-12-30 | 2026-01-03 | Completed | Released to archive | 701237 | Archive release | Morgan Lee | M. Sullivan | TXT | Analysis_programs_1237.txt | Timing estimate is illustrative | Central | 1282
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p026mk0001 | 1230 |  |  | 32 days | 2025-12-11 | 2025-12-13 | 2026-01-12 |  | In Progress | Awaiting final source document | 701238 | Publishing prep | Sam Brooks | M. Sullivan | XLSX | p026mk0001_1238.xlsx | Placeholder timeline for reporting test | Central | 1283
[5 empty] | 5.3.3.4 |  | Study report [p026mk0001] and related information | 1231 |  |  | 32 days | 2025-12-13 | 2025-12-19 | 2026-01-14 |  | In Progress | Awaiting final source document | 701239 | Authoring | Sam Brooks | R. Gupta | PDF | Study_report_p026mk0001_and_related_information_1239.pdf | Timing estimate is illustrative | Central | 1284
[5 empty] | 5.3.3.4 |  | Case Report Forms - CRF FOLDER p026mk0001 | 1232 |  |  | 12 days | 2025-12-16 |  | 2025-12-28 |  | Not Started | Scheduled after current milestone | 701240 |  | Morgan Lee | N. Ortiz | DOCX | Case_Report_Forms_CRF_FOLDER_p026mk0001_1240.docx | Sample entry for dashboard validation | Central | 1285
[5 empty] | 5.3.3.4 |  | Listing of Case Report Forms (CRFs TOC) | 1233 |  |  | 25 days | 2025-12-15 | 2025-12-18 | 2026-01-09 |  | In Progress | Awaiting final source document | 701241 | Publishing prep | Taylor Chen | A. Shah | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_1241.csv | Dummy data added for planning demo | Central | 1286
[5 empty] | 5.3.3.4 |  | Case Report Forms - eCRFs (by site) for US | 1234 |  |  | 33 days | 2025-12-18 | 2025-12-22 | 2026-01-20 |  | In Progress | Draft in QC review | 701242 | Authoring | Jordan Patel | R. Gupta | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1242.docx | Sample entry for dashboard validation | Central | 1287
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p026mk0001 | 1235 |  |  | 25 days | 2025-12-20 |  | 2026-01-14 |  | Not Started | Resource assignment not yet confirmed | 701243 |  | Taylor Chen | L. Bennett | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_1243.xlsx | Placeholder timeline for reporting test | Central | 1288
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1236 |  |  | 20 days | 2025-12-13 | 2025-12-18 | 2026-01-02 |  | In Progress | Pending cross-functional signoff | 701244 | Authoring | Casey Rivera | L. Bennett | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_1244.csv | Placeholder timeline for reporting test | Central | 1289
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1237 |  |  | 11 days | 2025-12-15 | 2025-12-17 | 2025-12-26 | 2025-12-22 | Completed | Completed as planned | 701245 | Publishing QC | Morgan Lee | A. Shah | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_1245.zip | Placeholder timeline for reporting test | Central | 1290
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1238 |  |  | 32 days | 2025-12-16 | 2025-12-19 | 2026-01-17 | 2026-01-16 | Completed | Completed as planned | 701246 |  | Alex Kim | A. Shah | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_1246.pdf | Placeholder timeline for reporting test | Central | 1291
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p026mk0001 | 1239 |  |  | 16 days | 2025-12-19 | 2025-12-20 | 2026-01-04 |  | In Progress | Awaiting final source document | 701247 |  | Taylor Chen | M. Sullivan | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p026mk0001_1247.csv | Placeholder timeline for reporting test | Central | 1292
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 1240 |  |  | 11 days | 2025-12-18 | 2025-12-20 | 2025-12-29 | 2025-12-28 | Completed | Filed in baseline wave | 701248 |  | Jordan Patel | M. Sullivan | ZIP | Analysis_datasets_ADAM_format_1248.zip | Dummy data added for planning demo | Central | 1293
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 1241 |  |  | 9 days | 2025-12-18 | 2025-12-20 | 2025-12-27 |  | In Progress | Publishing build in progress | 701249 | Authoring | Alex Kim | N. Ortiz | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1249.csv | Timing estimate is illustrative | Central | 1294
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 1242 |  |  | 21 days | 2025-12-20 | 2025-12-20 | 2026-01-10 |  | In Progress | Awaiting final source document | 701250 | Publishing prep | Alex Kim | A. Shah | XLSX | Analysis_Data_Reviewers_Guide_1250.xlsx | Placeholder timeline for reporting test | Central | 1295
[5 empty] | 5.3.3.4 |  | Analysis programs | 1243 |  |  | 25 days | 2025-12-23 |  | 2026-01-17 |  | Not Started | Scheduled after current milestone | 701251 |  | Casey Rivera | N. Ortiz | ZIP | Analysis_programs_1251.zip | Dummy data added for planning demo | Central | 1296
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p027mk0001 | 1244 |  |  | 20 days | 2025-12-19 | 2025-12-24 | 2026-01-08 |  | In Progress | Awaiting final source document | 701252 | Regional alignment | Jamie Carter | M. Sullivan | DOCX | p027mk0001_1252.docx | Dummy data added for planning demo | Central | 1297
[5 empty] | 5.3.3.4 |  | Study report [p027mk0001] and related information | 1245 |  |  | 31 days | 2025-12-27 | 2026-01-01 | 2026-01-27 |  | In Progress | Publishing build in progress | 701253 |  | Morgan Lee | R. Gupta | PDF | Study_report_p027mk0001_and_related_information_1253.pdf | Sample entry for dashboard validation | Central | 1298
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p027mk0001 | 1246 |  |  | 26 days | 2025-12-27 | 2026-01-01 | 2026-01-22 |  | In Progress | Pending cross-functional signoff | 701254 | QC review | Morgan Lee | N. Ortiz | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_1254.zip | Dummy data added for planning demo | Central | 1299
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1247 |  |  | 12 days | 2025-12-26 | 2025-12-27 | 2026-01-07 |  | In Progress | Awaiting final source document | 701255 | Publishing prep | Morgan Lee | L. Bennett | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_1255.csv | Timing estimate is illustrative | Central | 1300
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1248 |  |  | 35 days | 2025-12-24 | 2025-12-28 | 2026-01-28 | 2026-01-24 | Completed |  | 701256 | Submission build | Sam Brooks | A. Shah | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_1256.csv | Dummy data added for planning demo | Central | 1301
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1249 |  |  | 25 days | 2025-12-27 | 2025-12-31 | 2026-01-21 |  | In Progress | Draft in QC review | 701257 | Regional alignment | Casey Rivera | L. Bennett | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_1257.docx | Dummy data added for planning demo | Central | 1302
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p027mk0001 | 1250 |  |  | 15 days | 2025-12-28 | 2025-12-30 | 2026-01-12 |  | In Progress | Metadata check in progress | 701258 | Publishing prep | Casey Rivera | N. Ortiz | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p027mk0001_1258.xlsx | Timing estimate is illustrative | Central | 1303
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 1251 |  |  | 26 days | 2025-12-30 | 2025-12-31 | 2026-01-25 |  | In Progress | Draft in QC review | 701259 | Regional alignment | Morgan Lee | A. Shah | XLSX | Analysis_datasets_ADAM_format_1259.xlsx | Dummy data added for planning demo | Central | 1304
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 1252 |  |  | 9 days | 2025-12-25 |  | 2026-01-03 |  | Not Started | Resource assignment not yet confirmed | 701260 |  | Alex Kim | R. Gupta | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1260.xlsx | Placeholder timeline for reporting test | Central | 1305
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 1253 |  |  | 11 days | 2025-12-30 | 2026-01-03 | 2026-01-10 |  | In Progress | Metadata check in progress | 701261 | QC review | Jordan Patel | L. Bennett | CSV | Analysis_Data_Reviewers_Guide_1261.csv | Timing estimate is illustrative | Central | 1306
[5 empty] | 5.3.3.4 |  | Analysis programs | 1254 |  |  | 9 days | 2026-01-01 | 2025-12-31 | 2026-01-10 |  | In Progress | Pending cross-functional signoff | 701262 | Authoring | Taylor Chen | N. Ortiz | TXT | Analysis_programs_1262.txt | Sample entry for dashboard validation | Central | 1307
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p028mk0001 | 1255 |  |  | 35 days | 2025-12-31 | 2025-12-29 | 2026-02-04 |  | In Progress | Awaiting final source document | 701263 |  | Sam Brooks | A. Shah | PDF | p028mk0001_1263.pdf | Dummy data added for planning demo | Central | 1308
[5 empty] | 5.3.3.4 |  | Study report [p028mk0001] and related information | 1256 |  |  | 33 days | 2025-12-29 |  | 2026-01-31 |  | Not Started | Resource assignment not yet confirmed | 701264 |  | Alex Kim | L. Bennett | DOCX | Study_report_p028mk0001_and_related_information_1264.docx | Timing estimate is illustrative | Central | 1309
[5 empty] | 5.3.3.4 |  | Case Report Forms - CRF FOLDER p028mk0001 | 1257 |  |  | 24 days | 2025-12-28 |  | 2026-01-21 |  | Not Started | Pending authoring start | 701265 |  | Jamie Carter | A. Shah | DOCX | Case_Report_Forms_CRF_FOLDER_p028mk0001_1265.docx | Timing estimate is illustrative | Central | 1310
[5 empty] | 5.3.3.4 |  | Listing of Case Report Forms (CRFs TOC) | 1258 |  |  | 23 days | 2025-12-30 |  | 2026-01-22 |  | Not Started | Resource assignment not yet confirmed | 701266 |  | Taylor Chen | A. Shah | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_1266.csv | Timing estimate is illustrative | Central | 1311
[5 empty] | 5.3.3.4 |  | Case Report Forms - eCRFs (by site) for US | 1259 |  |  | 8 days | 2025-12-29 | 2025-12-29 | 2026-01-06 |  | In Progress | Awaiting final source document | 701267 |  | Jamie Carter | R. Gupta | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1267.docx | Sample entry for dashboard validation | Central | 1312
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p028mk0001 | 1260 |  |  | 21 days | 2025-12-31 | 2025-12-30 | 2026-01-21 |  | In Progress | Regional review underway | 701268 | QC review | Jordan Patel | M. Sullivan | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p02_1268.xlsx | Dummy data added for planning demo | Central | 1313
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1261 |  |  | 11 days | 2026-01-03 | 2026-01-07 | 2026-01-14 | 2026-01-18 | Completed | Released to archive | 701269 |  | Taylor Chen | M. Sullivan | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_1269.zip | Sample entry for dashboard validation | Central | 1314
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1262 |  |  | 21 days | 2026-01-06 |  | 2026-01-27 |  | Not Started | Resource assignment not yet confirmed | 701270 |  | Morgan Lee | M. Sullivan | ZIP | Individual_patient_data_listings_Data_definitions_for_data_t_1270.zip | Sample entry for dashboard validation | Central | 1315
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1263 |  |  | 23 days | 2026-01-02 |  | 2026-01-25 |  | Not Started | Pending authoring start | 701271 |  | Taylor Chen | L. Bennett | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_1271.pdf | Dummy data added for planning demo | Central | 1316
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p028mk0001 | 1264 |  |  | 9 days | 2026-01-02 |  | 2026-01-11 |  | Not Started | Waiting on dependency from Module 3 | 701272 |  | Jamie Carter | R. Gupta | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p028mk0001_1272.xlsx | Sample entry for dashboard validation | Central | 1317
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 1265 |  |  | 19 days | 2026-01-06 | 2026-01-04 | 2026-01-25 |  | In Progress | Metadata check in progress | 701273 | Regional alignment | Jordan Patel | A. Shah | XLSX | Analysis_datasets_ADAM_format_1273.xlsx | Sample entry for dashboard validation | Central | 1318
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 1266 |  |  | 21 days | 2026-01-02 |  | 2026-01-23 |  | Not Started | On hold pending document availability | 701274 |  | Jordan Patel | R. Gupta | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1274.csv | Timing estimate is illustrative | Central | 1319
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 1267 |  |  | 7 days | 2026-01-03 |  | 2026-01-10 |  | Not Started | Scheduled after current milestone | 701275 |  | Morgan Lee | L. Bennett | CSV | Analysis_Data_Reviewers_Guide_1275.csv | Sample entry for dashboard validation | Central | 1320
[5 empty] | 5.3.3.4 |  | Analysis programs | 1268 |  |  | 18 days | 2026-01-08 |  | 2026-01-26 |  | Not Started | Scheduled after current milestone | 701276 |  | Jordan Patel | L. Bennett | ZIP | Analysis_programs_1276.zip | Timing estimate is illustrative | Central | 1321
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p031mk0001 | 1269 |  |  | 35 days | 2026-01-04 |  | 2026-02-08 |  | Not Started | Planned for upcoming wave | 701277 |  | Morgan Lee | R. Gupta | PDF | p031mk0001_1277.pdf | Placeholder timeline for reporting test | Central | 1322
[5 empty] | 5.3.3.4 |  | Study report [p031mk0001] and related information | 1270 |  |  | 19 days | 2026-01-10 |  | 2026-01-29 |  | Not Started | Scheduled after current milestone | 701278 |  | Alex Kim | M. Sullivan | DOCX | Study_report_p031mk0001_and_related_information_1278.docx | Placeholder timeline for reporting test | Central | 1323
[5 empty] | 5.3.3.4 |  | Case Report Forms - CRF FOLDER p031mk0001 | 1271 |  |  | 24 days | 2026-01-11 | 2026-01-16 | 2026-02-04 |  | In Progress | Draft in QC review | 701279 | Publishing prep | Morgan Lee | N. Ortiz | DOCX | Case_Report_Forms_CRF_FOLDER_p031mk0001_1279.docx | Timing estimate is illustrative | Central | 1324
[5 empty] | 5.3.3.4 |  | Listing of Case Report Forms (CRFs TOC) | 1272 |  |  | 10 days | 2026-01-04 | 2026-01-10 | 2026-01-14 |  | In Progress | Metadata check in progress | 701280 | Authoring | Alex Kim | M. Sullivan | XLSX | Listing_of_Case_Report_Forms_CRFs_TOC_1280.xlsx | Placeholder timeline for reporting test | Central | 1325
[5 empty] | 5.3.3.4 |  | Case Report Forms - eCRFs (by site) for US | 1273 |  |  | 21 days | 2026-01-04 | 2026-01-09 | 2026-01-25 |  | In Progress | Metadata check in progress | 701281 |  | Morgan Lee | R. Gupta | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1281.docx | Dummy data added for planning demo | Central | 1326
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p031mk0001 | 1274 |  |  | 25 days | 2026-01-13 | 2026-01-18 | 2026-02-07 |  | In Progress | Publishing build in progress | 701282 | Regional alignment | Jamie Carter | M. Sullivan | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p03_1282.xlsx | Dummy data added for planning demo | Central | 1327
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1275 |  |  | 33 days | 2026-01-08 | 2026-01-13 | 2026-02-10 |  | In Progress | Regional review underway | 701283 | Publishing prep | Jordan Patel | N. Ortiz | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_1283.xlsx | Dummy data added for planning demo | Central | 1328
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1276 |  |  | 15 days | 2026-01-12 | 2026-01-10 | 2026-01-27 |  | In Progress | Draft in QC review | 701284 | Publishing prep | Alex Kim | N. Ortiz | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_1284.xlsx | Sample entry for dashboard validation | Central | 1329
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1277 |  |  | 20 days | 2026-01-10 |  | 2026-01-30 |  | Not Started | Pending authoring start | 701285 |  | Casey Rivera | M. Sullivan | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_1285.docx | Timing estimate is illustrative | Central | 1330
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p031mk0001 | 1278 |  |  | 9 days | 2026-01-08 | 2026-01-06 | 2026-01-17 |  | In Progress | Metadata check in progress | 701286 | Regional alignment | Jamie Carter | A. Shah | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p031mk0001_1286.xlsx | Sample entry for dashboard validation | Central | 1331
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 1279 |  |  | 28 days | 2026-01-10 | 2026-01-09 | 2026-02-07 |  | In Progress | Regional review underway | 701287 | Regional alignment | Jamie Carter | R. Gupta | ZIP | Analysis_datasets_ADAM_format_1287.zip | Placeholder timeline for reporting test | Central | 1332
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 1280 |  |  | 15 days | 2026-01-16 |  | 2026-01-31 |  | Not Started | Resource assignment not yet confirmed | 701288 |  | Jamie Carter | R. Gupta | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1288.zip | Placeholder timeline for reporting test | Central | 1333
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 1281 |  |  | 11 days | 2026-01-17 |  | 2026-01-28 |  | Not Started | On hold pending document availability | 701289 |  | Taylor Chen | M. Sullivan | ZIP | Analysis_Data_Reviewers_Guide_1289.zip | Placeholder timeline for reporting test | Central | 1334
[5 empty] | 5.3.3.4 |  | Analysis programs | 1282 |  |  | 14 days | 2026-01-13 |  | 2026-01-27 |  | Not Started | Scheduled after current milestone | 701290 |  | Casey Rivera | R. Gupta | TXT | Analysis_programs_1290.txt | Placeholder timeline for reporting test | Central | 1335
[5 empty] | 5.3.3.4 |  | 5.3.3.4 p034mk0001 | 1283 |  |  | 30 days | 2026-01-18 |  | 2026-02-17 |  | Not Started | Planned for upcoming wave | 701291 |  | Taylor Chen | R. Gupta | DOCX | p034mk0001_1291.docx | Dummy data added for planning demo | Central | 1336
[5 empty] | 5.3.3.4 |  | Study report [p034mk0001] and related information | 1284 |  |  | 24 days | 2026-01-13 | 2026-01-14 | 2026-02-06 |  | In Progress | Awaiting final source document | 701292 | Regional alignment | Jordan Patel | A. Shah | DOCX | Study_report_p034mk0001_and_related_information_1292.docx | Sample entry for dashboard validation | Central | 1337
[5 empty] | 5.3.3.4 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p034mk0001 | 1285 |  |  | 20 days | 2026-01-18 |  | 2026-02-07 |  | Not Started | Waiting on dependency from Module 3 | 701293 |  | Alex Kim | N. Ortiz | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p03_1293.xlsx | Sample entry for dashboard validation | Central | 1338
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1286 |  |  | 31 days | 2026-01-13 | 2026-01-11 | 2026-02-13 |  | In Progress | Publishing build in progress | 701294 | Regional alignment | Jamie Carter | L. Bennett | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_1294.xlsx | Sample entry for dashboard validation | Central | 1339
[5 empty] | 5.3.3.4 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1287 |  |  | 7 days | 2026-01-20 | 2026-01-23 | 2026-01-27 |  | In Progress | Draft in QC review | 701295 | Publishing prep | Jordan Patel | L. Bennett | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_1295.csv | Sample entry for dashboard validation | Central | 1340
[5 empty] | 5.3.3.4 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1288 |  |  | 19 days | 2026-01-17 | 2026-01-18 | 2026-02-05 |  | In Progress | Metadata check in progress | 701296 | QC review | Taylor Chen | N. Ortiz | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_1296.docx | Timing estimate is illustrative | Central | 1341
[5 empty] | 5.3.3.4 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p034mk0001 | 1289 |  |  | 25 days | 2026-01-19 | 2026-01-18 | 2026-02-13 |  | In Progress | Draft in QC review | 701297 | Authoring | Alex Kim | A. Shah | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p034mk0001_1297.xlsx | Sample entry for dashboard validation | Central | 1342
[5 empty] | 5.3.3.4 |  | Analysis datasets - ADAM format | 1290 |  |  | 35 days | 2026-01-22 | 2026-01-21 | 2026-02-26 | 2026-02-22 | Completed | Completed as planned | 701298 |  | Jordan Patel | A. Shah | XLSX | Analysis_datasets_ADAM_format_1298.xlsx | Placeholder timeline for reporting test | Central | 1343
[5 empty] | 5.3.3.4 |  | Data definition for analysis datasets - ADAM format (define file) | 1291 |  |  | 28 days | 2026-01-20 |  | 2026-02-17 |  | Not Started | On hold pending document availability | 701299 |  | Morgan Lee | M. Sullivan | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1299.xlsx | Dummy data added for planning demo | Central | 1344
[5 empty] | 5.3.3.4 |  | Analysis Data Reviewers Guide | 1292 |  |  | 35 days | 2026-01-18 | 2026-01-17 | 2026-02-22 |  | In Progress | Draft in QC review | 701300 |  | Alex Kim | A. Shah | ZIP | Analysis_Data_Reviewers_Guide_1300.zip | Dummy data added for planning demo | Central | 1345
[5 empty] | 5.3.3.4 |  | Analysis programs | 1293 |  |  | 32 days | 2026-01-20 | 2026-01-24 | 2026-02-21 |  | In Progress | Publishing build in progress | 701301 | Authoring | Morgan Lee | M. Sullivan | TXT | Analysis_programs_1301.txt | Dummy data added for planning demo | Central | 1346
[5 empty] | 5.3.5 |  | 5.3.5 Reports of efficacy and safety studies [hypercholest] | 1294 |  |  | 28 days | 2026-01-21 | 2026-01-22 | 2026-02-18 | 2026-02-16 | Completed |  | 701302 | Publishing QC | Casey Rivera | M. Sullivan | PDF | Reports_of_efficacy_and_safety_studies_hypercholest_1302.pdf | Placeholder timeline for reporting test | Central | 1347
[5 empty] | 5.3.5.1 |  | 5.3.5.1 p008mk0001 Study reports and related information of controlled clinical studies pertinent to the claimed indication [placebo] | 1295 |  |  | 19 days | 2026-01-18 |  | 2026-02-06 |  | Not Started | On hold pending document availability | 701303 |  | Jordan Patel | L. Bennett | DOCX | p008mk0001_Study_reports_and_related_information_of_controll_1303.docx | Placeholder timeline for reporting test | Central | 1348
[5 empty] | 5.3.5.1 |  | Study report [p008mk0001] and related information | 1296 |  |  | 16 days | 2026-01-26 | 2026-01-30 | 2026-02-11 |  | In Progress | Publishing build in progress | 701304 | QC review | Jamie Carter | R. Gupta | DOCX | Study_report_p008mk0001_and_related_information_1304.docx | Timing estimate is illustrative | Central | 1349
[5 empty] | 5.3.5.1 |  | Clinical Study Report | 1297 |  |  | 21 days | 2026-01-22 | 2026-01-22 | 2026-02-12 |  | In Progress | Draft in QC review | 701305 | Authoring | Alex Kim | M. Sullivan | PDF | Clinical_Study_Report_1305.pdf | Timing estimate is illustrative | Central | 1350
[5 empty] | 5.3.5.1 |  | Case Report Forms - CRF FOLDER p008mk0001 | 1298 |  |  | 21 days | 2026-01-21 | 2026-01-20 | 2026-02-11 |  | In Progress | Metadata check in progress | 701306 | Publishing prep | Sam Brooks | R. Gupta | PDF | Case_Report_Forms_CRF_FOLDER_p008mk0001_1306.pdf | Sample entry for dashboard validation | Central | 1351
[5 empty] | 5.3.5.1 |  | Listing of Case Report Forms (CRFs TOC) | 1299 |  |  | 20 days | 2026-01-26 | 2026-02-01 | 2026-02-15 |  | In Progress | Regional review underway | 701307 |  | Morgan Lee | N. Ortiz | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_1307.csv | Dummy data added for planning demo | Central | 1352
[5 empty] | 5.3.5.1 |  | Case Report Forms - eCRFs (by site) for US | 1300 |  |  | 12 days | 2026-01-26 | 2026-01-29 | 2026-02-07 |  | In Progress | Draft in QC review | 701308 | Authoring | Alex Kim | R. Gupta | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1308.docx | Timing estimate is illustrative | Central | 1353
[5 empty] | 5.3.5.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p008mk0001 | 1301 |  |  | 21 days | 2026-01-28 |  | 2026-02-18 |  | Not Started | Scheduled after current milestone | 701309 |  | Jamie Carter | R. Gupta | CSV | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p00_1309.csv | Timing estimate is illustrative | Central | 1355
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1302 |  |  | 30 days | 2026-01-27 |  | 2026-02-26 |  | Not Started | Scheduled after current milestone | 701310 |  | Sam Brooks | R. Gupta | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_1310.zip | Timing estimate is illustrative | Central | 1356
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1303 |  |  | 34 days | 2026-01-23 |  | 2026-02-26 |  | Not Started | Waiting on dependency from Module 3 | 701311 |  | Casey Rivera | A. Shah | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_1311.csv | Placeholder timeline for reporting test | Central | 1357
[5 empty] | 5.3.5.1 |  | Study Data Reviewers Guide | 1304 |  |  | 8 days | 2026-01-25 |  | 2026-02-02 |  | Not Started | Pending authoring start | 701312 |  | Taylor Chen | M. Sullivan | DOCX | Study_Data_Reviewers_Guide_1312.docx | Placeholder timeline for reporting test | Central | 1358
[5 empty] | 5.3.5.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1305 |  |  | 30 days | 2026-01-27 | 2026-01-25 | 2026-02-26 |  | In Progress | Draft in QC review | 701313 | Publishing prep | Sam Brooks | R. Gupta | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_1313.docx | Placeholder timeline for reporting test | Central | 1359
[5 empty] | 5.3.5.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p008mk0001 | 1306 |  |  | 10 days | 2026-01-25 | 2026-01-31 | 2026-02-04 |  | In Progress | Awaiting final source document | 701314 | QC review | Jordan Patel | R. Gupta | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p008mk0001_1314.zip | Placeholder timeline for reporting test | Central | 1360
[5 empty] | 5.3.5.1 |  | Analysis datasets - ADAM format | 1307 |  |  | 19 days | 2026-02-02 |  | 2026-02-21 |  | Not Started | Resource assignment not yet confirmed | 701315 |  | Taylor Chen | M. Sullivan | XLSX | Analysis_datasets_ADAM_format_1315.xlsx | Sample entry for dashboard validation | Central | 1361
[5 empty] | 5.3.5.1 |  | Data definition for analysis datasets - ADAM format (define file) | 1308 |  |  | 21 days | 2026-01-26 |  | 2026-02-16 |  | Not Started | Resource assignment not yet confirmed | 701316 |  | Taylor Chen | R. Gupta | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1316.zip | Sample entry for dashboard validation | Central | 1362
[5 empty] | 5.3.5.1 |  | Analysis Data Reviewers Guide | 1309 |  |  | 16 days | 2026-01-26 | 2026-01-30 | 2026-02-11 |  | In Progress | Pending cross-functional signoff | 701317 | Authoring | Casey Rivera | L. Bennett | CSV | Analysis_Data_Reviewers_Guide_1317.csv | Timing estimate is illustrative | Central | 1363
[5 empty] | 5.3.5.1 |  | Analysis results Metadata (ARM) | 1310 |  |  | 33 days | 2026-02-01 |  | 2026-03-06 |  | Not Started | Scheduled after current milestone | 701318 |  | Morgan Lee | R. Gupta | XLSX | Analysis_results_Metadata_ARM_1318.xlsx | Dummy data added for planning demo | Central | 1364
[5 empty] | 5.3.5.1 |  | Analysis programs | 1311 |  |  | 28 days | 2026-01-31 |  | 2026-02-28 |  | Not Started | Waiting on dependency from Module 3 | 701319 |  | Casey Rivera | R. Gupta | ZIP | Analysis_programs_1319.zip | Timing estimate is illustrative | Central | 1365
[5 empty] | 5.3.5.1 |  | 5.3.5.1 p013mk0001 Study reports and related information of controlled clinical studies pertinent to the claimed indication [placebo] | 1312 |  |  | 14 days | 2026-01-28 |  | 2026-02-11 |  | Not Started | Scheduled after current milestone | 701320 |  | Jordan Patel | L. Bennett | PDF | p013mk0001_Study_reports_and_related_information_of_controll_1320.pdf | Sample entry for dashboard validation | Central | 1366
[5 empty] | 5.3.5.1 |  | Study report [p013mk0001] and related information | 1313 |  |  | 9 days | 2026-01-29 |  | 2026-02-07 |  | Not Started | Waiting on dependency from Module 3 | 701321 |  | Taylor Chen | M. Sullivan | DOCX | Study_report_p013mk0001_and_related_information_1321.docx | Dummy data added for planning demo | Central | 1367
[5 empty] | 5.3.5.1 |  | P013 SAP | 1314 |  |  | 34 days | 2026-02-06 |  | 2026-03-12 |  | Not Started | On hold pending document availability | 701322 |  | Jamie Carter | R. Gupta | XLSX | P013_SAP_1322.xlsx | Dummy data added for planning demo | Central | 1368
[5 empty] | 5.3.5.1 |  | Clinical Study Report | 1315 |  |  | 25 days | 2026-02-06 | 2026-02-12 | 2026-03-03 |  | In Progress | Metadata check in progress | 701323 | Authoring | Jamie Carter | N. Ortiz | DOCX | Clinical_Study_Report_1323.docx | Placeholder timeline for reporting test | Central | 1369
[5 empty] | 5.3.5.1 |  | Case Report Forms - CRF FOLDER p013mk0001 | 1316 |  |  | 24 days | 2026-02-02 |  | 2026-02-26 |  | Not Started | Planned for upcoming wave | 701324 |  | Sam Brooks | L. Bennett | PDF | Case_Report_Forms_CRF_FOLDER_p013mk0001_1324.pdf | Placeholder timeline for reporting test | Central | 1370
[5 empty] | 5.3.5.1 |  | Listing of Case Report Forms (CRFs TOC) | 1317 |  |  | 22 days | 2026-02-03 | 2026-02-02 | 2026-02-25 | 2026-03-04 | Completed | QC completed | 701325 | Submission build | Sam Brooks | R. Gupta | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_1325.zip | Placeholder timeline for reporting test | Central | 1371
[5 empty] | 5.3.5.1 |  | Case Report Forms - eCRFs (by site) for US | 1318 |  |  | 12 days | 2026-02-07 |  | 2026-02-19 |  | Not Started | Pending authoring start | 701326 |  | Sam Brooks | N. Ortiz | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1326.docx | Dummy data added for planning demo | Central | 1372
[5 empty] | 5.3.5.1 |  | Adjudication Packages (if applicable) | 1319 |  |  | 16 days | 2026-02-05 |  | 2026-02-21 |  | Not Started | On hold pending document availability | 701327 |  | Taylor Chen | A. Shah | PDF | Adjudication_Packages_if_applicable_1327.pdf | Timing estimate is illustrative | Central | 1373
[5 empty] | 5.3.5.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p013mk0001 | 1320 |  |  | 34 days | 2026-02-03 |  | 2026-03-09 |  | Not Started | Pending authoring start | 701328 |  | Alex Kim | R. Gupta | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_1328.xlsx | Dummy data added for planning demo | Central | 1374
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1321 |  |  | 17 days | 2026-02-10 | 2026-02-16 | 2026-02-27 |  | In Progress | Publishing build in progress | 701329 |  | Alex Kim | L. Bennett | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_1329.zip | Placeholder timeline for reporting test | Central | 1375
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1322 |  |  | 18 days | 2026-02-04 |  | 2026-02-22 |  | Not Started | Waiting on dependency from Module 3 | 701330 |  | Jordan Patel | L. Bennett | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_1330.xlsx | Placeholder timeline for reporting test | Central | 1376
[5 empty] | 5.3.5.1 |  | Study Data Reviewers Guide | 1323 |  |  | 26 days | 2026-02-04 |  | 2026-03-02 |  | Not Started | Planned for upcoming wave | 701331 |  | Alex Kim | N. Ortiz | PDF | Study_Data_Reviewers_Guide_1331.pdf | Placeholder timeline for reporting test | Central | 1377
[5 empty] | 5.3.5.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1324 |  |  | 23 days | 2026-02-06 |  | 2026-03-01 |  | Not Started | Resource assignment not yet confirmed | 701332 |  | Jordan Patel | L. Bennett | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_1332.docx | Dummy data added for planning demo | Central | 1378
[5 empty] | 5.3.5.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p013mk0001 | 1325 |  |  | 34 days | 2026-02-10 | 2026-02-14 | 2026-03-16 |  | In Progress | Draft in QC review | 701333 |  | Jamie Carter | L. Bennett | XLSX | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p013mk0001_1333.xlsx | Timing estimate is illustrative | Central | 1379
[5 empty] | 5.3.5.1 |  | Analysis datasets - ADAM format | 1326 |  |  | 26 days | 2026-02-09 |  | 2026-03-07 |  | Not Started | Resource assignment not yet confirmed | 701334 |  | Sam Brooks | A. Shah | ZIP | Analysis_datasets_ADAM_format_1334.zip | Timing estimate is illustrative | Central | 1380
[5 empty] | 5.3.5.1 |  | Data definition for analysis datasets - ADAM format (define file) | 1327 |  |  | 24 days | 2026-02-13 |  | 2026-03-09 |  | Not Started | Scheduled after current milestone | 701335 |  | Morgan Lee | R. Gupta | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1335.xlsx | Dummy data added for planning demo | Central | 1381
[5 empty] | 5.3.5.1 |  | Analysis Data Reviewers Guide | 1328 |  |  | 21 days | 2026-02-07 | 2026-02-10 | 2026-02-28 |  | In Progress | Draft in QC review | 701336 | Publishing prep | Sam Brooks | R. Gupta | CSV | Analysis_Data_Reviewers_Guide_1336.csv | Dummy data added for planning demo | Central | 1382
[5 empty] | 5.3.5.1 |  | Analysis results Metadata (ARM) | 1329 |  |  | 34 days | 2026-02-12 | 2026-02-12 | 2026-03-18 |  | In Progress | Draft in QC review | 701337 |  | Taylor Chen | M. Sullivan | PDF | Analysis_results_Metadata_ARM_1337.pdf | Timing estimate is illustrative | Central | 1383
[5 empty] | 5.3.5.1 |  | Analysis programs | 1330 |  |  | 22 days | 2026-02-15 |  | 2026-03-09 |  | Not Started | Resource assignment not yet confirmed | 701338 |  | Sam Brooks | R. Gupta | ZIP | Analysis_programs_1338.zip | Dummy data added for planning demo | Central | 1384
[5 empty] | 5.3.5.1 |  | 5.3.5.1 p017mk0001 Study reports and related information of controlled clinical studies pertinent to the claimed indication [placebo] | 1331 |  |  | 14 days | 2026-02-14 | 2026-02-18 | 2026-02-28 |  | In Progress | Metadata check in progress | 701339 | Authoring | Jamie Carter | A. Shah | PDF | p017mk0001_Study_reports_and_related_information_of_controll_1339.pdf | Placeholder timeline for reporting test | Central | 1385
[5 empty] | 5.3.5.1 |  | Study report [p017mk0001 ] and related information | 1332 |  |  | 29 days | 2026-02-11 | 2026-02-15 | 2026-03-12 |  | In Progress | Awaiting final source document | 701340 | Publishing prep | Morgan Lee | L. Bennett | PDF | Study_report_p017mk0001_and_related_information_1340.pdf | Placeholder timeline for reporting test | Central | 1386
[5 empty] | 5.3.5.1 |  | P017 SAP | 1333 |  |  | 22 days | 2026-02-11 | 2026-02-13 | 2026-03-05 |  | In Progress | Publishing build in progress | 701341 | Authoring | Alex Kim | R. Gupta | DOCX | P017_SAP_1341.docx | Timing estimate is illustrative | Central | 1387
[5 empty] | 5.3.5.1 |  | Clinical Study Report | 1334 |  |  | 34 days | 2026-02-11 | 2026-02-17 | 2026-03-17 |  | In Progress | Pending cross-functional signoff | 701342 |  | Jamie Carter | A. Shah | DOCX | Clinical_Study_Report_1342.docx | Dummy data added for planning demo | Central | 1388
[5 empty] | 5.3.5.1 |  | Case Report Forms - CRF FOLDER p017mk0001 | 1335 |  |  | 15 days | 2026-02-12 |  | 2026-02-27 |  | Not Started | Waiting on dependency from Module 3 | 701343 |  | Alex Kim | N. Ortiz | PDF | Case_Report_Forms_CRF_FOLDER_p017mk0001_1343.pdf | Dummy data added for planning demo | Central | 1389
[5 empty] | 5.3.5.1 |  | Listing of Case Report Forms (CRFs TOC) | 1336 |  |  | 8 days | 2026-02-15 | 2026-02-21 | 2026-02-23 |  | In Progress | Pending cross-functional signoff | 701344 | Authoring | Jamie Carter | M. Sullivan | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_1344.zip | Placeholder timeline for reporting test | Central | 1390
[5 empty] | 5.3.5.1 |  | Case Report Forms - eCRFs (by site) for US | 1337 |  |  | 28 days | 2026-02-20 | 2026-02-24 | 2026-03-20 |  | In Progress | Draft in QC review | 701345 | Publishing prep | Casey Rivera | A. Shah | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1345.docx | Placeholder timeline for reporting test | Central | 1391
[5 empty] | 5.3.5.1 |  | Adjudication Packages (if applicable) | 1338 |  |  | 11 days | 2026-02-13 | 2026-02-10 | 2026-02-24 | 2026-02-21 | Completed | Released to archive | 701346 | Publishing QC | Casey Rivera | R. Gupta | DOCX | Adjudication_Packages_if_applicable_1346.docx | Dummy data added for planning demo | Central | 1392
[5 empty] | 5.3.5.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p017mk0001 | 1339 |  |  | 12 days | 2026-02-18 |  | 2026-03-02 |  | Not Started | Resource assignment not yet confirmed | 701347 |  | Jamie Carter | N. Ortiz | XLSX | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_1347.xlsx | Placeholder timeline for reporting test | Central | 1393
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1340 |  |  | 12 days | 2026-02-16 |  | 2026-02-28 |  | Not Started | Resource assignment not yet confirmed | 701348 |  | Sam Brooks | A. Shah | ZIP | Individual_patient_data_listings_Data_tabulation_datasets_SD_1348.zip | Dummy data added for planning demo | Central | 1394
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1341 |  |  | 13 days | 2026-02-22 |  | 2026-03-07 |  | Not Started | Pending authoring start | 701349 |  | Jordan Patel | M. Sullivan | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_1349.xlsx | Sample entry for dashboard validation | Central | 1395
[5 empty] | 5.3.5.1 |  | Study Data Reviewers Guide | 1342 |  |  | 28 days | 2026-02-15 | 2026-02-17 | 2026-03-15 |  | In Progress | Pending cross-functional signoff | 701350 | QC review | Casey Rivera | M. Sullivan | PDF | Study_Data_Reviewers_Guide_1350.pdf | Dummy data added for planning demo | Central | 1396
[5 empty] | 5.3.5.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1343 |  |  | 13 days | 2026-02-22 |  | 2026-03-07 |  | Not Started | Scheduled after current milestone | 701351 |  | Jordan Patel | M. Sullivan | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_1351.docx | Placeholder timeline for reporting test | Central | 1397
[5 empty] | 5.3.5.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p017mk0001 | 1344 |  |  | 19 days | 2026-02-19 |  | 2026-03-10 |  | Not Started | Scheduled after current milestone | 701352 |  | Taylor Chen | R. Gupta | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p017mk0001_1352.csv | Timing estimate is illustrative | Central | 1398
[5 empty] | 5.3.5.1 |  | Analysis datasets - ADAM format | 1345 |  |  | 29 days | 2026-02-18 | 2026-02-23 | 2026-03-19 |  | In Progress | Draft in QC review | 701353 | Authoring | Casey Rivera | M. Sullivan | XLSX | Analysis_datasets_ADAM_format_1353.xlsx | Placeholder timeline for reporting test | Central | 1399
[5 empty] | 5.3.5.1 |  | Data definition for analysis datasets - ADAM format (define file) | 1346 |  |  | 25 days | 2026-02-20 | 2026-02-19 | 2026-03-17 |  | In Progress | Regional review underway | 701354 | QC review | Jordan Patel | A. Shah | XLSX | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1354.xlsx | Timing estimate is illustrative | Central | 1400
[5 empty] | 5.3.5.1 |  | Analysis Data Reviewers Guide | 1347 |  |  | 30 days | 2026-02-18 | 2026-02-21 | 2026-03-20 | 2026-03-18 | Completed | Filed in baseline wave | 701355 | Archive release | Alex Kim | M. Sullivan | XLSX | Analysis_Data_Reviewers_Guide_1355.xlsx | Timing estimate is illustrative | Central | 1401
[5 empty] | 5.3.5.1 |  | Analysis results Metadata (ARM) | 1348 |  |  | 33 days | 2026-02-20 |  | 2026-03-25 |  | Not Started | Scheduled after current milestone | 701356 |  | Alex Kim | R. Gupta | PDF | Analysis_results_Metadata_ARM_1356.pdf | Sample entry for dashboard validation | Central | 1402
[5 empty] | 5.3.5.1 |  | Analysis programs | 1349 |  |  | 11 days | 2026-02-22 |  | 2026-03-05 |  | Not Started | Planned for upcoming wave | 701357 |  | Jamie Carter | R. Gupta | TXT | Analysis_programs_1357.txt | Sample entry for dashboard validation | Central | 1403
[5 empty] | 5.3.5.1 |  | 5.3.5.1 p018mk0001 Study reports and related information of controlled clinical studies pertinent to the claimed indication [no treatment] | 1350 |  |  | 28 days | 2026-02-26 | 2026-02-28 | 2026-03-26 |  | In Progress | Publishing build in progress | 701358 | QC review | Jamie Carter | N. Ortiz | PDF | p018mk0001_Study_reports_and_related_information_of_controll_1358.pdf | Sample entry for dashboard validation | Central | 1404
[5 empty] | 5.3.5.1 |  | Study report [p018mk0001] and related information | 1351 |  |  | 13 days | 2026-02-26 |  | 2026-03-11 |  | Not Started | On hold pending document availability | 701359 |  | Jordan Patel | L. Bennett | DOCX | Study_report_p018mk0001_and_related_information_1359.docx | Placeholder timeline for reporting test | Central | 1405
[5 empty] | 5.3.5.1 |  | P018 SAP | 1352 |  |  | 8 days | 2026-02-27 | 2026-03-03 | 2026-03-07 |  | In Progress | Publishing build in progress | 701360 | QC review | Alex Kim | A. Shah | XLSX | P018_SAP_1360.xlsx | Sample entry for dashboard validation | Central | 1406
[5 empty] | 5.3.5.1 |  | Clinical Study Report | 1353 |  |  | 16 days | 2026-03-02 | 2026-03-01 | 2026-03-18 |  | In Progress | Metadata check in progress | 701361 | QC review | Morgan Lee | R. Gupta | PDF | Clinical_Study_Report_1361.pdf | Sample entry for dashboard validation | Central | 1407
[5 empty] | 5.3.5.1 |  | Case Report Forms - CRF FOLDER p018mk0001 | 1354 |  |  | 22 days | 2026-02-23 |  | 2026-03-17 |  | Not Started | Resource assignment not yet confirmed | 701362 |  | Alex Kim | M. Sullivan | DOCX | Case_Report_Forms_CRF_FOLDER_p018mk0001_1362.docx | Placeholder timeline for reporting test | Central | 1408
[5 empty] | 5.3.5.1 |  | Listing of Case Report Forms (CRFs TOC) | 1355 |  |  | 27 days | 2026-02-27 | 2026-02-28 | 2026-03-26 |  | In Progress | Regional review underway | 701363 | Publishing prep | Jamie Carter | L. Bennett | CSV | Listing_of_Case_Report_Forms_CRFs_TOC_1363.csv | Placeholder timeline for reporting test | Central | 1409
[5 empty] | 5.3.5.1 |  | Case Report Forms - eCRFs (by site) for US | 1356 |  |  | 22 days | 2026-02-26 | 2026-02-26 | 2026-03-20 |  | In Progress | Draft in QC review | 701364 | QC review | Sam Brooks | L. Bennett | DOCX | Case_Report_Forms_eCRFs_by_site_for_US_1364.docx | Timing estimate is illustrative | Central | 1410
[5 empty] | 5.3.5.1 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p018mk0001 | 1357 |  |  | 23 days | 2026-03-04 |  | 2026-03-27 |  | Not Started | Pending authoring start | 701365 |  | Alex Kim | R. Gupta | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_1365.zip | Placeholder timeline for reporting test | Central | 1411
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1358 |  |  | 15 days | 2026-03-05 |  | 2026-03-20 |  | Not Started | Waiting on dependency from Module 3 | 701366 |  | Jamie Carter | M. Sullivan | CSV | Individual_patient_data_listings_Data_tabulation_datasets_SD_1366.csv | Sample entry for dashboard validation | Central | 1412
[5 empty] | 5.3.5.1 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1359 |  |  | 9 days | 2026-02-26 |  | 2026-03-07 |  | Not Started | Planned for upcoming wave | 701367 |  | Jordan Patel | R. Gupta | CSV | Individual_patient_data_listings_Data_definitions_for_data_t_1367.csv | Timing estimate is illustrative | Central | 1413
[5 empty] | 5.3.5.1 |  | Study Data Reviewers Guide | 1360 |  |  | 34 days | 2026-03-06 |  | 2026-04-09 |  | Not Started | Resource assignment not yet confirmed | 701368 |  | Jordan Patel | L. Bennett | PDF | Study_Data_Reviewers_Guide_1368.pdf | Timing estimate is illustrative | Central | 1414
[5 empty] | 5.3.5.1 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1361 |  |  | 17 days | 2026-02-27 |  | 2026-03-16 |  | Not Started | Resource assignment not yet confirmed | 701369 |  | Casey Rivera | M. Sullivan | DOCX | Annotated_Case_Report_Forms_CRFs_SDTM_format_1369.docx | Dummy data added for planning demo | Central | 1415
[5 empty] | 5.3.5.1 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p018mk0001 | 1362 |  |  | 13 days | 2026-03-06 | 2026-03-08 | 2026-03-19 |  | In Progress | Regional review underway | 701370 | Regional alignment | Morgan Lee | R. Gupta | ZIP | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p018mk0001_1370.zip | Timing estimate is illustrative | Central | 1416
[5 empty] | 5.3.5.1 |  | Analysis datasets - ADAM format | 1363 |  |  | 28 days | 2026-03-06 |  | 2026-04-03 |  | Not Started | Resource assignment not yet confirmed | 701371 |  | Taylor Chen | M. Sullivan | CSV | Analysis_datasets_ADAM_format_1371.csv | Dummy data added for planning demo | Central | 1417
[5 empty] | 5.3.5.1 |  | Data definition for analysis datasets - ADAM format (define file) | 1364 |  |  | 22 days | 2026-03-07 |  | 2026-03-29 |  | Not Started | Pending authoring start | 701372 |  | Morgan Lee | A. Shah | CSV | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1372.csv | Placeholder timeline for reporting test | Central | 1418
[5 empty] | 5.3.5.1 |  | Analysis Data Reviewers Guide | 1365 |  |  | 31 days | 2026-03-08 | 2026-03-11 | 2026-04-08 |  | In Progress | Publishing build in progress | 701373 | QC review | Casey Rivera | M. Sullivan | XLSX | Analysis_Data_Reviewers_Guide_1373.xlsx | Dummy data added for planning demo | Central | 1419
[5 empty] | 5.3.5.1 |  | Analysis results Metadata (ARM) | 1366 |  |  | 25 days | 2026-03-03 |  | 2026-03-28 |  | Not Started | Pending authoring start | 701374 |  | Casey Rivera | A. Shah | PDF | Analysis_results_Metadata_ARM_1374.pdf | Sample entry for dashboard validation | Central | 1420
[5 empty] | 5.3.5.1 |  | Analysis programs | 1367 |  |  | 24 days | 2026-03-09 |  | 2026-04-02 |  | Not Started | Planned for upcoming wave | 701375 |  | Alex Kim | M. Sullivan | TXT | Analysis_programs_1375.txt | Timing estimate is illustrative | Central | 1421
[5 empty] | 5.3.5.2 |  | 5.3.5.2 p019mk0001 Study reports and related information of uncontrolled clinical studies | 1368 |  |  | 30 days | 2026-03-06 | 2026-03-09 | 2026-04-05 |  | In Progress | Draft in QC review | 701376 | Authoring | Morgan Lee | A. Shah | DOCX | p019mk0001_Study_reports_and_related_information_of_uncontro_1376.docx | Dummy data added for planning demo | Central | 1422
[5 empty] | 5.3.5.2 |  | Study report [p019mk0001] and related information | 1369 |  |  | 27 days | 2026-03-08 |  | 2026-04-04 |  | Not Started | Scheduled after current milestone | 701377 |  | Jordan Patel | A. Shah | DOCX | Study_report_p019mk0001_and_related_information_1377.docx | Timing estimate is illustrative | Central | 1423
[5 empty] | 5.3.5.2 |  | P019 Summary Report for OMA | 1370 |  |  | 9 days | 2026-03-05 |  | 2026-03-14 |  | Not Started | Resource assignment not yet confirmed | 701378 |  | Taylor Chen | N. Ortiz | PDF | P019_Summary_Report_for_OMA_1378.pdf | Sample entry for dashboard validation | Central | 1424
[5 empty] | 5.3.5.2 |  | Protocol 019-03 | 1371 |  |  | 24 days | 2026-03-09 | 2026-03-07 | 2026-04-02 |  | In Progress | Publishing build in progress | 701379 | QC review | Jamie Carter | L. Bennett | DOCX | Protocol_019_03_1379.docx | Dummy data added for planning demo | Central | 1425
[5 empty] | 5.3.5.2 |  | P019 SAP-01 | 1372 |  |  | 23 days | 2026-03-07 |  | 2026-03-30 |  | Not Started | Resource assignment not yet confirmed | 701380 |  | Morgan Lee | A. Shah | DOCX | P019_SAP_01_1380.docx | Placeholder timeline for reporting test | Central | 1426
[5 empty] | 5.3.5.2 |  | Case Report Forms - CRF FOLDER p019mk0001 | 1373 |  |  | 31 days | 2026-03-11 | 2026-03-11 | 2026-04-11 |  | In Progress | Draft in QC review | 701381 | Authoring | Sam Brooks | M. Sullivan | PDF | Case_Report_Forms_CRF_FOLDER_p019mk0001_1381.pdf | Placeholder timeline for reporting test | Central | 1427
[5 empty] | 5.3.5.2 |  | Listing of Case Report Forms (CRFs TOC) | 1374 |  |  | 12 days | 2026-03-10 |  | 2026-03-22 |  | Not Started | Pending authoring start | 701382 |  | Sam Brooks | A. Shah | ZIP | Listing_of_Case_Report_Forms_CRFs_TOC_1382.zip | Timing estimate is illustrative | Central | 1428
[5 empty] | 5.3.5.2 |  | Case Report Forms - eCRFs (by site) for US | 1375 |  |  | 33 days | 2026-03-10 | 2026-03-10 | 2026-04-12 |  | In Progress | Metadata check in progress | 701383 | Regional alignment | Alex Kim | L. Bennett | PDF | Case_Report_Forms_eCRFs_by_site_for_US_1383.pdf | Timing estimate is illustrative | Central | 1429
[5 empty] | 5.3.5.2 |  | Individual Patient Data Listings (CRTs) - TABULATIONS FOLDER p019mk0001 | 1376 |  |  | 10 days | 2026-03-08 |  | 2026-03-18 |  | Not Started | On hold pending document availability | 701384 |  | Jordan Patel | R. Gupta | ZIP | Individual_Patient_Data_Listings_CRTs_TABULATIONS_FOLDER_p01_1384.zip | Placeholder timeline for reporting test | Central | 1430
[5 empty] | 5.3.5.2 |  | Individual patient data listings - Data tabulation datasets - SDTM format | 1377 |  |  | 11 days | 2026-03-15 |  | 2026-03-26 |  | Not Started | Pending authoring start | 701385 |  | Casey Rivera | L. Bennett | XLSX | Individual_patient_data_listings_Data_tabulation_datasets_SD_1385.xlsx | Timing estimate is illustrative | Central | 1431
[5 empty] | 5.3.5.2 |  | Individual patient data listings - Data definitions for data tabulation datasets - SDTM format (define file) | 1378 |  |  | 8 days | 2026-03-14 | 2026-03-18 | 2026-03-22 |  | In Progress | Draft in QC review | 701386 | Authoring | Jamie Carter | N. Ortiz | XLSX | Individual_patient_data_listings_Data_definitions_for_data_t_1386.xlsx | Dummy data added for planning demo | Central | 1432
[5 empty] | 5.3.5.2 |  | Study Data Reviewers Guide | 1379 |  |  | 20 days | 2026-03-12 | 2026-03-13 | 2026-04-01 |  | In Progress | Regional review underway | 701387 | QC review | Morgan Lee | M. Sullivan | DOCX | Study_Data_Reviewers_Guide_1387.docx | Sample entry for dashboard validation | Central | 1433
[5 empty] | 5.3.5.2 |  | Annotated Case Report Forms (CRFs) - SDTM format | 1380 |  |  | 33 days | 2026-03-12 |  | 2026-04-14 |  | Not Started | Resource assignment not yet confirmed | 701388 |  | Sam Brooks | M. Sullivan | PDF | Annotated_Case_Report_Forms_CRFs_SDTM_format_1388.pdf | Sample entry for dashboard validation | Central | 1434
[5 empty] | 5.3.5.2 |  | Analysis Data Sets and Programs - ANALYSIS FOLDER p019mk0001 | 1381 |  |  | 12 days | 2026-03-17 |  | 2026-03-29 |  | Not Started | Scheduled after current milestone | 701389 |  | Morgan Lee | R. Gupta | CSV | Analysis_Data_Sets_and_Programs_ANALYSIS_FOLDER_p019mk0001_1389.csv | Timing estimate is illustrative | Central | 1435
[5 empty] | 5.3.5.2 |  | Analysis datasets - ADAM format | 1382 |  |  | 13 days | 2026-03-12 | 2026-03-16 | 2026-03-25 |  | In Progress | Pending cross-functional signoff | 701390 | Regional alignment | Alex Kim | M. Sullivan | XLSX | Analysis_datasets_ADAM_format_1390.xlsx | Timing estimate is illustrative | Central | 1436
[5 empty] | 5.3.5.2 |  | Data definition for analysis datasets - ADAM format (define file) | 1383 |  |  | 14 days | 2026-03-12 |  | 2026-03-26 |  | Not Started | Resource assignment not yet confirmed | 701391 |  | Jamie Carter | A. Shah | ZIP | Data_definition_for_analysis_datasets_ADAM_format_define_fil_1391.zip | Sample entry for dashboard validation | Central | 1437
[5 empty] | 5.3.5.2 |  | Analysis Data Reviewers Guide | 1384 |  |  | 27 days | 2026-03-19 |  | 2026-04-15 |  | Not Started | On hold pending document availability | 701392 |  | Jamie Carter | N. Ortiz | XLSX | Analysis_Data_Reviewers_Guide_1392.xlsx | Timing estimate is illustrative | Central | 1438
[5 empty] | 5.3.5.2 |  | Analysis Results Metadata (ARM) | 1385 |  |  | 35 days | 2026-03-21 | 2026-03-21 | 2026-04-25 |  | In Progress | Awaiting final source document | 701393 | Authoring | Taylor Chen | M. Sullivan | XLSX | Analysis_Results_Metadata_ARM_1393.xlsx | Dummy data added for planning demo | Central | 1439
[5 empty] | 5.3.5.2 |  | Analysis programs | 1386 |  |  | 24 days | 2026-03-17 |  | 2026-04-10 |  | Not Started | Waiting on dependency from Module 3 | 701394 |  | Taylor Chen | M. Sullivan | ZIP | Analysis_programs_1394.zip | Placeholder timeline for reporting test | Central | 1440
[5 empty] | 5.3.5 |  | 5.3.5 Reports of efficacy and safety studies [hypercholest] | 1387 |  |  | 41 days | 2026-03-19 | 2026-03-19 | 2026-04-29 |  | In Progress | Draft in QC review | 701395 | Regional alignment | Casey Rivera | N. Ortiz | PDF | Reports_of_efficacy_and_safety_studies_hypercholest_1395.pdf | Timing estimate is illustrative | Central | 1441
[5 empty] | 5.3.5 |  | 5.3.5 Summary of Main Efficacy Results (EU) | 1388 |  |  | 53 days | 2026-03-16 | 2026-03-21 | 2026-05-08 |  | In Progress | Draft in QC review | 701396 | Regional alignment | Sam Brooks | M. Sullivan | PDF | Summary_of_Main_Efficacy_Results_EU_1396.pdf | Placeholder timeline for reporting test | Central | 1442
[5 empty] | 5.3.5.3 |  | 5.3.5.3 Reports of analyses of data from more than one study | 1389 |  |  | 12 days | 2026-03-23 |  | 2026-04-04 |  | Not Started | Waiting on dependency from Module 3 | 701397 |  | Alex Kim | A. Shah | PDF | Reports_of_analyses_of_data_from_more_than_one_study_1397.pdf | Dummy data added for planning demo | Central | 1443
[5 empty] | 5.3.5.3.1 |  | 5.3.5.3.1 ClinPharm Pooled Summary of Safety (CPSOS) | 1390 |  |  | 34 days | 2026-03-16 |  | 2026-04-19 |  | Not Started | Planned for upcoming wave | 701398 |  | Alex Kim | R. Gupta | PDF | ClinPharm_Pooled_Summary_of_Safety_CPSOS_1398.pdf | Dummy data added for planning demo | Central | 1444
[5 empty] | 5.3.5.3.1 |  | Clin Pharm Summary of Safety | 1391 |  |  | 29 days | 2026-03-18 | 2026-03-17 | 2026-04-16 |  | In Progress | Publishing build in progress | 701399 |  | Sam Brooks | R. Gupta | PDF | Clin_Pharm_Summary_of_Safety_1399.pdf | Dummy data added for planning demo | Central | 1445
[5 empty] | 5.3.5.3.1 |  | Analysis Data Sets and Programs | 1392 |  |  | 18 days | 2026-03-20 | 2026-03-19 | 2026-04-07 |  | In Progress | Pending cross-functional signoff | 701400 | Publishing prep | Jamie Carter | R. Gupta | CSV | Analysis_Data_Sets_and_Programs_1400.csv | Timing estimate is illustrative | Central | 1446
[5 empty] | 5.3.5.3.1 |  | Analysis datasets - ADAM format or Legacy format( Choose the correct Data format with team) | 1393 |  |  | 24 days | 2026-03-19 |  | 2026-04-12 |  | Not Started | Resource assignment not yet confirmed | 701401 |  | Sam Brooks | M. Sullivan | ZIP | Analysis_datasets_ADAM_format_or_Legacy_format_Choose_the_co_1401.zip | Sample entry for dashboard validation | Central | 1447
[5 empty] | 5.3.5.3.1 |  | Data definition for analysis datasets - ADAM format or Legacy format( Choose the correct Data format with team) | 1394 |  |  | 22 days | 2026-03-23 | 2026-03-22 | 2026-04-14 |  | In Progress | Awaiting final source document | 701402 | QC review | Jamie Carter | R. Gupta | ZIP | Data_definition_for_analysis_datasets_ADAM_format_or_Legacy__1402.zip | Dummy data added for planning demo | Central | 1448
[5 empty] | 5.3.5.3.2 |  | 5.3.5.3.2 Integrated Summary of Efficacy (ISE) | 1395 |  |  | 19 days | 2026-03-24 | 2026-03-30 | 2026-04-12 |  | In Progress | Publishing build in progress | 701403 | Regional alignment | Alex Kim | A. Shah | PDF | Integrated_Summary_of_Efficacy_ISE_1403.pdf | Dummy data added for planning demo | Central | 1449
[5 empty] | 5.3.5.3.2 |  | Integrated Summary of Efficacy (ISE) | 1396 |  |  | 35 days | 2026-03-24 | 2026-03-27 | 2026-04-28 |  | In Progress | Regional review underway | 701404 | Publishing prep | Alex Kim | R. Gupta | DOCX | Integrated_Summary_of_Efficacy_ISE_1404.docx | Timing estimate is illustrative | Central | 1450
[5 empty] | 5.3.5.3.2 |  | Analysis Data Sets and Programs | 1397 |  |  | 19 days | 2026-03-27 |  | 2026-04-15 |  | Not Started | Pending authoring start | 701405 |  | Casey Rivera | N. Ortiz | CSV | Analysis_Data_Sets_and_Programs_1405.csv | Timing estimate is illustrative | Central | 1452
[5 empty] | 5.3.5.3.2 |  | Analysis datasets - ADAM format | 1398 |  |  | 18 days | 2026-03-26 |  | 2026-04-13 |  | Not Started | Waiting on dependency from Module 3 | 701406 |  | Morgan Lee | N. Ortiz | ZIP | Analysis_datasets_ADAM_format_1406.zip | Sample entry for dashboard validation | Central | 1453
[5 empty] | 5.3.5.3.2 |  | Data definition for analysis datasets - ADAM format | 1399 |  |  | 24 days | 2026-03-22 |  | 2026-04-15 |  | Not Started | On hold pending document availability | 701407 |  | Casey Rivera | A. Shah | CSV | Data_definition_for_analysis_datasets_ADAM_format_1407.csv | Timing estimate is illustrative | Central | 1454
[5 empty] | 5.3.5.3.2 |  | Analysis programs | 1400 |  |  | 20 days | 2026-03-26 |  | 2026-04-15 |  | Not Started | Resource assignment not yet confirmed | 701408 |  | Taylor Chen | L. Bennett | TXT | Analysis_programs_1408.txt | Dummy data added for planning demo | Central | 1455
[5 empty] | 5.3.5.3.3 |  | 5.3.5.3.3 Integrated Summary of Safety (ISS) | 1401 |  |  | 12 days | 2026-03-31 | 2026-03-29 | 2026-04-12 |  | In Progress | Metadata check in progress | 701409 | Authoring | Alex Kim | L. Bennett | DOCX | Integrated_Summary_of_Safety_ISS_1409.docx | Dummy data added for planning demo | Central | 1456
[5 empty] | 5.3.5.3.3 |  | Integrated Summary of Safety (ISS) | 1402 |  |  | 23 days | 2026-04-01 |  | 2026-04-24 |  | Not Started | Waiting on dependency from Module 3 | 701410 |  | Sam Brooks | R. Gupta | PDF | Integrated_Summary_of_Safety_ISS_1410.pdf | Sample entry for dashboard validation | Central | 1457
[5 empty] | 5.3.5.3.3 |  | Analysis Data Sets and Programs - iss | 1403 |  |  | 35 days | 2026-03-31 |  | 2026-05-05 |  | Not Started | Resource assignment not yet confirmed | 701411 |  | Jordan Patel | L. Bennett | ZIP | Analysis_Data_Sets_and_Programs_iss_1411.zip | Timing estimate is illustrative | Central | 1459
[5 empty] | 5.3.5.3.3 |  | Analysis datasets - ADAM format | 1404 |  |  | 27 days | 2026-04-02 | 2026-04-03 | 2026-04-29 | 2026-04-28 | Completed | Filed in baseline wave | 701412 | Publishing QC | Jordan Patel | L. Bennett | ZIP | Analysis_datasets_ADAM_format_1412.zip | Placeholder timeline for reporting test | Central | 1460
[5 empty] | 5.3.5.3.3 |  | Data definition for analysis datasets - ADAM format | 1405 |  |  | 23 days | 2026-03-28 |  | 2026-04-20 |  | Not Started | On hold pending document availability | 701413 |  | Sam Brooks | R. Gupta | CSV | Data_definition_for_analysis_datasets_ADAM_format_1413.csv | Placeholder timeline for reporting test | Central | 1461
[5 empty] | 5.3.5.3.3 |  | Analysis programs | 1406 |  |  | 7 days | 2026-03-28 | 2026-04-01 | 2026-04-04 |  | In Progress | Regional review underway | 701414 | QC review | Morgan Lee | M. Sullivan | TXT | Analysis_programs_1414.txt | Timing estimate is illustrative | Central | 1462
[5 empty] | 5.3.5.3.3 |  | Analysis Data Reviewer Guide | 1407 |  |  | 16 days | 2026-03-28 |  | 2026-04-13 |  | Not Started | Waiting on dependency from Module 3 | 701415 |  | Alex Kim | L. Bennett | XLSX | Analysis_Data_Reviewer_Guide_1415.xlsx | Sample entry for dashboard validation | Central | 1463
[5 empty] | 5.3.5.3 |  | 5.3.5.3 Modeling & Simulation Reports | 1408 |  |  | 27 days | 2026-03-31 | 2026-04-03 | 2026-04-27 |  | In Progress | Metadata check in progress | 701416 | Publishing prep | Jamie Carter | A. Shah | PDF | Modeling_Simulation_Reports_1416.pdf | Sample entry for dashboard validation | Central | 1464
[5 empty] | 5.3.5.3 |  | 5.3.5.3 Modeling & Simulation Report #1 | 1409 |  |  | 30 days | 2026-03-31 |  | 2026-04-30 |  | Not Started | Waiting on dependency from Module 3 | 701417 |  | Taylor Chen | N. Ortiz | DOCX | Modeling_Simulation_Report_1_1417.docx | Timing estimate is illustrative | Central | 1465
[5 empty] | 5.3.5.3 |  | 5.3.5.3 Modeling Dataset #1 | 1410 |  |  | 28 days | 2026-03-29 | 2026-04-01 | 2026-04-26 | 2026-04-26 | Completed | Released to archive | 701418 | Archive release | Jamie Carter | R. Gupta | ZIP | Modeling_Dataset_1_1418.zip | Dummy data added for planning demo | Central | 1466
[5 empty] | 5.3.5.3 |  | 5.3.5.3 Modeling & Simulation Report #2 | 1411 |  |  | 30 days | 2026-04-01 | 2026-04-02 | 2026-05-01 |  | In Progress | Pending cross-functional signoff | 701419 |  | Taylor Chen | N. Ortiz | DOCX | Modeling_Simulation_Report_2_1419.docx | Placeholder timeline for reporting test | Central | 1467
[5 empty] | 5.3.5.3 |  | 5.3.5.3 Modeling Dataset #2 | 1412 |  |  | 21 days | 2026-04-01 |  | 2026-04-22 |  | Not Started | On hold pending document availability | 701420 |  | Alex Kim | R. Gupta | XLSX | Modeling_Dataset_2_1420.xlsx | Placeholder timeline for reporting test | Central | 1468
[5 empty] | 5.3.5.4 |  | 5.3.5.4 Other Study reports and related information | 1413 |  |  | 34 days | 2026-03-30 | 2026-03-31 | 2026-05-03 |  | In Progress | Awaiting final source document | 701421 | QC review | Jamie Carter | R. Gupta | PDF | Other_Study_reports_and_related_information_1421.pdf | Placeholder timeline for reporting test | Central | 1469
[5 empty] | 5.3.5.4 |  | BIMO Deliverables (CDER Only) Previously call OSI | 1414 |  |  | 35 days | 2026-04-05 |  | 2026-05-10 |  | Not Started | Scheduled after current milestone | 701422 |  | Sam Brooks | N. Ortiz | PDF | BIMO_Deliverables_CDER_Only_Previously_call_OSI_1422.pdf | Dummy data added for planning demo | Central | 1470
[5 empty] | 5.3.5.4 |  | Data Listing Dataset | 1415 |  |  | 10 days | 2026-04-02 |  | 2026-04-12 |  | Not Started | Scheduled after current milestone | 701423 |  | Taylor Chen | L. Bennett | ZIP | Data_Listing_Dataset_1423.zip | Dummy data added for planning demo | Central | 1471
[5 empty] | 5.3.5.4 |  | Data definition for the BIMO deliverables | 1416 |  |  | 8 days | 2026-04-09 |  | 2026-04-17 |  | Not Started | Pending authoring start | 701424 |  | Jordan Patel | M. Sullivan | PDF | Data_definition_for_the_BIMO_deliverables_1424.pdf | Timing estimate is illustrative | Central | 1473
[5 empty] | 5.3.5.3 |  | 5.3.5.3 iSAP - safety | 1417 |  |  | 13 days | 2026-04-09 | 2026-04-12 | 2026-04-22 |  | In Progress | Awaiting final source document | 701425 | Authoring | Casey Rivera | A. Shah | XLSX | iSAP_safety_1425.xlsx | Dummy data added for planning demo | Central | 1474
[5 empty] | 5.3.5.3 |  | 5.3.5.3 iSAP - efficacy | 1418 |  |  | 31 days | 2026-04-03 |  | 2026-05-04 |  | Not Started | Resource assignment not yet confirmed | 701426 |  | Casey Rivera | R. Gupta | DOCX | iSAP_efficacy_1426.docx | Dummy data added for planning demo | Central | 1475
[5 empty] | 5.4 |  | 5.4 Literature References | 1419 |  |  | 109 days | 2026-04-10 |  | 2026-07-28 |  | Not Started | Resource assignment not yet confirmed | 701427 |  | Sam Brooks | M. Sullivan | PDF | Literature_References_1427.pdf | Dummy data added for planning demo | Central | 1476
[5 empty] | 5.4 |  | 5.4 Literature References - EU RMP | 1420 |  |  | 71 days | 2026-04-06 |  | 2026-06-16 |  | Not Started | Planned for upcoming wave | 701428 |  | Taylor Chen | A. Shah | DOCX | Literature_References_EU_RMP_1428.docx | Sample entry for dashboard validation | Central | 1477
[5 empty] | 5.4 |  | 5.4 Literature References - Core RMP | 1421 |  |  | 115 days | 2026-04-05 | 2026-04-11 | 2026-07-29 |  | In Progress | Draft in QC review | 701429 | QC review | Sam Brooks | L. Bennett | DOCX | Literature_References_Core_RMP_1429.docx | Sample entry for dashboard validation | Central | 1478
|  | Filing Milestones | [5 empty] | 1422 |  |  | 255 days | 2026-04-12 |  | 2026-12-23 |  | Not Started | Resource assignment not yet confirmed | 701430 |  | Alex Kim | L. Bennett |  |  |  | Central | 1479
|  |  | Plan Baseline |  |  |  | Plan Baseline | 1423 |  |  | 19 days | 2026-04-05 |  | 2026-04-24 |  | Not Started | Scheduled after current milestone | 701431 |  | Morgan Lee | M. Sullivan | PDF | Plan_Baseline_1431.pdf | Timing estimate is illustrative | Central | 1480
|  |  | Plan Complete |  |  |  | Plan Complete | 1424 |  |  | 1 days | 2026-04-06 | 2026-04-11 | 2026-04-07 | 2026-04-13 | Completed |  | 701432 | Archive release | Alex Kim | M. Sullivan | PDF | Plan_Complete_1432.pdf | Timing estimate is illustrative | Central | 1481
|  |  | Publishing Complete |  |  |  | Publishing Complete | 1425 |  |  | 0 days | 2026-04-10 | 2026-04-10 | 2026-04-10 |  | In Progress | Publishing build in progress | 701433 | QC review | Jordan Patel | N. Ortiz | PDF | Publishing_Complete_1433.pdf | Timing estimate is illustrative | Central | 1482
|  |  | Agency Submission |  |  |  | Agency Submission | 1426 |  |  | 5 days | 2026-04-08 | 2026-04-12 | 2026-04-13 |  | In Progress | Draft in QC review | 701434 | Authoring | Morgan Lee | A. Shah | XLSX | Agency_Submission_1434.xlsx | Placeholder timeline for reporting test | Central | 1483
|  |  | Agency Decision |  |  |  | Agency Decision | 1427 |  |  | 0 days | 2026-04-10 |  | 2026-04-10 |  | Not Started | Waiting on dependency from Module 3 | 701435 |  | Sam Brooks | A. Shah | DOCX | Agency_Decision_1435.docx | Timing estimate is illustrative | Central | 1484
720
1043217